## A
WBS # | WBS Nomenclature | Appendix | WBS Definition
1 | Aircraft System | APPENDIX A: AIRCRAFT SYSTEMS | A.4.1 Aircraft System. The complex of equipment (hardware/software), data, services, and facilities required to develop, produce, and support air vehicles. Includes, for example: a. Those employing manned fixed, movable, rotary, or compound wing b. Those unmanned air vehicles designed for powered or unpowered flight (i.e., gliders)
1.1 | Aircraft System, Integration, Assembly, Test, and Checkout | APPENDIX A: AIRCRAFT SYSTEMS | A.4.2 Aircraft System Integration, Assembly, Test, and Checkout. The integration, assembly, test, and checkout element includes all efforts as identified in Appendix K: Common Elements, Work Breakdown Structure and Definitions, to provide a complete aircraft system.
1.2 | Air Vehicle | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3 Air Vehicle. The complete flying aircraft. It includes the design, development, and production of complete units (i.e., the prototype or operationally configured units, which satisfy the requirements of their applicable specification(s), regardless of end use). Includes, for example: a. Airframe, propulsion, vehicles subsystems, avionics systems and all other installed equipment (except those equipment considered as payloads, those are captured within their own Level 2 WBS element)
1.2.1 | Air Vehicle Integration, Assembly, Test, and Checkout | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.1 Air Vehicle Integration, Assembly, Test, and Checkout. The integration, assembly, test, and checkout element includes all efforts as identified in Appendix K: Common Elements, Work Breakdown Structure and Definitions, to provide a complete air vehicle.
1.2.2 | Airframe | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.2 Airframe. The assembled structural and aerodynamic components of the air vehicle that support subsystems essential to designated mission requirements. Includes, for example: a. Basic structure: fuselage, wing, empennage, and nacelle b. All administrative and technical engineering labor to perform integration of Level 4 airframe elements; development of engineering layouts; determination of overall design characteristics; and determination of requirements of design review Excludes, for example: a. All effort associated with vehicle subsystems, avionics, and other Level 3 elements, and their integration into the airframe
1.2.2.1 | Airframe Integration, Assembly, Test, and Checkout | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.2.1 Airframe Integration, Assembly, Test, and Checkout. The integration, assembly, test, and checkout element includes all efforts as identified in Appendix K: Common Elements, Work Breakdown Structure and Definitions, to provide a complete airframe. NOTE: When rate tooling is deliverable to the Government, it should be shown at the next lower level breakout of integration, assembly, test, and checkout. Included in this element are the efforts required to provide the integration, assembly, test, and checkout of the major airframe structures (fuselage, wing, empennage, nacelle, and other airframe) including modification installation. Included in this effort is all administrative and technical engineering labor to perform integration of Level 4 airframe elements. Includes, for example: a. Overall airframe design and producibility engineering b. Detailed production design; acoustic and noise analysis c. Loads analysis; stress analysis on interfacing airframe elements and all subsystems d. Design maintenance effort and development of functional test procedures e. Coordination of engineering master drawings and consultation with test and manufacturing groups f. Tooling planning, design, and fabrication of basic and rate tools and functional test equipment, as well as the maintenance of such equipment g. Production scheduling and expediting h. Joining or installation of structures such as racks, mounts, etc. i. Installation of wiring, ducting, engines, and miscellaneous equipment, and painting j. Set up, conduct, and review of testing assembled components or subsystems prior to installation Excludes, for example: a. All integration, assembly, test, and checkout activities associated with non-airframe Level 3 elements
1.2.2.2 | Fuselage | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.2.2 Fuselage. The structural airframe encompassing the forward, center, and aft fuselage sections of the aircraft. Includes, for example: a. Structural fuselage section for the forward, center, and aft fuselage sections to include the main and secondary structures b. Efforts required to splice the forward, center, and aft sections c. Windshield/canopy assembly d. Radome e. Access doors f. Mounting provisions for mission peculiar avionics and armament/weapons delivery systems
1.2.2.3 | Wing | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.2.3 Wing. The structure used to produce lift for flight through the air. Includes, for example: a. Wing torque box, inner and outer wing panels, leading edge extension wing tip, movable control surfaces to include ailerons and leading and trailing edge flaps, attach fittings for pylons, wing fold mechanism, installation of airframe related subsystems, and installation of flight test instrumentation b. Fitting for store stations c. Material for sealing the integral fuel tanks d. Provisions for the electrical, hydraulic, fuel, aerodynamic flight controls, etc. Excludes, for example: a. Efforts for the structural splicing of the wing to the fuselage as provided by the Airframe Integration, Assembly, Test, and Checkout.
1.2.2.4 | Empennage | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.2.4 Empennage. The structural tail group encompassing the fin, stabilizer, and rudder as well as provisions for electrical wiring, plumbing, control linkages, antennae, and associated equipment. Includes, for example: a. Structural stabilators, vertical tails, rudders, installation of airframe related subsystems, and installation of flight test instrumentation b. Tail boom for rotary wing
1.2.2.5 | Nacelle | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.2.5 Nacelle. The streamlined enclosure, separate from the fuselage, used for sheltering the crew, cargo, or housing an engine.
1.2.2.6 | Other Airframe Components 1...n (Specify) | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.2.6 Other Airframe Components 1...n (Specify). This element should be replaced with other product-oriented airframe components that are either not listed above or that cannot be categorized into one of the above elements. Each additional element is to be clearly identified and defined.
1.2.3 | Propulsion | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.3 Propulsion. That portion of the air vehicle that pertains to installed equipment (propulsion unit and other propulsion) to provide power/thrust to propel the aircraft through all phases of powered flight. Includes, for example: a. The engine as a propulsion unit within itself (e.g., reciprocating, turbo with or without afterburner, or other type propulsion) suitable for integration with the airframe b. Thrust reversers, thrust vector devices, nozzles, transmissions, gear boxes, and engine control units, if furnished as integral to the propulsion unit c. Other propulsion equipment required in addition to the engine but not furnished as an integral part of the engine, such as booster units d. The design, development, production, and assembly efforts to provide the propulsion unit as an entity Excludes, for example: a. All effort directly associated with the integration, assembly, test, and checkout of these elements into the air vehicle b. All ancillary equipment that are not an integral part of the engine required to provide an operational primary power source—air inlets, instruments, controls, etc. NOTE: For lower level information, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.2.4 | Vehicle Subsystems | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.4 Vehicle Subsystems. The collection of core non-avionics subsystems.
1.2.4.1 | Vehicle Subsystem Integration, Assembly, Test, and Checkout | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.4.1 Vehicle Subsystems Integration, Assembly, Test, and Checkout. This element includes all effort of technical and functional activities associated with the design, development, and production of mating surfaces, structures, equipment, parts, materials, and software required to assemble and test the vehicle subsystem parts and subsystems equipment (hardware/software) elements. Reference Appendix K: Common Elements, Work Breakdown Structure and Definitions for further detail.
1.2.4.2 | Flight Control Subsystem | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.4.2 Flight Control Subsystem. Primary and secondary mechanical devices and automatic equipment installed in the air vehicle when used with control surfaces, to control the flight path of the air vehicle as well as to provide additional lift, drag and trim effect. Includes, for example: a. Primary and secondary mechanical controls, linkage, and control surface actuators for ailerons, rudders, stabilators, leading edge flaps, trailing edge flaps, and speed brakes, which are used to control the flight path of the air vehicle and provide additional lift, drag, and trim effect. Excludes, for example: a. Structural control surfaces, ailerons, rudder, stabilizer, etc. included in airframe as well as the installation of flight control subsystems into the appropriate basis structures element NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.2.4.3 | Auxiliary Power Subsystem | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.4.3 Auxiliary Power Subsystem. The equipment that performs engine start up on the ground, emergency starting during flight, ground checkout operations of aircraft accessories, and power takeoff for hydraulic pumps and electrical generator system and fuel motive flow pumps. Includes, for example: a. Power takeoff shafts and oil cooling lines b. Auxiliary power unit (APU) c. Airframe mounted accessory drive (AMAD) d. Air turbine starter e. Secondary power, furnishings—cargo, etc. NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.2.4.4 | Hydraulic Subsystem | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.4.4 Hydraulic Subsystem. This system provides hydraulic power for the actuation of landing/launching gear subsystems, in-flight refueling probe, gun drive and flight control surfaces. Includes, for example: a. Pumps, reservoirs, accumulators, valves, regulators and associated plumbing distribution systems to provide hydraulic power b. Hydraulic tubing, check valves, etc., which interconnect the hydraulic equipment NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.2.4.5 | Electrical Subsystem | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.4.5 Electrical Subsystem. Equipment installed to provide electrical power function, the AC and DC distribution of this power supply and the provision for exterior lighting. Includes, for example: a. Wire bundles and miscellaneous electrical parts, which provide the electrical power function, the AC and DC distribution of this power supply and exterior lighting in the center fuselage, aft fuselage and vertical tail b. Generator system, battery system, a transformer rectifier unit and power contactors c. Power relays, circuit breakers and distribution systems between electronic mission equipment NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.2.4.6 | Crew Station Subsystem | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.4.6 Crew Station Subsystem. The provisions and space allocated to the human component of the weapon system that allow performance of specific functions to ensure mission success. Aircraft system human interfaces and components that sustain and protect the human operators, troops, and passengers. Includes, for example: a. Life support systems; flight clothing, head protection, noise attenuation systems, communication systems, anti-exposure systems, cooling systems, gravity onset protective systems, laser threat protection, chemical/biological protection, physiological monitoring systems, body armor, oxygen systems, survival equipment, personal flotation devices, flotation platforms, survival radios/beacons b. Escape systems; ejection seats, canopy/hatch removal or penetration systems, sequencing systems, restraint systems, seat survival kits, parachutes, emergency exits, slides, crashworthy seats, armored seats, personal connection systems c. Crash protection devices; includes attenuating seats, airbag systems and inflatable restraints d. Search and rescue equipment e. Aero-medical equipment (AE) f. Canopy/wind screen systems; transparencies, seals, actuators, frames g. Crew, passenger, and troop compartment geometry and design, secondary structure, interior/exterior lighting, seat installations, consoles, instrument panels, glare shields, personal cargo stowage, and waste management systems h. Display/control interfaces; display/control locations and configuration, display symbology definition, helmet mounted devices, lighting, switches, pedals, control grips such as those for the stick/yoke, throttle, cyclic and collective i. Human interface; human factors design features, speech intelligibility, and anthropometry for air vehicle interface, control and mission tasks j. Crew environment habitability considerations; acoustical noise, radiation hazard, thermal environment, relative humidity, air velocity, and pressurization k. Integration tests related to human interface with the air vehicle, including part task and full mission simulations, workload and situational awareness evaluations, life support system man rating, ejection tests, bailout or emergency egress, and lighting mockup evaluations Excludes, for example: a. Primary structure supporting seat installations and restraints covered under the airframe WBS element b. Display hardware/software covered under the data display and controls WBS element c. Wiring and plumbing for aircrew support covered under the airframe or other Level 4 vehicle systems WBS elements NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.2.4.7 | Environmental Control Subsystem | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.4.7 Environmental Control Subsystem. Environmental equipment and distribution systems on board the air vehicle for air conditioning and cooling equipment compartments, pressurization of seals, fuel tanks and anti-icing. The distribution system provides for air ducts, cooling lines, and other plumbing required in supplying air and other cooling media from supply sources to the controlled environment. Includes, for example: a. Environmental and distribution systems on board the air vehicle to include fabricated air ducts, cooling lines and other plumbing required for cockpit air conditioning and pressurization (manned aircraft only) b. Equipment compartment and individual air units air conditioning, pressurization of canopy seal (manned aircraft only), and fuel tanks c. Bleed air for the gun gas purging; and windshield anti-icing and defogging subsystems (manned aircraft only) d. Air refrigeration system, liquid cooling system, air flow regulation system, and a suit ventilation system (manned aircraft only) e. Environmental control, racks, mounts, intersystem cables, distribution boxes, etc., which are inherent to, and non-separable from the assembled structure NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.2.4.8 | Fuel Subsystem | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.4.8 Fuel Subsystem. Equipment and distribution systems installed in the air vehicle to provide fuel to the engines and the auxiliary power unit, including associated functions such as fuel pressurization, venting, gauging, defueling, etc. Includes, for example: a. Equipment and distribution systems to provide fuel to the engines b. Associated functions included in the system are fuel storage, pressurization, venting, gauging, defueling, and in-flight refueling c. Rotary or manned pylons, air induction system, thrust reversers, thrust vector devices, starters, exhausts, fuel management, inlet control system d. Fuel lines, plumbing, etc., which interconnect the fuel subsystem equipment and storage cell in the air vehicle NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.2.4.9 | Landing Gear | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.4.9 Landing Gear. The structural and mechanical gear and associated equipment, including doors, for maneuvering of the air vehicle while on the ground, the devices for extension, retraction, and locking this gear, and the mechanical devices for arresting the air vehicle. Includes, for example: a. Alighting gear; tires, tubes, wheels, brakes, hydraulics, etc. b. Main landing gears, nose landing gear c. Arresting hook system and related doors and mechanisms
1.2.4.10 | Rotor Group | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.4.10 Rotor Group. Items that impart the pitch, yaw, roll, and thrust forces, which provide the lift and direction for Air Vehicle powered flight for rotary aircraft. Includes, for example: a. Main rotor blade b. Main rotor head c. Tail rotor blade
1.2.4.11 | Drive Group | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.4.11 Drive System. Those items that pertain to the engine control units such as transmissions and gear boxes. Includes, for example: a. Dynamic systems; transmissions, gear boxes, propellers, if not furnished as an integral part of the propulsion unit
1.2.4.12 | Vehicle Subsystem Software Release 1...n (Specify) | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.4.12 Vehicle Subsystems Software Release 1...n. All vehicle subsystem software not associated with a specific Level 4 element. NOTE 1: Refer to Appendix B, Electronic/Generic Systems for further breakout and definitions for Software.
1.2.4.13 | Other Subsystems 1...n (Specify) | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.4.13 Other Vehicle Subsystems 1...n (Specify). This element should be replaced with other product-oriented vehicle subsystems that are either not listed above or that cannot be categorized into one of the above elements. Each additional element is to be clearly identified and defined. NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.2.5 | Avionics | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.5 Avionics. Mission equipment embedded on board the air vehicle, which is primarily electronic in nature.
1.2.5.1 | Avionics Integration, Assembly, Test, and Checkout | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.5.1 Avionics Integration, Assembly, Test, and Checkout. This element includes all effort of technical and functional activities associated with the design, development, and production of mission equipment, parts, materials, and software required to assemble and test the avionics suite parts and subsystems equipment (hardware/software) elements. Reference Appendix K: Common Elements, Work Breakdown Structure and Definitions for further detail.
1.2.5.2 | Communication/Identification | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.5.2 Communication/Identification. That equipment (hardware/software) installed in the air vehicle for communications and identification purposes. Includes, for example: a. Intercoms, radio system(s), identification equipment (IFF), data links, and control boxes associated with the specific equipment b. Integral communication, navigation, and identification package (if used) Excludes, for example: a. Speech intelligibility work performed under the Crew Station WBS element b. Survival/radios/beacons included under the Crew Station WBS element c. Aircrew mounted communication components included under the Crew Station WBS element NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.2.5.3 | Navigation/Guidance | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.5.3 Navigation/Guidance. That equipment (hardware/software) installed in the air vehicle to perform the navigational guidance function. Includes, for example: a. Radio, or other essential navigation equipment, radar altimeter, direction finding set, doppler compass, computer, and other equipment homogeneous to the navigation/guidance function
1.2.5.4 | Mission Computer/Processing | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.5.4 Mission Computer/Processing. The master data processing unit(s) and memory devices responsible for coordinating and directing the major avionic mission systems. It should include any data bus used to pass information across the various components of avionics mission systems. NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.2.5.5 | Fire Control | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.5.5 Fire Control. That equipment (hardware/software) installed in the air vehicle, which provides the intelligence necessary for weapons delivery such as bombing, launching, and firing. Includes, for example: a. Radars and other sensors b. Apertures/antennas, if integral to the fire control system, necessary for search, target identification, rendezvous, and/or tracking c. Self-contained navigation and air data systems d. Dedicated displays, scopes, or sights e. Bombing computer and control and safety devices NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.2.5.6 | Data Display and Controls | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.5.6 Data Display and Controls. The equipment (hardware/software) that visually presents processed data by specially designed electronic devices through interconnection (on or offline) with computer or component equipment and the associated equipment needed to control the presentation of the primary flight information and tactical information to the crew. Includes, for example: a. Multi-function displays, control display units, display processors, and on-board mission planning systems Excludes, for example: a. Indicators and instruments not controlled by keyboard via the multiplex data bus, panels and consoles which are included under the crew station b. Display size/location and symbology definition included under the crew station NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.2.5.7 | Survivability | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.5.7 Survivability. Those equipment (hardware/software) installed in, or attached to, the air vehicle which assist in penetration for mission accomplishment. This represents survivability equipment permanently installed as an integral part to the system. Includes, for example: a. Ferret and search receivers, warning devices and other electronic devices, electronic countermeasures, jamming transmitters, chaff, infra-red jammers, terrain-following radars, and other devices typical of this mission function Excludes, for example: a. Survivability equipment installed as a payload on an unmanned system, or as an easily removed/reconfigured item for a manned aircraft (i.e., not integral to the air vehicle function, in a podded system, for example) are children of the Level 2 payload element. NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.2.5.8 | Reconnaissance | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.5.8 Reconnaissance. Those equipment (hardware/software) installed or integral to the air vehicle which provides the ability to perform Intelligence, Surveillance, and Reconnaissance (ISR) missions through capabilities to locate sense, record, image and communicate threat attributes meteorological, hydrographical or geographical characteristics. Includes, for example: a. Photographic, electronic, infrared, and other sensors b. Search receivers c. Recorders d. Warning devices e. Magazines f. Data link Excludes, for example: a. Gun cameras (included under armament/weapons delivery) b. Reconnaissance equipment installed as a payload on an unmanned system or as an easily removed/reconfigured item for a manned aircraft (i.e., not integral to the air vehicle function, in a podded system, for example) are children of the Level 2 payload element. NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.2.5.9 | Electronic Warfare | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.5.9 Electronic Warfare. Those equipment (hardware/software) installed on the air vehicle which assist in any action involving the use of the electromagnetic spectrum or directed energy to control the spectrum, attack of an enemy, or impede enemy assaults via the spectrum. Includes, for example: a. Electronic counter-countermeasures, jamming transmitters, electromagnetic detection equipment, and weapons that use electromagnetic or directed energy such as laser, radio frequency (RF) weapons, or particle beams. Excludes, for example: a. Electronic countermeasures, chaff, infra-red jammers, or other equipment utilized primarily for defensive purposes (include such equipment under A.4.2.5.7 Survivability) b. Electronic warfare equipment installed as a payload on an unmanned system, or as an easily removed/reconfigured item for a manned aircraft (i.e., not integral to the air vehicle function, in a podded system, for example) are children of the Level 2 payload element.
1.2.5.10 | Automatic Flight Control | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.5.10 Automatic Flight Control. Those electronic devices and sensors on-board the aircraft, which, in combination with the flight controls subsystem (under vehicle subsystems), enable the crew to control the flight path of the aircraft and provide lift, drag, trim, or conversion effects. Includes, for example: a. Flight control computers, software, signal processors, and data transmitting elements that are devoted to processing data for either primary or automatic flight control functions b. Electronic devices required for signal processing, data formatting, and interfacing between the flight control elements; the data buses, optical links, and other elements devoted to transmitting flight control data c. Flight control sensors such as pressure transducers, rate gyros, accelerometers, and motion sensors Excludes, for example: a. Devices—linkages, control surfaces, and actuating devices—covered under the airframe and vehicle subsystem WBS elements b. Avionics devices and sensors—central computers, navigation computers, avionics data buses and navigation sensors, which are included under other avionics WBS elements NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.2.5.11 | Health Monitoring System | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.5.11 Health Monitoring System. That equipment (hardware/software) installed in the air vehicle for malfunction detection and reporting. NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.2.5.12 | Stores Management | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.5.12 Stores Management. The avionics subsystem that controls and monitors the operational state of aircraft installed stores, and provides and manages the communications between aircraft stores, other aircraft subsystems, and weapons. NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.2.5.13 | Avionics Software Release 1...n (Specify) | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.5.13 Avionics Software Release 1...n. All avionics software not associated with a specific Level 4 element.
1.2.5.14 | Other Avionics Subsystems 1...n (Specify) | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.5.14 Other Avionics Subsystems 1...n (Specify). This element should be replaced with other product-oriented avionics subsystems that are either not listed above or that cannot be categorized into one of the above elements. Each additional element is to be clearly identified and defined. NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.2.6 | Armament/Weapons Delivery | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.6 Armament/Weapons Delivery. That equipment (hardware/software) installed in the air vehicle to provide the firepower functions and weapons delivery capability. (Armament/Weapons Delivery equipment installed as a payload on an unmanned system or as an easily removed/reconfigured item for a manned aircraft (i.e., not integral to the air vehicle function, in a podded system for example) are included in Level 2 payload element) Includes, for example: a. Guns, high energy weapons, mounts, turrets, weapon direction equipment, ammunition feed and ejection mechanisms, and gun cameras b. Launchers, pods, bomb racks, pylons, integral release mechanisms, and other mechanical or electro-mechanical equipment specifically oriented to the weapons delivery function Excludes, for example: a. Bombing/navigation system (included in the fire control element) NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.2.7 | Auxiliary Equipment | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.7 Auxiliary Equipment. Auxiliary airframe, electronics, and/or armament/weapons delivery equipment not allocable to individual element equipment, or which provide the ancillary functions to the applicable mission equipment. Includes, for example: a. Auxiliary airframe equipment such as external fuel tanks, pods, and rotodomes b. Multi-use equipment like antennas, control boxes, power supplies, environmental control, racks, and mountings, not homogeneous to the prescribed WBS elements NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.2.8 | Furnishings and Equipment | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.8 Furnishings and Equipment. This element includes the provisions that sustain and support the passengers, typically consists of non-mission specific removable items. Includes, for example: a. Carpets b. Executive interiors c. Seats Excludes, for example; a. All items pertaining to the crew station subsystem element b. Primary structure supporting seat installations and restraints covered under the airframe WBS element c. Displays hardware/software covered under the data display and controls WBS element d. Wiring and plumbing for aircrew support covered under the airframe and vehicle subsystems WBS elements
1.2.9 | Air Vehicle Software Release 1...n (Specify) | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.9 Air Vehicle Software Release 1...n (Specify). All air vehicle software not associated with a specific Level 3 or Level 4 element. NOTE: Refer to Appendix B, Electronic/Generic Systems for further breakout and definitions for Software.
1.2.10 | Other Air Vehicle 1...n (Specify) | APPENDIX A: AIRCRAFT SYSTEMS | A.4.3.10 Other Air Vehicle 1...n (Specify). This element should be replaced with other product-oriented air vehicle elements that are either not listed above or that cannot be categorized into one of the above elements. Each additional element is to be clearly identified and defined.
1.3 | Payload/Mission System | APPENDIX A: AIRCRAFT SYSTEMS | A.4.4 Payload/Mission System. Aircraft systems (manned or unmanned) may have single or multiple payloads attached to the aircraft versus embedded (avionics systems). Examples of payloads include targeting and ranging systems, bio/chemical detection sensors, meteorological sensors, and communication relay systems.
1.3.1 | Payload Integration, Assembly, Test, and Checkout | APPENDIX A: AIRCRAFT SYSTEMS | A.4.4.1 Payload Integration, Assembly, Test, and Checkout. This element includes all effort of technical and functional activities associated with the design, development, and production of payload equipment, parts, materials, and software required to assemble and test the payload suite parts and subsystems equipment (hardware/software) elements. Reference Appendix K: Common Elements, Work Breakdown Structure and Definitions for further detail.
1.3.2 | Survivability Payload 1...n (Specify) | APPENDIX A: AIRCRAFT SYSTEMS | A.4.4.2 Survivability. Those equipment (hardware/software) installed in, or attached to, the air vehicle, which assist in penetration for mission accomplishment. This represents survivability equipment permanently installed as an integral part to the system Includes, for example: a. Ferret and search receivers, warning devices and other electronic devices, electronic countermeasures, jamming transmitters, chaff, infra-red jammers, terrain-following radar, and other devices typical of this mission function Excludes, for example: a. Survivability equipment installed on a manned system integral to the air vehicle element. NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.3.3 | Reconnaissance Payload 1...n (Specify) | APPENDIX A: AIRCRAFT SYSTEMS | A.4.4.3 Reconnaissance Payload 1...n (Specify). Those equipment (hardware/software) installed in, or attached to, the air vehicle necessary to the reconnaissance mission. Includes, for example: a. Photographic, electronic, infrared, and other sensors b. Search receivers c. Recorders d. Warning devices e. Magazines f. Data link Excludes, for example: a. Gun cameras NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.3.4 | Electronic Warfare Payload 1...n (Specify) | APPENDIX A: AIRCRAFT SYSTEMS | A.4.4.4 Electronic Warfare. Those equipment (hardware/software) attached to the air vehicle which assist in any action involving the use of the electromagnetic spectrum or directed energy to control the spectrum, attack of an enemy, or impede enemy assaults via the spectrum. Includes, for example: a. Electronic counter-countermeasures, jamming transmitters, electromagnetic detection equipment, and weapons that use electromagnetic or directed energy such as laser, RF weapons, or particle beams. Excludes, for example: a. Electronic countermeasures, chaff, infra-red jammers, or other equipment utilized primarily for defensive purposes (include such equipment under A.4.3.2 Survivability). b. Electronic Warfare equipment installed on a manned system integral to the air vehicle function. NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.3.5 | Armament/Weapons Delivery Payload 1...n (Specify) | APPENDIX A: AIRCRAFT SYSTEMS | A.4.4.5 Armament/Weapons Delivery Payload 1...n (Specify). The equipment (hardware/software) installed in the air vehicle to provide the firepower functions and weapons delivery capability. Includes, for example: a. Guns, high energy weapons, mounts, turrets, weapon direction equipment, ammunition feed and ejection mechanisms, and gun cameras b. Launchers, pods, bomb racks, pylons, integral release mechanisms, and other mechanical or electro-mechanical equipment specifically oriented to the weapons delivery function Excludes, for example: a. Bombing/navigation system (included in the fire control element) NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.3.6 | Payload Software Release 1...n (Specify) | APPENDIX A: AIRCRAFT SYSTEMS | A.4.4.6 Payload Software Release 1...n (Specify). All payload software not associated with a specific Level 4 element. NOTE: Refer to Appendix B, Electronic/Generic Systems for further breakout and definitions for Software.
1.3.7 | Other Payload 1...n (Specify) | APPENDIX A: AIRCRAFT SYSTEMS | A.4.4.7 Other Payload 1...n (Specify). Any other product or equipment not already mentioned in the above definition, but that is also transported or delivered by the aircraft system. This element should be replaced with other product-oriented payload elements that are either not listed above or that cannot be categorized into one of the above elements. Each additional element is to be clearly identified and defined. NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.4 | Ground/Host Segment | APPENDIX A: AIRCRAFT SYSTEMS | A.4.5 Ground/Host Segment. The Ground segment is defined as a fixed, transportable, or mobile assembly of hardware, software, and firmware that has a communications interface with the vehicle to receive only, or to receive and transmit data generated and mission data collected by the air vehicle. In addition, vehicle telemetry, tracking and command (TT&C) and mission data may be processed within collocated facilities or alternatively in remotely located facilities. For example, Ground 1 could represent an operations center and Ground 2 a network operations center or some other type of command and control facility. Includes, for example: a. Support for the system and vehicle level integration and testing provided by the producer/integrator of the ground portion of the system
1.4.1 | Ground Segment Integration, Assembly, Test, and Checkout | APPENDIX A: AIRCRAFT SYSTEMS | A.4.5.1 Ground Segment Integration, Assembly, Test, and Checkout. The efforts as identified in Appendix K: Common Elements, Work Breakdown Structure and Definitions, to provide a complete ground system.
1.4.2 | Ground Control Systems | APPENDIX A: AIRCRAFT SYSTEMS | A.4.5.2 Ground Control Systems (GCS). This subsystem receives, down converts, demodulates, and conditions telemetry, tracking, command, and mission (payload) data. In addition, this subsystem generates the RF uplink, accepts tracking and command signals, and modulates them onto the RF uplink. Includes, for example: a. Antennas, feeds, antenna positioners, antenna support pedestals, radomes, transmitters, receivers, up/down frequency converters, modulators, demodulators, data links front-end equipment (encryptors/decryptors, synchronizers), etc. b. Ground terminal (GT) facilities/buildings, GT factory/contractor support facility, GT initial support, GT support equipment c. Environmental control units (air conditioners), power generators, etc. that are required for operation of the ground control stations NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.4.3 | Command and Control Subsystem | APPENDIX A: AIRCRAFT SYSTEMS | A.4.5.3 Command and Control Subsystem. This subsystem decodes, demultiplexes, and decrypts air vehicle telemetry, generates commands for transmission to the aircraft, and processes tracking data to generate air vehicle ephemeris. This subsystem supports all ground subsystems that require the capability to prepare and output commands to, and receive and process data from, the air vehicle while in operation or under test. Includes, for example: a. Network, computer processing and display hardware such as routers, switches, servers, workstations, storage devices, etc. b. Software for handling, processing, and executing air vehicle commands, as well as processing and analyzing air vehicle telemetry c. Command and control ground facilities/building, command and control factory/contractor support facility, command and control initial support and support equipment NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.4.4 | Launch Equipment | APPENDIX A: AIRCRAFT SYSTEMS | A.4.5.4 Launch Equipment. This is the equipment necessary to launch air vehicles during the performance of its mission. Includes, for example: a. Equipment required to launch the air vehicle with its mission payloads into flight b. Air vehicle hydraulic/pneumatic launcher, rail, and jet/rocket assisted take-off (JATO/RATO) bottles for short take-off NOTE: All effort directly associated with the remaining Level 3 WBS elements and the integration, assembly, test, and checkout of these elements into the Ground/Host Segment is excluded.
1.4.5 | Recovery Equipment | APPENDIX A: AIRCRAFT SYSTEMS | A.4.5.5 Recovery Equipment. This is the equipment necessary to recover air vehicles during the performance of its mission. Includes, for example: a. Automatic landing beacon system b. Arresting net or arresting lines c. Parachute
1.4.6 | Transport Vehicles | APPENDIX A: AIRCRAFT SYSTEMS | A.4.5.6 Transport Vehicles. Any vehicles that have been specifically designed or modified for the transportation of air vehicles, ground control station equipment or other mission equipment. This includes any vehicles used to perform movement of the prime mission vehicle, crew, maintenance equipment, and direct maintenance personnel, or any other special transport systems used in the relocation of the prime mission equipment so that it may perform its mission.
1.4.7 | Ground Segment Software Release 1...n (Specify) | APPENDIX A: AIRCRAFT SYSTEMS | A.4.5.7 Ground Segment Software Release 1...n. All Ground Segment software not associated with a specific Level 3 element. NOTE: Refer to Appendix B, Electronic/Generic Systems for further breakout and definitions for Software.
1.4.8 | Other Ground/Host Segment 1...n (Specify) | APPENDIX A: AIRCRAFT SYSTEMS | A.4.5.8 Other Ground Segment 1...n (Specify). This element should be replaced with other product-oriented Ground Segment elements that are either not listed above or that cannot be categorized into one of the above elements. Each additional element is to be clearly identified and defined. NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.5 | Aircraft System Software Release 1...n (Specify) | APPENDIX A: AIRCRAFT SYSTEMS | A.4.6 Common Elements. Common WBS elements and definitions for all commodities can be found at Appendix K.3. Several commodities have unique elements that are applied which also appear in Appendix K, specifically, Space Systems (K.4); Launch Systems (K.5); Information Systems/Defense Business Systems (K.6); and Strategic Missile Systems (K.7).
1.6 | Systems Engineering | APPENDIX A: AIRCRAFT SYSTEMS | K.3.2 Systems Engineering. The technical and management efforts of directing and controlling a totally integrated engineering effort of a system or program. The following represent many, but not all, of the systems engineering efforts needed for a system or program. If required, one or more areas of effort (e.g., software systems engineering, cybersecurity, etc., may be identified at the next level below systems engineering. In those cases, the remaining totality of systems engineering efforts will be defined as “core systems engineering” at the level equal to the segregated items. | K.3.2 Systems Engineering. The technical and management efforts of directing and controlling a totally integrated engineering effort of a system or program. The following represent many, but not all, of the systems engineering efforts needed for a system or program. If required, one or more areas of effort (e.g., software systems engineering, cybersecurity, etc., may be identified at the next level below systems engineering. In those cases, the remaining totality of systems engineering efforts will be defined as “core systems engineering” at the level equal to the segregated items.
1.6.1 | Software Systems Engineering | APPENDIX A: AIRCRAFT SYSTEMS | K.3.2.1 Software Systems Engineering. The efforts which encompass software systems technologies, software engineering methods, and management techniques that improve the quality and delivery of software intensive systems and applications. Includes, for example: a. The application of a systematic, disciplined, quantifiable approach to the development and operations and support (O&S) of software b. The determination of software development or software test facility/environment requirements c. Application of systems engineering to software, that is, the systematic application of scientific and technical knowledge, methods, and experience to the design, implementation, testing, and documentation of software d. Analyzing the system requirements allocated to the software, developing the software requirements, developing the software architecture, designing the software, implementing the software in the code, integrating the software components, and testing the software to verify that the software satisfies the specified requirements allocated to the software component of a system or subsystem.
1.6.2 | Integrated Logistics Support (ILS) Systems Engineering | APPENDIX A: AIRCRAFT SYSTEMS | K.3.2.2 Integrated Logistics Support (ILS) Systems Engineering. The efforts to ensure the integrated planning and action of a number of disciplines in concert with one another to assure system availability. The planning of each element of ILS (e.g., integrated product support (IPS) elements) is developed in coordination with systems engineering and other efforts. Includes, for example: a. Product support management b. Design interface c. Sustaining engineering d. Supply support e. Maintenance planning and management f. Packaging, handling, storage, and transportation g. Technical data h. Support equipment i. Training and training support j. Manpower and personnel k. Facilities and infrastructure l. Computer resources
1.6.3 | Cybersecurity Systems Engineering | APPENDIX A: AIRCRAFT SYSTEMS | K.3.2.3 Cybersecurity Systems Engineering. The efforts to apply scientific and engineering principles to identify security vulnerabilities and minimize or contain risks associated with these vulnerabilities. Includes, for example: a. Cybersecurity requirements evaluation b. Cyberattack surface characterization c. Cooperative vulnerability identification d. Vulnerability analysis e. System cross-functional cyber analysis f. Advise on RMF compliance tasks/documents (security assessment plan, etc.) g. Security configuration management (assess planned services for risk and impact) h. Develop system-level security architecture i. Design, develop, and implement system security measures that meets technical requirements j. Develop and implement specific security countermeasures for the system k. Develop approaches to mitigate system vulnerabilities l. Ensure the design of hardware, operating systems, and software applications adequately address cybersecurity requirements for the system
1.6.4 | Core Systems Engineering | APPENDIX A: AIRCRAFT SYSTEMS | K.3.2.4 Core Systems Engineering. The technical and management efforts that establish the technical framework for delivering materiel capabilities and ensure the effective development and delivery of capability through the implementation of a balanced approach with respect to cost, schedule, performance, and risk. This effort uses integrated, disciplined and consistent systems engineering activities and processes for development of resilient systems that are trusted, assured and easily modified. Systems engineering is composed of 16 processes: eight technical processes and eight technical management processes. These processes provide a structured approach to increasing the technical maturity of a system and increasing the likelihood that the capability being developed balances mission performance with cost, schedule, risk, and design constraints. To fulfill that purpose, a program implements the systems engineering technical processes to support the iterative maturation of the system solution or operational need. The technical processes enable the systems engineering team to ensure that the delivered capability accurately reflects the operational needs of the stakeholders. The technical processes include top down design processes such as stakeholder requirements definition, requirements analysis, and architecture design, as well as bottom-up realization processes such as transition, validation, verification, integration, and implementation. The eight technical management processes are implemented across the acquisition life cycle and provide insight and control to assist the program manager and systems engineer to meet performance, schedule, and cost goals. The eight technical processes closely align with the acquisition life cycle phases and include the top-down design processes and bottom-up realization processes that support transformation of operational needs into operational capabilities. The eight technical management processes are: decision analysis, technical planning, technical assessment, requirements management, risk management, configuration management, technical data management, and interface management. Also included are specialty engineering disciplines which bring together the hardware, software, and human elements of the systems. Includes, for example: a. System safety which is applicable to most DoD systems; this reflects the ubiquitous nature of software-driven functions, network connectivity, and systems of systems; specific certifications include safety, security, cybersecurity and airworthiness b. Reliability and maintainability – ensure that design interface and integration of the quantitative systems engineering design characteristics (i.e., reliability, maintainability, etc.) with the functional integrated product support elements c. Quality – ensures configuration item level requirements for the systems and subsystems meet critical functions and key quality attributes. d. Manufacturing and producibility – ensure manufacturing and producibility readiness, processes assessed and demonstrated, and risks identified, managed and reduced throughout the program’s life cycle e. Human systems integration – optimize total system performance and total ownership costs, while ensuring that the system is designed, operated, and maintained to effectively provide the user with the ability to complete their mission; ensure ergonomics, human factors engineering, and cognitive engineering is employed to provide for effective human-machine interfaces; define the human performance characteristics of the user based on the system description, projected characteristics of target occupational specialties, and recruitment and retention trends; establish requirements for the physical environment; determine the most efficient and cost-effective mix of DoD manpower and contract support; develop training options for operators, maintenance and support personnel; ensure that appropriate environmental safety and occupational health; assess risks to personnel and address, in terms of system design, protection from direct threat events and accidents (such as chemical, biological, and nuclear threats). f. System of systems (SoS) and system level architecting, modeling and simulation, verification and validation and external interface definition and management g. For sea systems; the Expanded Ship Work Breakdown Structure (ESWBS), configuration management (811), human factors (892), standardization (893), value engineering (894), and reliability and maintainability (895) elements Excludes, for example: a. Actual design engineering and the production engineering directly related to the WBS element with which it is associated b. Any systems engineering efforts that are called out in software systems engineering, ILS systems engineering, cybersecurity systems engineering, or “other” systems engineering effort separately identified in the WBS.
1.6.5 | Other Systems Engineering 1...n (Specify) | APPENDIX A: AIRCRAFT SYSTEMS | K.3.2.5 Other Systems Engineering 1...n (Specify). This element should be replaced with other systems engineering elements that cannot be categorized into one of the above elements or need to be separately identified due to high cost, high risk concerns within systems engineering. Each additional element is to be clearly identified and defined.
1.7 | Program Management | APPENDIX A: AIRCRAFT SYSTEMS | K.3.3 Program Management. The business and administrative planning, organizing, directing, coordinating, controlling, and approval actions designated to accomplish overall program objectives, which are not associated with specific hardware elements and are not included in systems engineering. If required, one or more areas of effort (e.g., software program management, cybersecurity program management, etc.,) may be identified at the next level below program management. In those cases, the remaining totality of program management efforts will be defined as “core program management” at the level equal to the segregated items.
1.7.1 | Software Program Management | APPENDIX A: AIRCRAFT SYSTEMS | K.3.3.1 Software Program Management. The software program management encompasses the management of the full software life cycle, from conception to deployment. The function focuses at the system level of applying business and project management skills needed to produce high-quality software products. Includes, for example: a. Overseeing requirements analysis and design, and effective implementation and delivery of all fully-tested software b. Ensure sufficient end-user involvement c. Maintain communication among customers, developers, users, and project managers d. Establish realistic or articulated project goals e. Develop accurate estimates of needed resources f. Define system requirements and specifications g. Assure reporting of the project’s status h. Proper management of risks i. Ensure the use of mature technology and handle the project’s complexity
1.7.2 | Integrated Logistics Support (ILS) Program Management | APPENDIX A: AIRCRAFT SYSTEMS | K.3.3.2 Integrated Logistics Support Program Management. The efforts to manage the planning and execution of the ILS disciplines to assure system acquisition logistics availability. Includes, for example: a. Support element management, defined as the logistics tasks management effort and technical control, and the business management of the support elements. The logistics management function encompasses the support evaluation and supportability assurance required to produce an affordable and supportable defense materiel system. b. Planning and management of all the functions of logistics. Examples are: maintenance support planning and support facilities planning; other support requirements determination; support equipment requirements determination; supply support; packaging, handling, storage, and transportation; provisioning requirements determination and planning; training system requirements determination; computer resource determination; organizational, intermediate, and depot maintenance determination management; and data management
1.7.3 | Cybersecurity Management | APPENDIX A: AIRCRAFT SYSTEMS | K.3.3.3 Cybersecurity Program Management. The management and understanding of cybersecurity program and its ramifications across the organization (only if costs are collected in this manner). Includes, for example: a. Overseeing cybersecurity risk assessment, management, and mediation b. Cybersecurity threat vectors and mitigation processes c. Ensuring design and management of secure information systems d. Emerging tools and resources for organizational and platform security
1.7.4 | Core Program Management | APPENDIX A: AIRCRAFT SYSTEMS | K.3.3.4 Core Program Management. The efforts to understand and manage multiple discipline areas in order the successfully accomplish program objectives for development, production, and sustainment of systems to meet the user’s operational needs Includes, for example: a. Cost, schedule, performance measurement management, warranty administration, contract management, vendor liaison, subcontract management, etc. b. For sea systems; the Expanded Ship Work Breakdown Structure (ESWBS), project management (897); data management (896); and supply support (853) elements Excludes, for example: a. Actual program management directly related to another WBS element b. Any program management efforts that are called out in software program management, cybersecurity program management, or “other” program management effort separately identified in the WBS.
1.7.5 | Other Program Management 1...n (Specify) | APPENDIX A: AIRCRAFT SYSTEMS | K.3.3.5 Other Program Management 1...n (Specify). This element should be replaced with other program management elements that cannot be categorized into one of the above elements or need to be separately identified due to high cost or high risk concerns within program management. Each additional element is to be clearly identified and defined.
1.8 | System Test and Evaluation | APPENDIX A: AIRCRAFT SYSTEMS | K.3.4 System Test and Evaluation. The use of pilot, prototype, production, or specifically fabricated hardware/software to obtain or validate engineering data on the performance of the system during the developmental phase of the program. It also includes all effort associated with the development of any specialized tools or data in support of the system level test program. Includes, for example: a. Detailed planning, conduct, support, data reduction and reports (excluding the contract data requirements list data) from such testing, and test articles that are functionally configured to represent and test subsystems/components of the defense materiel end item being developed or produced b. Design and production of models, specimens, fixtures and instrumentation c. System level labs that integrate both hardware and software NOTE: Test articles that are functionally configured to represent and test the complete defense materiel end item being developed or produced, are excluded from this WBS element. Excludes, for example: a. All formal and informal testing up through the subsystem level, which can be associated with the hardware/software element acceptance testing NOTE: These excluded efforts are to be included with the appropriate hardware or software elements.
1.8.1 | Development Test and Evaluation | APPENDIX A: AIRCRAFT SYSTEMS | K.3.4.1 Development Test and Evaluation. The test and evaluation conducted by the developing agency of the DoD component. It includes test and evaluation conducted to: a. Demonstrate that the engineering design and development process is complete b. Demonstrate that the design risks have been minimized c. Demonstrate that the system will meet specifications d. Assess the system’s military utility when introduced e. Determine whether the engineering design is supportable (practical, maintainable, safe, etc.) for operational use f. Provide test data with which to examine and evaluate trade-offs against specification requirements, life cycle cost, and schedule g. Perform the logistics testing efforts to evaluate the achievement of supportability goals, the adequacy of the support package for the system, (e.g., deliverable maintenance tools, test equipment, technical publications, maintenance instructions, and personnel skills and training requirements, etc.) Includes, for example: a. All contractor/system developer in-house effort b. Where applicable, models, tests and associated simulations (e.g., such as wind tunnel, static, drop, and fatigue); integration ground tests; test bed aircraft and associated support; qualification test and evaluation, development flight test, test instrumentation, environmental tests, ballistics, radiological, range and accuracy demonstrations, test facility operations, test equipment (including its support equipment), chase and calibrated pacer aircraft and support thereto, and logistics testing c. For aircraft; avionics integration test composed of the following: i. Test bench/laboratory, including design, acquisition, and installation of basic computers and test equipment that will provide an ability to simulate in the laboratory the operational environment of the avionics system/subsystem ii. Air vehicle equipment, consisting of the avionics and/or other air vehicle subsystem modules that are required by the bench/lab or flying test bed in order to provide a compatible airframe avionics system/subsystem for evaluation purposes iii. Flying test bed, including requirements analysis, design of modifications, lease or purchase of test bed aircraft, modification of aircraft, installation of avionics equipment and instrumentation, and checkout of an existing aircraft used essentially as a flying avionics laboratory iv. Avionics test program, consisting of the effort required to develop test plans/procedures, conduct tests, and analyze hardware and software test results to verify the avionics equipment’s operational capability and compatibility as an integrated air vehicle subsystem v. Software, referring to the effort required to design, code, de-bug, and document software programs necessary to direct the avionics integration test d. For engines: engine military qualification tests and engine preliminary flight rating tests e. For sea systems: model basin, hydrostatic, fatigue, shock, special sea tests and trials, etc., including the Expanded Ship Work Breakdown Structure (ESWBS), trials agenda preparation, data collection and analysis (842); dock and sea trials (9823); and hull vibration survey (9825) elements f. For missiles: test articles such as inert measurement vehicles, launch separation vehicles, separation and control test vehicles, boost test vehicles g. For ordnance: test articles such as ballistic test rounds, inert measurement rounds, dummy rounds, launch separation rounds, etc.
1.8.2 | Operational Test and Evaluation | APPENDIX A: AIRCRAFT SYSTEMS | K.3.4.2 Operational Test and Evaluation. The test and evaluation conducted by agencies other than the developing command to assess the prospective system’s military utility, operational effectiveness, operational suitability, logistics supportability (including compatibility, inter-operability, reliability, maintainability, logistic requirements, etc.), cost of ownership, and need for any modifications. Includes, for example: a. Initial operational test and evaluation conducted during the development of a system b. Such tests as system demonstration, flight tests, sea trials, mobility demonstrations, on-orbit tests, spin demonstration, stability tests, qualification operational test and evaluation, etc., and support thereto, required to prove the operational capability of the deliverable system. c. Contractor support (e.g., technical assistance, maintenance, labor, material, etc.) consumed during this phase of testing d. Logistics testing efforts to evaluate the achievement of supportability goals and the adequacy of the support for the system (e.g., deliverable maintenance tools, test equipment, technical publications, maintenance instructions, personnel skills and training requirements, and software support facility/environment elements)
1.8.3 | Cybersecurity Test and Evaluation | APPENDIX A: AIRCRAFT SYSTEMS | K.3.4.3 Cybersecurity System Test and Evaluation. The developmental test and evaluation and operational test and evaluation conducted and monitored by the developing agency of the DoD. The technical efforts of ensuring the confidentiality, integrity, and availability of information and technology by monitoring and defending against cyber (network) attacks. Includes, for example: a. Vulnerability scanning and interpretation b. Vulnerability testing and penetration testing (usually linked to patch management) c. Security information and event management d. Destructive and non-destructive exploitation e. Test conducted in an operational environment with certified red teams f. Cybersecurity compliance tracking and reporting g. Malware scanning, detection, and prevention services h. Security, IT certification, and accreditation compliance services
1.8.4 | Mock-ups/System Integration Labs (SILs) | APPENDIX A: AIRCRAFT SYSTEMS | K.3.4.4 Mock-ups/System Integration Labs (SILs). The design engineering and production of system or subsystem mock-ups that have special contractual or engineering significance or that are not required solely for the conduct of one of the above elements of testing. SILs are often used in lieu of (or in addition to) mock-ups. SILs are risk reduction facilities where software and hardware can be developed, integrated, tested, and evaluated for both standalone functionality and/or interoperability prior to being fielded. Includes, for example: a. Hardware/lab equipment b. SIL Software (written to simulate the operating environment or written to operate the SIL)
1.8.5 | Test and Evaluation Support | APPENDIX A: AIRCRAFT SYSTEMS | K.3.4.5 Test and Evaluation Support. The support elements necessary to operate and maintain, during test and evaluation, systems and subsystems, which are not consumed during the testing phase and are not allocated to a specific phase of testing. Includes, for example: a. Repairable spares, repair of reparables, repair parts, consumables, warehousing and distribution of spares and repair parts, test and support equipment, test bed vehicles, drones, surveillance aircraft/chase aircraft, tracking vessels, contractor technical support Excludes, for example: a. Operational and maintenance personnel, special fixtures, special instrumentation, etc., that are utilized and/or consumed in a single element of testing and that should be included under that element of testing
1.8.6 | Test Facilities | APPENDIX A: AIRCRAFT SYSTEMS | K.3.4.6 Test Facilities. The special test facilities required for performance of the various developmental tests necessary to prove the design and reliability of the system or subsystem. Includes, for example: a. Test tank test fixtures, propulsion test fixtures, white rooms, test chambers, range/targeting facilities Excludes, for example: a. Brick and mortar-type facilities identified as industrial facilities
1.9 | Training | APPENDIX A: AIRCRAFT SYSTEMS | K.3.5 Training. Deliverable training services, devices, accessories, aids, equipment, and parts used to facilitate instruction through which personnel will learn to operate and maintain the system with maximum efficiency. Includes, for example: a. All effort associated with the design, development, and production of deliverable training equipment and its associated software as well as the execution of training services Excludes, for example: a. Overall planning, management, and task analysis functions inherent in the WBS element systems engineering/program management
1.9.1 | Equipment | APPENDIX A: AIRCRAFT SYSTEMS | K.3.5.1 Equipment. Distinctive deliverable end items of training equipment, assigned by either a contractor or military service, required to meet specific training objectives. Includes, for example: a. Operational and Maintenance Trainers and training equipment including items such as cutaways, mock-ups, and models (e.g. Operator Instructional Equipment, Maintainer Instructional Equipment)
1.9.1.1 | Operator Instructional Equipment | APPENDIX A: AIRCRAFT SYSTEMS | [Blank]
1.9.1.2 | Maintainer Instructional Equipment | APPENDIX A: AIRCRAFT SYSTEMS | [Blank]
1.9.2. | Services | APPENDIX A: AIRCRAFT SYSTEMS | K.3.5.2 Services. Deliverable training services, accessories, and courseware aids necessary to accomplish the objectives of training. Includes, for example: a. Operational and Maintenance Training Services including courses, course materials; and curriculum required to design, execute, and produce a contractor developed training program and related software programs (e.g. operator instructional services, maintainer instructional services) Excludes, for example: a. Deliverable training data associated with support data (see Data Deliverables 1...n (Specify), Support Data)
1.9.2.1 | Operator Instructional Services | APPENDIX A: AIRCRAFT SYSTEMS | [Blank]
1.9.2.2 | Maintainer Instructional Services | APPENDIX A: AIRCRAFT SYSTEMS | [Blank]
1.9.3 | Facilities | APPENDIX A: AIRCRAFT SYSTEMS | K.3.5.3 Facilities. The special construction necessary to accomplish training objectives. Includes, for example: a. Modification or rehabilitation of existing training facilities and infrastructure used to accomplish training objectives Excludes, for example: a. Installed equipment used to acquaint the trainee with the system or establish trainee proficiency b. The brick and mortar-type facilities identified as industrial facilities
1.9.4 | Training Software 1...n (Specify) | APPENDIX A: AIRCRAFT SYSTEMS | K.3.5.4 Training Software Release 1...n (Specify). Updated/upgraded software for training purposes delivered to the field during the acquisition phase.
1.1 | Data | APPENDIX A: AIRCRAFT SYSTEMS | K.3.6 Data. The deliverable data required to be listed on a contract data requirements list. Includes, for example: a. Only such effort that can be reduced or avoided if the data item is eliminated b. Government-peculiar data; acquiring, assembling, reproducing, packaging and shipping the data c. Transforming data into Government
1.10.1 | Data Deliverables 1...n (Specify) | APPENDIX A: AIRCRAFT SYSTEMS | K.3.6.1 Data Deliverables 1...n (Specify). Deliverable data which provides technical, engineering, management, support, or other data required for contract delivery. Includes, for example: a. Technical Publications. Technical data, providing instructions for installation, operation, maintenance, training, and support, formatted into a technical manual. Data may be presented in any form regardless of the form or method of recording. Technical orders that meet the criteria of this definition may also be classified as technical manuals. For sea systems: Expanded Ship Work Breakdown Structure (ESWBS), technical manuals and other data (856) element. b. Engineering Data. Recorded scientific or technical information (regardless of the form or method of recording) including computer software documentation. Engineering data defines and documents an engineering design or product configuration (sufficient to allow duplication of the original items) and is used to support production, engineering, and logistics activities. For sea systems; Expanded Ship Work Breakdown Structure (ESWBS), design support, ship’s selected records (8302); design support, services, reproduction (8303); and engineering drawings and specifications (855) elements. c. Management Data. The data items necessary for configuration management, cost, schedule, contractual data management, program management, etc., required by the Government. For sea systems; Expanded Ship Work Breakdown Structure (ESWBS), contract data requirements (988) element. d. Support Data. The data items designed to document support planning in accordance with functional categories
1.10.2 | Data Repository | APPENDIX A: AIRCRAFT SYSTEMS | K.3.6.2 Data Repository. The activity and enterprise data storage entity (or sometimes entities) for Government approved documents that are the property of the Government into which data has been specifically partitioned for analytical or reporting purposes. As custodian for the Government, the repository, authorized by approved change orders, maintains master documents at the latest approved revision level. Includes, for example: a. All effort necessary to maintain documents
1.10.3 | Data Rights 1...n (Specify) | APPENDIX A: AIRCRAFT SYSTEMS | K.3.6.3 Data Rights 1...n (Specify). Government’s license rights of valuable intellectual property including technical data of any recorded information of a scientific or technical nature (e.g., product design or maintenance data, computer databases, and computer software documentation); and computer software including executable code, source code, code listings, design details, processes, flow charts, and related material. Includes, for example: a. Unlimited Rights. Developed exclusively at Government expense, and certain types of data (e.g., Form, Fit, and Function data (FFF); Operation, Maintenance, Installation, and Training (OMIT)). These rights involve the right to use, modify, reproduce, display, release, or disclose technical data in whole or in part, in any manner, and for any purpose whatsoever, and to have or authorize others to do so. b. Government Purpose Rights. This right involves the right to use, duplicate, or disclose technical data for Government purposes only, and to have or permit others to do so for Government purposes only. Government purposes include competitive procurement, but do not include the right to permit others to use the data for commercial purposes. c. Limited Rights. A limited rights agreement permits the Government to use proprietary technical data in whole or in part. It also means that the Government has to obtain the expressed permission of the party providing the technical data to release it, or disclose it, outside the Government.
1.11 | Peculiar Support Equipment | APPENDIX A: AIRCRAFT SYSTEMS | K.3.7 Peculiar Support Equipment. The design, development, and production of those deliverable items and associated software required to support and maintain the system or portions of the system while the system is not directly engaged in the performance of its mission, and which are not common support equipment. Items should be designated by commodity subassembly (airframe, engine, avionics, etc.). Includes, for example: a. Vehicles, equipment, tools, etc., used to fuel, service, transport, hoist, repair, overhaul, assemble, disassemble, test, inspect, or otherwise maintain mission equipment b. Any production of duplicate or modified factory test or tooling equipment delivered to the Government for use in maintaining the system. (Factory test and tooling equipment initially used by the contractor in the production process but subsequently delivered to the Government will be included as cost of the item produced.) c. Any additional equipment or software required to maintain or modify the software portions of the system Excludes, for example: a. Overall planning, management, and task analysis functions inherent in the work breakdown structure elements Systems Engineering and Program Management b. Common support equipment, presently in the DoD inventory or commercially available, bought by the using command, not by the acquiring command
1.11.1 | Test and Measurement Equipment | APPENDIX A: AIRCRAFT SYSTEMS | K.3.7.1 Test and Measurement Equipment. The peculiar or unique testing and measurement equipment that allows an operator or maintenance function to evaluate operational conditions of a system or equipment by performing specific diagnostics, screening, or quality assurance effort at an organizational, intermediate, or depot level of equipment support. Includes, for example: a. Test measurement and diagnostic equipment, precision measuring equipment, automatic test equipment, manual test equipment, automatic test systems, test program sets, appropriate interconnect devices, automated load modules, tapes, and related software, firmware and support hardware (power supply equipment, etc.) used at all levels of maintenance b. Packages that enable line or shop replaceable units, printed circuit boards, or similar items to be diagnosed using automatic test equipment
1.11.1.1 | Test and Measurement Equipment (Airframe/Hull/Vehicle) | APPENDIX A: AIRCRAFT SYSTEMS | K.3.7.1.1 Test and Measurement Equipment (Airframe/Hull/Vehicle). This element captures the cost of the airframe, ship hull, or ground vehicle hull/frame related test and measurement equipment. Identify the related WBS subassemblies associated with the airframe/hull/vehicle. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested
1.11.1.2 | Test and Measurement Equipment (Propulsion) | APPENDIX A: AIRCRAFT SYSTEMS | K.3.7.1.2 Test and Measurement Equipment (Propulsion). This element captures the cost of the propulsion system, engines, prime movers, turbines, etc. related test and measurement equipment. Identify the related WBS subassemblies associated with propulsion. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.11.1.3 | Test and Measurement Equipment (Electronics/Avionics) | APPENDIX A: AIRCRAFT SYSTEMS | K.3.7.1.3 Test and Measurement Equipment (Electronics/Avionics). This element captures the cost of the electronics/avionics related test and measurement equipment. Identify the related WBS subassemblies associated with electronics/avionics. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.11.1.4 | Test and Measurement Equipment (Other Major Subsystems 1...n (Specify)) | APPENDIX A: AIRCRAFT SYSTEMS | K.3.7.1.4 Test and Measurement Equipment (Other Major Subsystem 1...n (Specify)). This element captures the cost of other major subsystems (e.g., armament, weapons, vehicle subsystems, etc.) not captured above related test and measurement equipment. Identify the related WBS subassemblies associated with the other major subsystems. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.11.2 | Support and Handling Equipment | APPENDIX A: AIRCRAFT SYSTEMS | K.3.7.2 Support and Handling Equipment. The peculiar or unique tools and handling equipment used for support of the mission system at an organizational, intermediate, or depot level Includes, for example: a. Ground support equipment, vehicular support equipment, powered support equipment, non-powered support equipment, munitions material handling equipment, materiel handling equipment, and software support equipment (hardware and software)
1.11.2.1 | Support and Handling Equipment (Airframe/Hull/Vehicle) | APPENDIX A: AIRCRAFT SYSTEMS | K.3.7.2.1 Support and Handling Equipment (Airframe/Hull/Vehicle). This element captures the cost of the airframe, ship hull, or ground vehicle hull/frame related support and handling equipment. Identify the related WBS subassemblies associated with airframe/hull/vehicle. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.11.2.2 | Support and Handling Equipment (Propulsion) | APPENDIX A: AIRCRAFT SYSTEMS | K.3.7.2.2 Support and Handling Equipment (Propulsion). This element captures the cost of propulsion related support and handling equipment. Identify the related WBS subassemblies associated with propulsion. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.11.2.3 | Support and Handling Equipment (Electronics/Avionics) | APPENDIX A: AIRCRAFT SYSTEMS | K.3.7.2.3 Support and Handling Equipment (Electronics/Avionics). This element captures the cost of the electronics/avionics related support and handling equipment. Identify the related WBS subassemblies associated with electronics/avionics. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.11.2.4 | Support and Handling Equipment (Other Major Subsystems 1...n (Specify)) | APPENDIX A: AIRCRAFT SYSTEMS | K.3.7.2.4 Support and Handling Equipment (Other Major Subsystem 1...n (Specify)). This element captures the cost of other major subsystems (e.g., armament, weapons, vehicle subsystems, etc.) not captured above related support and handling equipment. Identify the related WBS subassemblies associated with the other major subsystems. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.12 | Common Support Equipment | APPENDIX A: AIRCRAFT SYSTEMS | K.3.8 Common Support Equipment. The items required to support and maintain the system or portions of the system while not directly engaged in the performance of its mission, and which are presently in the DoD inventory for support of other systems. Includes, for example: a. Acquisition of additional quantities of this equipment needed to support the item b. All efforts required to assure the availability of this equipment to support the item
1.12.1 | Test and Measurement Equipment | APPENDIX A: AIRCRAFT SYSTEMS | K.3.8.1 Test and Measurement Equipment. The common testing and measurement equipment that allows an operator or maintenance function to evaluate operational conditions of a system or equipment by performing specific diagnostics, screening, or quality assurance effort at an organizational, intermediate, or depot level of equipment support. Includes, for example: a. Test measurement and diagnostic equipment, precision measuring equipment, automatic test equipment, manual test equipment, automatic test systems, test program sets, appropriate interconnect devices, automated load modules, tapes, and related software, firmware, and support hardware (power supply equipment, etc.) Used at all levels of maintenance b. Packages that enable line or shop replaceable units, printed circuit boards, or similar items to be diagnosed using automatic test equipment
1.12.1.1 | Test and Measurement Equipment (Airframe/Hull/Vehicle) | APPENDIX A: AIRCRAFT SYSTEMS | K.3.8.1.1 Test and Measurement Equipment (Airframe/Hull/Vehicle). This element captures the cost of the airframe, ship hull, or ground vehicle hull/frame related test and measurement equipment. Identify the related WBS subassemblies associated with the airframe/hull/vehicle. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.12.1.2 | Test and Measurement Equipment (Propulsion) | APPENDIX A: AIRCRAFT SYSTEMS | K.3.8.1.2 Test and Measurement Equipment (Propulsion). This element captures the cost of the propulsion system, engines, prime movers, turbines, etc. related test and measurement equipment. Identify the related WBS subassemblies associated with propulsion. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.12.1.3 | Test and Measurement Equipment (Electronics/Avionics) | APPENDIX A: AIRCRAFT SYSTEMS | K.3.8.1.3 Test and Measurement Equipment (Electronics/Avionics). This element captures the cost of the electronics/avionics related test and measurement equipment. Identify the related WBS subassemblies associated with electronics/avionics. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.12.1.4 | Test and Measurement Equipment (Other Major Subsystems 1...n (Specify)) | APPENDIX A: AIRCRAFT SYSTEMS | K.3.8.1.4 Test and Measurement Equipment (Other Major Subsystem 1...n (Specify)). This element captures the cost of other major subsystems (e.g., armament, weapons, vehicle subsystems, etc.) not captured above related test and measurement equipment. Identify the related WBS subassemblies associated with the other major subsystems. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.12.2 | Support and Handling Equipment | APPENDIX A: AIRCRAFT SYSTEMS | K.3.8.2 Support and Handling Equipment. The common tools and handling equipment used for support of the mission system at an organizational, intermediate, or depot level Includes, for example: a. Ground support equipment, vehicular support equipment, powered support equipment, non-powered support equipment, munitions material handling equipment, materiel handling equipment, and software support equipment (hardware/software)
1.12.2.1 | Support and Handling Equipment (Airframe/Hull/Vehicle) | APPENDIX A: AIRCRAFT SYSTEMS | K.3.8.2.1 Support and Handling Equipment (Airframe/Hull/Vehicle). This element captures the cost of the airframe, ship hull, or ground vehicle hull/frame related support and handling equipment. Identify the related WBS subassemblies associated with airframe/hull/vehicle. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.12.2.2 | Support and Handling Equipment (Propulsion) | APPENDIX A: AIRCRAFT SYSTEMS | K.3.8.2.2 Support and Handling Equipment (Propulsion). This element captures the cost of propulsion related support and handling equipment. Identify the related WBS subassemblies associated with propulsion. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.12.2.3 | Support and Handling Equipment (Electronics/Avionics) | APPENDIX A: AIRCRAFT SYSTEMS | K.3.8.2.3 Support and Handling Equipment (Electronics/Avionics). This element captures the cost of the electronics/avionics related support and handling equipment. Identify the related WBS subassemblies associated with electronics/avionics. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.12.2.4 | Support and Handling Equipment (Other Major Subsystems 1...n (Specify)) | APPENDIX A: AIRCRAFT SYSTEMS | K.3.8.2.4 Support and Handling Equipment (Other Major Subsystem 1...n (Specify)). This element captures the cost of other major subsystems (e.g., armament, weapons, vehicle subsystems, etc.) not captured above related support and handling equipment. Identify the related WBS subassemblies associated with the other major subsystems. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.13 | Operational/Site Activation by Site 1...n (Specify) | APPENDIX A: AIRCRAFT SYSTEMS | K.3.9 Operational/Site Activation by Site 1...n (Specify). The real estate, construction, conversion, utilities, and equipment to provide all facilities required to house, service, and launch prime mission equipment at the organizational and intermediate level. Includes, for example: a. Conversion of site, ship, or vehicle b. System assembly, checkout, and installation (of mission and support equipment) into site facility or ship to achieve operational status c. Contractor support in relation to operational/site activation
1.13.1 | System Assembly, Installation, and Checkout on Site | APPENDIX A: AIRCRAFT SYSTEMS | K.3.9.1 System Assembly, Installation, and Checkout. The materials and services involved in the assembly of mission equipment at the site. Includes, for example: a. Installation of mission and support equipment in the operations or support facilities and complete system checkout or shakedown to ensure operational status. Where appropriate, specify by site, ship, or vehicle. b. The efforts and activities associated with shipping the system from contractor facility to customer site. That site could be a DT&E site, an installation and checkout site, or any similar site that is outside the direct control of the contractor. Excludes, for example: a. Field team installation
1.13.2 | Contractor Technical Support | APPENDIX A: AIRCRAFT SYSTEMS | K.3.9.2 Contractor Technical Support. The materials and services provided by the contractor related to activation. Includes, for example: a. Repair of reparables, standby services, and final turnover
1.13.3 | Site Construction | APPENDIX A: AIRCRAFT SYSTEMS | K.3.9.3 Site Construction. Real estate, site planning and preparation, construction, and other special-purpose facilities necessary to achieve system operational status. Includes, for example: a. Construction of utilities, roads, and interconnecting cabling
1.13.4 | Site/Ship/Vehicle Conversion | APPENDIX A: AIRCRAFT SYSTEMS | K.3.9.4 Site/Ship/Vehicle Conversion. The materials and services required to convert existing sites, ships, or vehicles to accommodate the mission equipment and selected support equipment directly related to the specific system. Includes, for example: a. Operations, support, and other special purpose facilities conversion necessary to achieve system operational status, e.g., launch. Where appropriate, specify by site, ship, or vehicle
1.13.5 | Interim Contractor Support (ICS) | APPENDIX A: AIRCRAFT SYSTEMS | K.3.9.5 Interim Contractor Support (ICS). The effort required to provide temporary contractor support in lieu of a permanent support solution (organic or commercial) for a predetermined time, while a permanent support capability is put in place. Interim support is usually required for support of prototypes and early test and production assets during development and initial fielding (i.e., Initial Operating Capability (IOC)). Includes, for example: a. Providing life cycle logistics in accordance with the integrated product support (IPS) elements in support of the prime mission product. Excludes, for example: a. The development and production of the original prime mission product.
1.14 | Contractor Logistics Support (CLS) | APPENDIX A: AIRCRAFT SYSTEMS | K.3.10 Contractor Logistics Support (CLS). Contracted weapon system sustainment including performance of maintenance and/or materiel management functions for a DoD weapon system by a commercial activity or contractor sustainment of a weapon system that is intended to start after a permanent decision is made to cover the operations and support efforts of the weapon system. CLS generally starts before FOC (final operating capability) or when performance based logistics (PBL) is implemented in the operating and support (O&S) phase. Includes, for example: a. Prime Mission Product (PMP) maintenance and refurbishment. The cost for this element includes maintenance and refurbishment (including the development and production) of existing operational systems. b. Support functions required to maintain the system, such as sustaining engineering, program management, logistics support, and supply chain management c. Test and evaluation for system and subsystem modifications d. Repair of reparable items; replacement of condemned items (including all PMP, support equipment, and training equipment) e. Operational, maintenance and other personnel required at the operational unit level f. Unit operations costs, including operating material and support services at the operating unit g. Installation and personnel support functions in support of the unit level manpower Excludes, for example: a. Does not include interim contractor support (ICS), a temporary measure for a system’s initial period of operation before a permanent form of support is in place. b. Contractor sustainment support for a specific sustainment task that a service would otherwise conduct itself.
1.15 | Industrial Facilities | APPENDIX A: AIRCRAFT SYSTEMS | K.3.11 Industrial Facilities. The construction, conversion, or expansion of industrial facilities for production, inventory, and contractor depot maintenance required when that service is for the specific system. Includes, for example: a. Equipment acquisition or modernization, where applicable b. Maintenance of these facilities or equipment c. Industrial facilities for hazardous waste management to satisfy environmental standards Excludes, for example: a. Capital equipment
1.15.1 | Construction/Conversion/Expansion | APPENDIX A: AIRCRAFT SYSTEMS | K.3.11.1 Construction/Conversion/Expansion. The real estate and preparation of system peculiar industrial facilities for production, inventory, depot maintenance, and other related activities.
1.15.2 | Equipment Acquisition or Modernization | APPENDIX A: AIRCRAFT SYSTEMS | K.3.11.2 Equipment Acquisition or Modernization. The production equipment acquisition, modernization, or transfer of equipment for the particular system. This pertains to Government owned and leased equipment under facilities contract.
1.15.3 | Maintenance (Industrial Facilities) | APPENDIX A: AIRCRAFT SYSTEMS | K.3.11.3 Maintenance (Industrial Facilities). The maintenance, preservation, and repair of industrial facilities and equipment.
1.16 | Initial Spares and Repair Parts | APPENDIX A: AIRCRAFT SYSTEMS | K.3.12 Initial Spares and Repair Parts. The deliverable spare components, assemblies, and subassemblies used for initial replacement purposes in the materiel system equipment end item. Includes, for example: a. Repairable spares (reparables) and repair parts required as initial stockage to support and maintain newly fielded systems or subsystems during the initial phase of service, including pipeline and war reserve quantities, at all levels of maintenance and support. Lower level WBS breakouts should be by subsystem. b. Spare training and support equipment items c. The combination of resources, processes, planning, procedures, design, considerations, methods, and all hardware to ensure that all system, equipment, and support items are preserved, packaged, handled, and transported properly, including environmental considerations, equipment preservation for short and long term storage, and transportability. This includes requirements such as special environmentally controlled, shock isolated containers for transport to and from repair facilities and ensuring proper Care of Supplies in Storage (COSIS) program requirements are followed. Excludes, for example: a. Development test spares and spares provided specifically for use during installation, assembly, and checkout on site

## B
WBS # | WBS Nomenclature | Appendix | WBS Definition
1 | Electronic System/Generic System | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | B.4.1 Electronic System/Generic System. The complex of equipment (hardware/software), data, services, and facilities required to develop and produce an electronic system capability such as a command and control system, radar system, communications system, sensor system, navigation/guidance system, electronic warfare system, support system, etc. This structure may also be used if no structure is defined within the MIL-STD. The purpose is providing a generic, logical decomposition of the WBS of a product-oriented systems or subsystem (i.e., engines, electronics, communication systems, etc.). NOTE 1: To differentiate between the Electronic/Generic System category and other defense materiel item categories, use the following rule: When the item is a stand-alone system or used on several systems but not accounted for within the system, use the Electronic/Generic System category. NOTE 2: When the opportunity to collect lower level information on electronic and software items exists, regardless of which defense materiel item category is selected, the structure and definitions in this appendix apply.
1.1 | Prime Mission Product (PMP) 1...n (Specify) | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | B.4.2 Prime Mission Product (PMP). The standalone system or major end item used to accomplish the primary mission of the defense materiel item. This WBS element includes the segments, subsystems, and software items as well as the efforts associated with the design, development, and production of complete units (i.e., the prototype or operationally configured units, which satisfy the requirements of their applicable specifications, regardless of end use) and is comprised of the sub elements listed below. Includes, for example: a. Hardware, software, and integration, assembly, test, and checkout associated with the overall prime mission product (PMP). When the electronic or generic system comprises several PMPs, each PMP will be listed separately at Level 2. b. Breadboards, brass boards, development test and qualification test units c. Factory special test equipment, special tooling, and production planning required to fabricate the PMP. Excludes, for example: a. Test articles that are functionally configured to represent and test subsystems or components should be included in the System Test and Evaluation element. b. Duplicate or modified factory special test equipment delivered to the Government for depot repair should be included in the Peculiar Support Equipment element. c. Spares for initial fielding should be included in the Initial Spares and Repair Parts element.
1.1.1 | PMP Integration, Assembly, Test, and Checkout | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | B.4.2.1 Prime Mission Product Integration, Assembly, Test, and Checkout. This WBS element contains all of the resources in order to perform integration, assembly, test, and checkout of the PMP. This is the process of combining and evaluating CSCIs and hardware of a system or segment of a system that have undergone individual CSCI and hardware qualification test.
1.1.2 | PMP Subsystem 1...n (Specify) | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | B.4.2.2 PMP Subsystem 1...n (Specify). The hardware and software components of the specific electronic or generic subsystem. Includes, for example: a. All associated special test equipment, special tooling, production planning, and all technical and management activities b. Software components, consisting of the software required to direct and maintain the specific electronic subsystem c. All in-plant integration, assembly, test, and checkout of hardware components and software into an electronic subsystem, including the subsystem hardware and software integration and test d. Interface materials and parts required for the in-plant integration and assembly of other Level 4 components into the electronic subsystem and all materials and parts or other mating equipment furnished by/to an integrating agency or contractor e. Cables, conduits, connectors, shelters, and other devices associated with the operational electronic subsystem f. The design, development, production, and assembly efforts to provide each electronic subsystem as an entity Excludes, for example: a. All effort directly associated with the remaining Level 3 WBS elements and the integration, assembly, test, and checkout of these elements into the prime mission product NOTE: All software that is an integral part of any specific equipment system, subsystem or component specification or specifically designed and developed for system test and evaluation should be identified with that system, subsystem, component or effort. It may be appropriate to collect lower level information when it exists. In such cases, the following structure and definitions should be used: LEVEL X Subsystem Hardware 1...n (Specify) Subsystem Software Release 1...n (Specify) LEVEL Y Computer Software Configuration Item (CSCI) 1...n (defined per B 4.2.3.1) Software Integration, Assembly, Test, and Checkout (defined per B.4.2.3.2)
1.1.2.1 | Subsystem Integration, Assembly, Test, and Checkout | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | B.4.2.2.1 Subsystem Integration, Assembly, Test, and Checkout. The resources specifically related to evaluating the CSCIs and hardware operation as a subsystem. (ISO/IEC/IEEE 12207) Includes, for example: a. All resources necessary to integrate the subsystem components as a complete subsystem b. Subsystem integration management c. Requirements definition, planning, and scheduling d. Development of integration plans and procedures e. Integration test preparations, conduct testing, post-test teardown and review analysis, and documentation of subsystem integration results.
1.1.2.2 | Subsystem Hardware 1...n (Specify) | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | B.4.2.2.2 Subsystem Hardware 1...n (Specify). The hardware and associated resource components of the specific electronic or generic subsystem.
1.1.2.3 | Subsystem Software Release 1...n (Specify) | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | B.4.2.2.3 Subsystem Software Release 1...n (Specify). The resources associated with the subsystem software for release 1...n. A software release is an aggregate of one or more CSCIs that satisfies a specific set or subset of requirements. When incremental, spiral, or other software development methods are used, multiple releases may be necessary to meet program requirements. A release is a separately tested and delivered product. Within releases are CSCIs. When a release is complete, a portion or all of one or more CSCIs will be completed. Therefore, a CSCI may appear in one or more releases of software, but will be successively more functional as each release of software is completed. (Note: The term “release” used in agile development should not be confused with the release of software as defined above. The MIL-STD definition is similar to multiple EPIC level CSCIs in Agile. In other words, a release of one or more EPIC level CSCIs is equivalent to a release in the MIL-STD.) Includes, for example: a. Computer Software Configuration Item (CSCI) 1...n b. Subsystem Integration, Assembly, Test, and Checkout
1.1.3 | PMP Software Release 1...n (Specify) | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | B.4.2.3 Prime Mission Product Software Release 1...n (Specify). The resources associated with PMP software that are not associated with a specific PMP subsystem (i.e., distributed software environment) for release (1...n). Includes, for example: a. Computer Software Configuration Item (CSCI) 1...n b. Software Integration, Assembly, Test, and Checkout
1.1.3.1 | Computer Software Configuration Item (CSCI) 1...n (Specify) | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | B.4.2.3.1 Computer Software Configuration Item (CSCI) 1...n (Specify). An aggregation of software or any of its discrete portions that satisfies an end use function and has been designated by the Government or contractor, if the Government did not specify, for configuration management. CSCIs are the major software products of a system acquisition, which are developed in accordance with standard DoD or commercial practices and processes. Includes, for example: a. Software requirements b. Software architecture and design c. Software code and unit test d. Software integration e. Software qualification testing f. Commercial off-the-shelf (COTS)/Government off-the-shelf (GOTS) approach g. COTS/GOTS component identification h. COTS/GOTS assessment and selection i. COTS/GOTS prototyping j. COTS/GOTS glue code development k. COTS/GOTS tailoring and configuration When software development is accomplished, items (a) through (e) are typical development activities. When COTS/GOTS is to be used and integrated, items (f) through (k) are typical integration activities. CSCIs may align to major capabilities that span the software architecture.
1.1.3.2 | PMP Software Integration, Assembly, Test, and Checkout | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | B.4.2.3.2 PMP Software Integration, Assembly, Test, and Checkout. The element includes the effort and material associated with integrating and testing subsystem software CSCIs and hardware of an individual (or group of) subsystem software that have undergone individual CSCI qualification test. Excludes, for example: a. Software development efforts necessary for external system interfaces
1.2 | Platform Integration, Assembly, Test, and Checkout | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | B.4.3 Platform Integration, Assembly, Test, and Checkout. The effort involved in providing technical and engineering services to the platform manufacturer or integrator during the installation and integration of the PMP into the host system. Includes, for example: a. Labor required to analyze, design, and develop the interfaces with other host vehicle subsystems b. Drawing preparation and establishment of equipment requirements and specifications c. Technical liaison and coordination with the military services subcontractors, associated contractors, and test groups Excludes, for example: a. All integration effort not directly associated with the host vehicle and management liaison with the military services, subcontractors, and associated contractors
1.3 | Systems Engineering | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.2 Systems Engineering. The technical and management efforts of directing and controlling a totally integrated engineering effort of a system or program. The following represent many, but not all, of the systems engineering efforts needed for a system or program. If required, one or more areas of effort (e.g., software systems engineering, cybersecurity, etc., may be identified at the next level below systems engineering. In those cases, the remaining totality of systems engineering efforts will be defined as “core systems engineering” at the level equal to the segregated items.
1.3.1 | Software Systems Engineering | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.2.1 Software Systems Engineering. The efforts which encompass software systems technologies, software engineering methods, and management techniques that improve the quality and delivery of software intensive systems and applications. Includes, for example: a. The application of a systematic, disciplined, quantifiable approach to the development and operations and support (O&S) of software b. The determination of software development or software test facility/environment requirements c. Application of systems engineering to software, that is, the systematic application of scientific and technical knowledge, methods, and experience to the design, implementation, testing, and documentation of software d. Analyzing the system requirements allocated to the software, developing the software requirements, developing the software architecture, designing the software, implementing the software in the code, integrating the software components, and testing the software to verify that the software satisfies the specified requirements allocated to the software component of a system or subsystem.
1.3.2 | Integrated Logistics Support (ILS) Systems Engineering | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.2.2 Integrated Logistics Support (ILS) Systems Engineering. The efforts to ensure the integrated planning and action of a number of disciplines in concert with one another to assure system availability. The planning of each element of ILS (e.g., integrated product support (IPS) elements) is developed in coordination with systems engineering and other efforts. Includes, for example: a. Product support management b. Design interface c. Sustaining engineering d. Supply support e. Maintenance planning and management f. Packaging, handling, storage, and transportation g. Technical data h. Support equipment i. Training and training support j. Manpower and personnel k. Facilities and infrastructure l. Computer resources
1.3.3 | Cybersecurity Systems Engineering | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.2.3 Cybersecurity Systems Engineering. The efforts to apply scientific and engineering principles to identify security vulnerabilities and minimize or contain risks associated with these vulnerabilities. Includes, for example: a. Cybersecurity requirements evaluation b. Cyberattack surface characterization c. Cooperative vulnerability identification d. Vulnerability analysis e. System cross-functional cyber analysis f. Advise on RMF compliance tasks/documents (security assessment plan, etc.) g. Security configuration management (assess planned services for risk and impact) h. Develop system-level security architecture i. Design, develop, and implement system security measures that meets technical requirements j. Develop and implement specific security countermeasures for the system k. Develop approaches to mitigate system vulnerabilities l. Ensure the design of hardware, operating systems, and software applications adequately address cybersecurity requirements for the system
1.3.4 | Core Systems Engineering | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.2.4 Core Systems Engineering. The technical and management efforts that establish the technical framework for delivering materiel capabilities and ensure the effective development and delivery of capability through the implementation of a balanced approach with respect to cost, schedule, performance, and risk. This effort uses integrated, disciplined and consistent systems engineering activities and processes for development of resilient systems that are trusted, assured and easily modified. Systems engineering is composed of 16 processes: eight technical processes and eight technical management processes. These processes provide a structured approach to increasing the technical maturity of a system and increasing the likelihood that the capability being developed balances mission performance with cost, schedule, risk, and design constraints. To fulfill that purpose, a program implements the systems engineering technical processes to support the iterative maturation of the system solution or operational need. The technical processes enable the systems engineering team to ensure that the delivered capability accurately reflects the operational needs of the stakeholders. The technical processes include top down design processes such as stakeholder requirements definition, requirements analysis, and architecture design, as well as bottom-up realization processes such as transition, validation, verification, integration, and implementation. The eight technical management processes are implemented across the acquisition life cycle and provide insight and control to assist the program manager and systems engineer to meet performance, schedule, and cost goals. The eight technical processes closely align with the acquisition life cycle phases and include the top-down design processes and bottom-up realization processes that support transformation of operational needs into operational capabilities. The eight technical management processes are: decision analysis, technical planning, technical assessment, requirements management, risk management, configuration management, technical data management, and interface management. Also included are specialty engineering disciplines which bring together the hardware, software, and human elements of the systems. Includes, for example: a. System safety which is applicable to most DoD systems; this reflects the ubiquitous nature of software-driven functions, network connectivity, and systems of systems; specific certifications include safety, security, cybersecurity and airworthiness b. Reliability and maintainability – ensure that design interface and integration of the quantitative systems engineering design characteristics (i.e., reliability, maintainability, etc.) with the functional integrated product support elements c. Quality – ensures configuration item level requirements for the systems and subsystems meet critical functions and key quality attributes. d. Manufacturing and producibility – ensure manufacturing and producibility readiness, processes assessed and demonstrated, and risks identified, managed and reduced throughout the program’s life cycle e. Human systems integration – optimize total system performance and total ownership costs, while ensuring that the system is designed, operated, and maintained to effectively provide the user with the ability to complete their mission; ensure ergonomics, human factors engineering, and cognitive engineering is employed to provide for effective human-machine interfaces; define the human performance characteristics of the user based on the system description, projected characteristics of target occupational specialties, and recruitment and retention trends; establish requirements for the physical environment; determine the most efficient and cost-effective mix of DoD manpower and contract support; develop training options for operators, maintenance and support personnel; ensure that appropriate environmental safety and occupational health; assess risks to personnel and address, in terms of system design, protection from direct threat events and accidents (such as chemical, biological, and nuclear threats). f. System of systems (SoS) and system level architecting, modeling and simulation, verification and validation and external interface definition and management g. For sea systems; the Expanded Ship Work Breakdown Structure (ESWBS), configuration management (811), human factors (892), standardization (893), value engineering (894), and reliability and maintainability (895) elements Excludes, for example: a. Actual design engineering and the production engineering directly related to the WBS element with which it is associated b. Any systems engineering efforts that are called out in software systems engineering, ILS systems engineering, cybersecurity systems engineering, or “other” systems engineering effort separately identified in the WBS.
1.3.5 | Other Systems Engineering 1...n (Specify) | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.2.5 Other Systems Engineering 1...n (Specify). This element should be replaced with other systems engineering elements that cannot be categorized into one of the above elements or need to be separately identified due to high cost, high risk concerns within systems engineering. Each additional element is to be clearly identified and defined.
1.4 | Program Management | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.3 Program Management. The business and administrative planning, organizing, directing, coordinating, controlling, and approval actions designated to accomplish overall program objectives, which are not associated with specific hardware elements and are not included in systems engineering. If required, one or more areas of effort (e.g., software program management, cybersecurity program management, etc.,) may be identified at the next level below program management. In those cases, the remaining totality of program management efforts will be defined as “core program management” at the level equal to the segregated items.
1.4.1 | Software Program Management | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.3.1 Software Program Management. The software program management encompasses the management of the full software life cycle, from conception to deployment. The function focuses at the system level of applying business and project management skills needed to produce high-quality software products. Includes, for example: a. Overseeing requirements analysis and design, and effective implementation and delivery of all fully-tested software b. Ensure sufficient end-user involvement c. Maintain communication among customers, developers, users, and project managers d. Establish realistic or articulated project goals e. Develop accurate estimates of needed resources f. Define system requirements and specifications g. Assure reporting of the project’s status h. Proper management of risks i. Ensure the use of mature technology and handle the project’s complexity
1.4.2 | Integrated Logistics Support (ILS) Program Management | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.3.2 Integrated Logistics Support Program Management. The efforts to manage the planning and execution of the ILS disciplines to assure system acquisition logistics availability. Includes, for example: a. Support element management, defined as the logistics tasks management effort and technical control, and the business management of the support elements. The logistics management function encompasses the support evaluation and supportability assurance required to produce an affordable and supportable defense materiel system. b. Planning and management of all the functions of logistics. Examples are: maintenance support planning and support facilities planning; other support requirements determination; support equipment requirements determination; supply support; packaging, handling, storage, and transportation; provisioning requirements determination and planning; training system requirements determination; computer resource determination; organizational, intermediate, and depot maintenance determination management; and data management
1.4.3 | Cybersecurity Management | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.3.3 Cybersecurity Program Management. The management and understanding of cybersecurity program and its ramifications across the organization (only if costs are collected in this manner). Includes, for example: a. Overseeing cybersecurity risk assessment, management, and mediation b. Cybersecurity threat vectors and mitigation processes c. Ensuring design and management of secure information systems d. Emerging tools and resources for organizational and platform security
1.4.4 | Core Program Management | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.3.4 Core Program Management. The efforts to understand and manage multiple discipline areas in order the successfully accomplish program objectives for development, production, and sustainment of systems to meet the user’s operational needs Includes, for example: a. Cost, schedule, performance measurement management, warranty administration, contract management, vendor liaison, subcontract management, etc. b. For sea systems; the Expanded Ship Work Breakdown Structure (ESWBS), project management (897); data management (896); and supply support (853) elements Excludes, for example: a. Actual program management directly related to another WBS element b. Any program management efforts that are called out in software program management, cybersecurity program management, or “other” program management effort separately identified in the WBS.
1.4.5 | Other Program Management 1...n (Specify) | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.3.5 Other Program Management 1...n (Specify). This element should be replaced with other program management elements that cannot be categorized into one of the above elements or need to be separately identified due to high cost or high risk concerns within program management. Each additional element is to be clearly identified and defined.
1.5 | System Test and Evaluation | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.4 System Test and Evaluation. The use of pilot, prototype, production, or specifically fabricated hardware/software to obtain or validate engineering data on the performance of the system during the developmental phase of the program. It also includes all effort associated with the development of any specialized tools or data in support of the system level test program. Includes, for example: a. Detailed planning, conduct, support, data reduction and reports (excluding the contract data requirements list data) from such testing, and test articles that are functionally configured to represent and test subsystems/components of the defense materiel end item being developed or produced b. Design and production of models, specimens, fixtures and instrumentation c. System level labs that integrate both hardware and software NOTE: Test articles that are functionally configured to represent and test the complete defense materiel end item being developed or produced, are excluded from this WBS element. Excludes, for example: a. All formal and informal testing up through the subsystem level, which can be associated with the hardware/software element acceptance testing NOTE: These excluded efforts are to be included with the appropriate hardware or software elements.
1.5.1 | Development Test and Evaluation | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.4.1 Development Test and Evaluation. The test and evaluation conducted by the developing agency of the DoD component. It includes test and evaluation conducted to: a. Demonstrate that the engineering design and development process is complete b. Demonstrate that the design risks have been minimized c. Demonstrate that the system will meet specifications d. Assess the system’s military utility when introduced e. Determine whether the engineering design is supportable (practical, maintainable, safe, etc.) for operational use f. Provide test data with which to examine and evaluate trade-offs against specification requirements, life cycle cost, and schedule g. Perform the logistics testing efforts to evaluate the achievement of supportability goals, the adequacy of the support package for the system, (e.g., deliverable maintenance tools, test equipment, technical publications, maintenance instructions, and personnel skills and training requirements, etc.) Includes, for example: a. All contractor/system developer in-house effort b. Where applicable, models, tests and associated simulations (e.g., such as wind tunnel, static, drop, and fatigue); integration ground tests; test bed aircraft and associated support; qualification test and evaluation, development flight test, test instrumentation, environmental tests, ballistics, radiological, range and accuracy demonstrations, test facility operations, test equipment (including its support equipment), chase and calibrated pacer aircraft and support thereto, and logistics testing c. For aircraft; avionics integration test composed of the following: i. Test bench/laboratory, including design, acquisition, and installation of basic computers and test equipment that will provide an ability to simulate in the laboratory the operational environment of the avionics system/subsystem ii. Air vehicle equipment, consisting of the avionics and/or other air vehicle subsystem modules that are required by the bench/lab or flying test bed in order to provide a compatible airframe avionics system/subsystem for evaluation purposes iii. Flying test bed, including requirements analysis, design of modifications, lease or purchase of test bed aircraft, modification of aircraft, installation of avionics equipment and instrumentation, and checkout of an existing aircraft used essentially as a flying avionics laboratory iv. Avionics test program, consisting of the effort required to develop test plans/procedures, conduct tests, and analyze hardware and software test results to verify the avionics equipment’s operational capability and compatibility as an integrated air vehicle subsystem v. Software, referring to the effort required to design, code, de-bug, and document software programs necessary to direct the avionics integration test d. For engines: engine military qualification tests and engine preliminary flight rating tests e. For sea systems: model basin, hydrostatic, fatigue, shock, special sea tests and trials, etc., including the Expanded Ship Work Breakdown Structure (ESWBS), trials agenda preparation, data collection and analysis (842); dock and sea trials (9823); and hull vibration survey (9825) elements f. For missiles: test articles such as inert measurement vehicles, launch separation vehicles, separation and control test vehicles, boost test vehicles g. For ordnance: test articles such as ballistic test rounds, inert measurement rounds, dummy rounds, launch separation rounds, etc.
1.5.2 | Operational Test and Evaluation | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.4.2 Operational Test and Evaluation. The test and evaluation conducted by agencies other than the developing command to assess the prospective system’s military utility, operational effectiveness, operational suitability, logistics supportability (including compatibility, inter-operability, reliability, maintainability, logistic requirements, etc.), cost of ownership, and need for any modifications. Includes, for example: a. Initial operational test and evaluation conducted during the development of a system b. Such tests as system demonstration, flight tests, sea trials, mobility demonstrations, on-orbit tests, spin demonstration, stability tests, qualification operational test and evaluation, etc., and support thereto, required to prove the operational capability of the deliverable system. c. Contractor support (e.g., technical assistance, maintenance, labor, material, etc.) consumed during this phase of testing d. Logistics testing efforts to evaluate the achievement of supportability goals and the adequacy of the support for the system (e.g., deliverable maintenance tools, test equipment, technical publications, maintenance instructions, personnel skills and training requirements, and software support facility/environment elements)
1.5.3 | Cybersecurity Test and Evaluation | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.4.3 Cybersecurity System Test and Evaluation. The developmental test and evaluation and operational test and evaluation conducted and monitored by the developing agency of the DoD. The technical efforts of ensuring the confidentiality, integrity, and availability of information and technology by monitoring and defending against cyber (network) attacks. Includes, for example: a. Vulnerability scanning and interpretation b. Vulnerability testing and penetration testing (usually linked to patch management) c. Security information and event management d. Destructive and non-destructive exploitation e. Test conducted in an operational environment with certified red teams f. Cybersecurity compliance tracking and reporting g. Malware scanning, detection, and prevention services h. Security, IT certification, and accreditation compliance services
1.5.4 | Mock-ups/System Integration Labs (SILs) | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.4.4 Mock-ups/System Integration Labs (SILs). The design engineering and production of system or subsystem mock-ups that have special contractual or engineering significance or that are not required solely for the conduct of one of the above elements of testing. SILs are often used in lieu of (or in addition to) mock-ups. SILs are risk reduction facilities where software and hardware can be developed, integrated, tested, and evaluated for both standalone functionality and/or interoperability prior to being fielded. Includes, for example: a. Hardware/lab equipment b. SIL Software (written to simulate the operating environment or written to operate the SIL)
1.5.5 | Test and Evaluation Support | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.4.5 Test and Evaluation Support. The support elements necessary to operate and maintain, during test and evaluation, systems and subsystems, which are not consumed during the testing phase and are not allocated to a specific phase of testing. Includes, for example: a. Repairable spares, repair of reparables, repair parts, consumables, warehousing and distribution of spares and repair parts, test and support equipment, test bed vehicles, drones, surveillance aircraft/chase aircraft, tracking vessels, contractor technical support Excludes, for example: a. Operational and maintenance personnel, special fixtures, special instrumentation, etc., that are utilized and/or consumed in a single element of testing and that should be included under that element of testing
1.5.6 | Test Facilities | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.4.6 Test Facilities. The special test facilities required for performance of the various developmental tests necessary to prove the design and reliability of the system or subsystem. Includes, for example: a. Test tank test fixtures, propulsion test fixtures, white rooms, test chambers, range/targeting facilities Excludes, for example: a. Brick and mortar-type facilities identified as industrial facilities
1.6 | Training | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.5 Training. Deliverable training services, devices, accessories, aids, equipment, and parts used to facilitate instruction through which personnel will learn to operate and maintain the system with maximum efficiency. Includes, for example: a. All effort associated with the design, development, and production of deliverable training equipment and its associated software as well as the execution of training services Excludes, for example: a. Overall planning, management, and task analysis functions inherent in the WBS element systems engineering/program management
1.6.1 | Equipment | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.5.1 Equipment. Distinctive deliverable end items of training equipment, assigned by either a contractor or military service, required to meet specific training objectives. Includes, for example: a. Operational and Maintenance Trainers and training equipment including items such as cutaways, mock-ups, and models (e.g. Operator Instructional Equipment, Maintainer Instructional Equipment)
1.6.1.1 | Operator Instructional Equipment | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | [Blank]
1.6.1.2 | Maintainer Instructional Equipment | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | [Blank]
1.6.2 | Services | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.5.2 Services. Deliverable training services, accessories, and courseware aids necessary to accomplish the objectives of training. Includes, for example: a. Operational and Maintenance Training Services including courses, course materials; and curriculum required to design, execute, and produce a contractor developed training program and related software programs (e.g. operator instructional services, maintainer instructional services) Excludes, for example: a. Deliverable training data associated with support data (see Data Deliverables 1...n (Specify), Support Data)
1.6.2.1 | Operator Instructional Services | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | [Blank]
1.6.2.2 | Maintainer Instructional Services | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | [Blank]
1.6.3 | Facilities | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.5.3 Facilities. The special construction necessary to accomplish training objectives. Includes, for example: a. Modification or rehabilitation of existing training facilities and infrastructure used to accomplish training objectives Excludes, for example: a. Installed equipment used to acquaint the trainee with the system or establish trainee proficiency b. The brick and mortar-type facilities identified as industrial facilities
1.6.4 | Training Software 1...n (Specify) | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.5.4 Training Software Release 1...n (Specify). Updated/upgraded software for training purposes delivered to the field during the acquisition phase.
1.7 | Data | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.6 Data. The deliverable data required to be listed on a contract data requirements list. Includes, for example: a. Only such effort that can be reduced or avoided if the data item is eliminated b. Government-peculiar data; acquiring, assembling, reproducing, packaging and shipping the data c. Transforming data into Government
1.7.1 | Data Deliverables 1...n (Specify) | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.6.1 Data Deliverables 1...n (Specify). Deliverable data which provides technical, engineering, management, support, or other data required for contract delivery. Includes, for example: a. Technical Publications. Technical data, providing instructions for installation, operation, maintenance, training, and support, formatted into a technical manual. Data may be presented in any form regardless of the form or method of recording. Technical orders that meet the criteria of this definition may also be classified as technical manuals. For sea systems: Expanded Ship Work Breakdown Structure (ESWBS), technical manuals and other data (856) element. b. Engineering Data. Recorded scientific or technical information (regardless of the form or method of recording) including computer software documentation. Engineering data defines and documents an engineering design or product configuration (sufficient to allow duplication of the original items) and is used to support production, engineering, and logistics activities. For sea systems; Expanded Ship Work Breakdown Structure (ESWBS), design support, ship’s selected records (8302); design support, services, reproduction (8303); and engineering drawings and specifications (855) elements. c. Management Data. The data items necessary for configuration management, cost, schedule, contractual data management, program management, etc., required by the Government. For sea systems; Expanded Ship Work Breakdown Structure (ESWBS), contract data requirements (988) element. d. Support Data. The data items designed to document support planning in accordance with functional categories
1.7.2 | Data Repository | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.6.2 Data Repository. The activity and enterprise data storage entity (or sometimes entities) for Government approved documents that are the property of the Government into which data has been specifically partitioned for analytical or reporting purposes. As custodian for the Government, the repository, authorized by approved change orders, maintains master documents at the latest approved revision level. Includes, for example: a. All effort necessary to maintain documents
1.7.3 | Data Rights 1...n (Specify) | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.6.3 Data Rights 1...n (Specify). Government’s license rights of valuable intellectual property including technical data of any recorded information of a scientific or technical nature (e.g., product design or maintenance data, computer databases, and computer software documentation); and computer software including executable code, source code, code listings, design details, processes, flow charts, and related material. Includes, for example: a. Unlimited Rights. Developed exclusively at Government expense, and certain types of data (e.g., Form, Fit, and Function data (FFF); Operation, Maintenance, Installation, and Training (OMIT)). These rights involve the right to use, modify, reproduce, display, release, or disclose technical data in whole or in part, in any manner, and for any purpose whatsoever, and to have or authorize others to do so. b. Government Purpose Rights. This right involves the right to use, duplicate, or disclose technical data for Government purposes only, and to have or permit others to do so for Government purposes only. Government purposes include competitive procurement, but do not include the right to permit others to use the data for commercial purposes. c. Limited Rights. A limited rights agreement permits the Government to use proprietary technical data in whole or in part. It also means that the Government has to obtain the expressed permission of the party providing the technical data to release it, or disclose it, outside the Government.
1.8 | Peculiar Support Equipment | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.7 Peculiar Support Equipment. The design, development, and production of those deliverable items and associated software required to support and maintain the system or portions of the system while the system is not directly engaged in the performance of its mission, and which are not common support equipment. Items should be designated by commodity subassembly (airframe, engine, avionics, etc.). Includes, for example: a. Vehicles, equipment, tools, etc., used to fuel, service, transport, hoist, repair, overhaul, assemble, disassemble, test, inspect, or otherwise maintain mission equipment b. Any production of duplicate or modified factory test or tooling equipment delivered to the Government for use in maintaining the system. (Factory test and tooling equipment initially used by the contractor in the production process but subsequently delivered to the Government will be included as cost of the item produced.) c. Any additional equipment or software required to maintain or modify the software portions of the system Excludes, for example: a. Overall planning, management, and task analysis functions inherent in the work breakdown structure elements Systems Engineering and Program Management b. Common support equipment, presently in the DoD inventory or commercially available, bought by the using command, not by the acquiring command
1.8.1 | Test and Measurement Equipment | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.7.1 Test and Measurement Equipment. The peculiar or unique testing and measurement equipment that allows an operator or maintenance function to evaluate operational conditions of a system or equipment by performing specific diagnostics, screening, or quality assurance effort at an organizational, intermediate, or depot level of equipment support. Includes, for example: a. Test measurement and diagnostic equipment, precision measuring equipment, automatic test equipment, manual test equipment, automatic test systems, test program sets, appropriate interconnect devices, automated load modules, tapes, and related software, firmware and support hardware (power supply equipment, etc.) used at all levels of maintenance b. Packages that enable line or shop replaceable units, printed circuit boards, or similar items to be diagnosed using automatic test equipment
1.8.1.1 | Test and Measurement Equipment (Airframe/Hull/Vehicle) | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.7.1.1 Test and Measurement Equipment (Airframe/Hull/Vehicle). This element captures the cost of the airframe, ship hull, or ground vehicle hull/frame related test and measurement equipment. Identify the related WBS subassemblies associated with the airframe/hull/vehicle. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested
1.8.1.2 | Test and Measurement Equipment (Propulsion) | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.7.1.2 Test and Measurement Equipment (Propulsion). This element captures the cost of the propulsion system, engines, prime movers, turbines, etc. related test and measurement equipment. Identify the related WBS subassemblies associated with propulsion. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.8.1.3 | Test and Measurement Equipment (Electronics/Avionics) | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.7.1.3 Test and Measurement Equipment (Electronics/Avionics). This element captures the cost of the electronics/avionics related test and measurement equipment. Identify the related WBS subassemblies associated with electronics/avionics. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.8.1.4 | Test and Measurement Equipment (Other Major Subsystems 1...n (Sif)) | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.7.1.4 Test and Measurement Equipment (Other Major Subsystem 1...n (Specify)). This element captures the cost of other major subsystems (e.g., armament, weapons, vehicle subsystems, etc.) not captured above related test and measurement equipment. Identify the related WBS subassemblies associated with the other major subsystems. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.8.2 | Support and Handling Equipment | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.7.2 Support and Handling Equipment. The peculiar or unique tools and handling equipment used for support of the mission system at an organizational, intermediate, or depot level Includes, for example: a. Ground support equipment, vehicular support equipment, powered support equipment, non-powered support equipment, munitions material handling equipment, materiel handling equipment, and software support equipment (hardware and software)
1.8.2.1 | Support and Handling Equipment (Airframe/Hull/Vehicle) | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.7.2.1 Support and Handling Equipment (Airframe/Hull/Vehicle). This element captures the cost of the airframe, ship hull, or ground vehicle hull/frame related support and handling equipment. Identify the related WBS subassemblies associated with airframe/hull/vehicle. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.8.2.2 | Support and Handling Equipment (Propulsion) | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.7.2.2 Support and Handling Equipment (Propulsion). This element captures the cost of propulsion related support and handling equipment. Identify the related WBS subassemblies associated with propulsion. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.8.2.3 | Support and Handling Equipment (Electronics/Avionics) | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.7.2.3 Support and Handling Equipment (Electronics/Avionics). This element captures the cost of the electronics/avionics related support and handling equipment. Identify the related WBS subassemblies associated with electronics/avionics. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.8.2.4 | Support and Handling Equipment (Other Major Subsystems 1...n (Specify)) | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.7.2.4 Support and Handling Equipment (Other Major Subsystem 1...n (Specify)). This element captures the cost of other major subsystems (e.g., armament, weapons, vehicle subsystems, etc.) not captured above related support and handling equipment. Identify the related WBS subassemblies associated with the other major subsystems. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.9 | Common Support Equipment | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.8 Common Support Equipment. The items required to support and maintain the system or portions of the system while not directly engaged in the performance of its mission, and which are presently in the DoD inventory for support of other systems. Includes, for example: a. Acquisition of additional quantities of this equipment needed to support the item b. All efforts required to assure the availability of this equipment to support the item
1.9.1 | Test and Measurement Equipment | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.8.1 Test and Measurement Equipment. The common testing and measurement equipment that allows an operator or maintenance function to evaluate operational conditions of a system or equipment by performing specific diagnostics, screening, or quality assurance effort at an organizational, intermediate, or depot level of equipment support. Includes, for example: a. Test measurement and diagnostic equipment, precision measuring equipment, automatic test equipment, manual test equipment, automatic test systems, test program sets, appropriate interconnect devices, automated load modules, tapes, and related software, firmware, and support hardware (power supply equipment, etc.) Used at all levels of maintenance b. Packages that enable line or shop replaceable units, printed circuit boards, or similar items to be diagnosed using automatic test equipment
1.9.1.1 | Test and Measurement Equipment (Airframe/Hull/Vehicle) | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.8.1.1 Test and Measurement Equipment (Airframe/Hull/Vehicle). This element captures the cost of the airframe, ship hull, or ground vehicle hull/frame related test and measurement equipment. Identify the related WBS subassemblies associated with the airframe/hull/vehicle. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.9.1.2 | Test and Measurement Equipment (Propulsion) | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.8.1.2 Test and Measurement Equipment (Propulsion). This element captures the cost of the propulsion system, engines, prime movers, turbines, etc. related test and measurement equipment. Identify the related WBS subassemblies associated with propulsion. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.9.1.3 | Test and Measurement Equipment (Electronics/Avionics) | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.8.1.3 Test and Measurement Equipment (Electronics/Avionics). This element captures the cost of the electronics/avionics related test and measurement equipment. Identify the related WBS subassemblies associated with electronics/avionics. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.9.1.4 | Test and Measurement Equipment (Other Major Subsystems 1...n (Specify)) | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.8.1.4 Test and Measurement Equipment (Other Major Subsystem 1...n (Specify)). This element captures the cost of other major subsystems (e.g., armament, weapons, vehicle subsystems, etc.) not captured above related test and measurement equipment. Identify the related WBS subassemblies associated with the other major subsystems. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.9.2 | Support and Handling Equipment | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.8.2 Support and Handling Equipment. The common tools and handling equipment used for support of the mission system at an organizational, intermediate, or depot level Includes, for example: a. Ground support equipment, vehicular support equipment, powered support equipment, non-powered support equipment, munitions material handling equipment, materiel handling equipment, and software support equipment (hardware/software)
1.9.2.1 | Support and Handling Equipment (Airframe/Hull/Vehicle) | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.8.2.1 Support and Handling Equipment (Airframe/Hull/Vehicle). This element captures the cost of the airframe, ship hull, or ground vehicle hull/frame related support and handling equipment. Identify the related WBS subassemblies associated with airframe/hull/vehicle. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.9.2.2 | Support and Handling Equipment (Propulsion) | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.8.2.2 Support and Handling Equipment (Propulsion). This element captures the cost of propulsion related support and handling equipment. Identify the related WBS subassemblies associated with propulsion. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.9.2.3 | Support and Handling Equipment (Electronics/Avionics) | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.8.2.3 Support and Handling Equipment (Electronics/Avionics). This element captures the cost of the electronics/avionics related support and handling equipment. Identify the related WBS subassemblies associated with electronics/avionics. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.9.2.4 | Support and Handling Equipment (Other Major Subsystems 1...n (Specify)) | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.8.2.4 Support and Handling Equipment (Other Major Subsystem 1...n (Specify)). This element captures the cost of other major subsystems (e.g., armament, weapons, vehicle subsystems, etc.) not captured above related support and handling equipment. Identify the related WBS subassemblies associated with the other major subsystems. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.1 | Operational/Site Activation by Site 1...n (Specify) | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.9 Operational/Site Activation by Site 1...n (Specify). The real estate, construction, conversion, utilities, and equipment to provide all facilities required to house, service, and launch prime mission equipment at the organizational and intermediate level. Includes, for example: a. Conversion of site, ship, or vehicle b. System assembly, checkout, and installation (of mission and support equipment) into site facility or ship to achieve operational status c. Contractor support in relation to operational/site activation
1.10.1 | System Assembly, Installation, and Checkout on Site | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.9.1 System Assembly, Installation, and Checkout. The materials and services involved in the assembly of mission equipment at the site. Includes, for example: a. Installation of mission and support equipment in the operations or support facilities and complete system checkout or shakedown to ensure operational status. Where appropriate, specify by site, ship, or vehicle. b. The efforts and activities associated with shipping the system from contractor facility to customer site. That site could be a DT&E site, an installation and checkout site, or any similar site that is outside the direct control of the contractor. Excludes, for example: a. Field team installation
1.10.2 | Contractor Technical Support | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.9.2 Contractor Technical Support. The materials and services provided by the contractor related to activation. Includes, for example: a. Repair of reparables, standby services, and final turnover
1.10.3 | Site Construction | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.9.3 Site Construction. Real estate, site planning and preparation, construction, and other special-purpose facilities necessary to achieve system operational status. Includes, for example: a. Construction of utilities, roads, and interconnecting cabling
1.10.4 | Site /Ship/Vehicle Conversion | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.9.4 Site/Ship/Vehicle Conversion. The materials and services required to convert existing sites, ships, or vehicles to accommodate the mission equipment and selected support equipment directly related to the specific system. Includes, for example: a. Operations, support, and other special purpose facilities conversion necessary to achieve system operational status, e.g., launch. Where appropriate, specify by site, ship, or vehicle
1.10.5 | Interim Contractor Support (ICS) | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.9.5 Interim Contractor Support (ICS). The effort required to provide temporary contractor support in lieu of a permanent support solution (organic or commercial) for a predetermined time, while a permanent support capability is put in place. Interim support is usually required for support of prototypes and early test and production assets during development and initial fielding (i.e., Initial Operating Capability (IOC)). Includes, for example: a. Providing life cycle logistics in accordance with the integrated product support (IPS) elements in support of the prime mission product. Excludes, for example: a. The development and production of the original prime mission product.
1.11 | Contractor Logistics Support (CLS) | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.10 Contractor Logistics Support (CLS). Contracted weapon system sustainment including performance of maintenance and/or materiel management functions for a DoD weapon system by a commercial activity or contractor sustainment of a weapon system that is intended to start after a permanent decision is made to cover the operations and support efforts of the weapon system. CLS generally starts before FOC (final operating capability) or when performance based logistics (PBL) is implemented in the operating and support (O&S) phase. Includes, for example: a. Prime Mission Product (PMP) maintenance and refurbishment. The cost for this element includes maintenance and refurbishment (including the development and production) of existing operational systems. b. Support functions required to maintain the system, such as sustaining engineering, program management, logistics support, and supply chain management c. Test and evaluation for system and subsystem modifications d. Repair of reparable items; replacement of condemned items (including all PMP, support equipment, and training equipment) e. Operational, maintenance and other personnel required at the operational unit level f. Unit operations costs, including operating material and support services at the operating unit g. Installation and personnel support functions in support of the unit level manpower Excludes, for example: a. Does not include interim contractor support (ICS), a temporary measure for a system’s initial period of operation before a permanent form of support is in place. b. Contractor sustainment support for a specific sustainment task that a service would otherwise conduct itself.
1.12 | Industrial Facilities | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.11 Industrial Facilities. The construction, conversion, or expansion of industrial facilities for production, inventory, and contractor depot maintenance required when that service is for the specific system. Includes, for example: a. Equipment acquisition or modernization, where applicable b. Maintenance of these facilities or equipment c. Industrial facilities for hazardous waste management to satisfy environmental standards Excludes, for example: a. Capital equipment
1.12.1 | Construction/Conversion/Expansion | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.11.1 Construction/Conversion/Expansion. The real estate and preparation of system peculiar industrial facilities for production, inventory, depot maintenance, and other related activities.
1.12.2 | Equipment Acquisition or Modernization | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.11.2 Equipment Acquisition or Modernization. The production equipment acquisition, modernization, or transfer of equipment for the particular system. This pertains to Government owned and leased equipment under facilities contract.
1.12.3 | Maintenance (Industrial Facilities) | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.11.3 Maintenance (Industrial Facilities). The maintenance, preservation, and repair of industrial facilities and equipment.
1.13 | Initial Spares and Repair Parts | APPENDIX B: ELECTRONIC OR GENERIC SYSTEMS | K.3.12 Initial Spares and Repair Parts. The deliverable spare components, assemblies, and subassemblies used for initial replacement purposes in the materiel system equipment end item. Includes, for example: a. Repairable spares (reparables) and repair parts required as initial stockage to support and maintain newly fielded systems or subsystems during the initial phase of service, including pipeline and war reserve quantities, at all levels of maintenance and support. Lower level WBS breakouts should be by subsystem. b. Spare training and support equipment items c. The combination of resources, processes, planning, procedures, design, considerations, methods, and all hardware to ensure that all system, equipment, and support items are preserved, packaged, handled, and transported properly, including environmental considerations, equipment preservation for short and long term storage, and transportability. This includes requirements such as special environmentally controlled, shock isolated containers for transport to and from repair facilities and ensuring proper Care of Supplies in Storage (COSIS) program requirements are followed. Excludes, for example: a. Development test spares and spares provided specifically for use during installation, assembly, and checkout on site

## C
WBS # | WBS Nomenclature | Appendix | WBS Definition
1 | Missile/Ordnance System | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.1 | Missile/Ordnance System Integration, Assembly, Test, and Checkout | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2 | Air Vehicle/Munition | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.1 | Air Vehicle/Munition Integration, Assembly, Test, and Checkout | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.2 | Airframe | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.2.1 | Airframe Integration, Assembly, Test, and Checkout | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.2.2 | Primary Structure | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.2.3 | Secondary Structure | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.2.4 | Aero-Structures | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.2.5 | Other Airframe Components 1...n (Specify) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.3 | Propulsion Subsystem 1...n (Specify) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.3.1 | Propulsion Integration, Assembly, Test, and Checkout | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.3.2 | Motor/Engine (Specify) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.3.3 | Fuel Management | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.3.4 | Thrust Vector Actuation | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.3.5 | Attitude Control System | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.3.6 | Arm/Fire Device | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.3.7 | Flight Termination/Mission Termination | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.3.8 | Propulsion Software Release 1...n (Specify) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.3.9 | Other Propulsion Subsystems 1...n (Specify) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.4 | Power and Distribution | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.4.1 | Power and Distribution Integration, Assembly, Test, and Checkout | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.4.2 | Primary Power | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.4.3 | Power Conditioning Electronics | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.4.4 | Distribution Harness | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.4.5 | Power and Distribution Software Release 1...n (Specify) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.4.6 | Other Power and Distribution Subsystems 1...n (Specify) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.5 | Guidance | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.5.1 | Guidance Integration, Assembly, Test, and Checkout | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.5.2 | Dome Assembly | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.5.3 | Seeker Assemblies | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.5.4 | Mission Computer | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.5.5 | Guidance Software Release 1...n (Specify) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.5.6 | Other Guidance Subsystems 1...n (Specify) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.6 | Navigation | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.6.1 | Navigation Integration, Assembly, Test, and Checkout | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.6.2 | Sensor Assemblies | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.6.3 | Navigation Software Release 1...n (Specify) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.6.4 | Other Navigation Subsystems 1...n (Specify) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.7 | Controls | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.7.1 | Controls Integration, Assembly, Test, and Checkout | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.7.2 | Primary Structure | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.7.3 | Fin/Canard Deployment System | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.7.4 | Actuators | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.7.5 | Control Power | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.7.6 | Controls Software Release 1...n (Specify) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.7.7 | Other Control Subsystems 1...n (Specify) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.8 | Communications | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.8.1 | Communications Integration, Assembly, Test, and Checkout | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.8.2 | Antenna Assembly | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.8.3 | Transmitter | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.8.4 | Receiver | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.8.5 | Communications Software Release 1...n (Specify) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.8.6 | Other Communications Subsystems 1...n (Specify) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.9 | Payload | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.9.1 | Payload Integration, Assembly, Test, and Checkout | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.9.2 | Target Defeat Mechanism | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.9.3 | Target Detection Device | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.9.4 | Fuze | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.9.5 | Payload Software Release 1...n (Specify) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.9.6 | Other Payload Subsystems 1...n (Specify) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.10 | On Board Test Equipment | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.11 | On Board Training Equipment | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.12 | Auxiliary Equipment | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.2.13 | Air Vehicle Software Release 1...n (Specify) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.3 | Encasement Device | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.3.1 | Encasement Device Integration, Assembly, Test, and Checkout | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.3.2 | Encasement Device Structure | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.3.3 | Encasement Device Software Release 1...n (Specify) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.3.4 | Other Encasement Device Subsystems 1...n (Specify) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.4 | Command and/or Launch | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.4.1 | Command and/or Launch Integration, Assembly, Test, and Checkout | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.4.2 | Surveillance, Identification and Tracking Sensors | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.4.3 | Communications | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.4.4 | Launcher | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.4.5 | Adapter Kits | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.4.6 | Launch and Guidance Control | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.4.7 | Ready Magazine | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.4.8 | Auxiliary Equipment | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.4.9 | Command and/or Launch Software Release 1...n (Specify) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.4.10 | Other Command and/or Launch 1...n (Specify) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.5 | Missile/Ordnance System Software Release 1...n (Specify) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.6 | Platform Integration, Assembly, Test, and Checkout 1...n (Specify) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS
1.7 | Systems Engineering | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.2 Systems Engineering. The technical and management efforts of directing and controlling a totally integrated engineering effort of a system or program. The following represent many, but not all, of the systems engineering efforts needed for a system or program. If required, one or more areas of effort (e.g., software systems engineering, cybersecurity, etc., may be identified at the next level below systems engineering. In those cases, the remaining totality of systems engineering efforts will be defined as “core systems engineering” at the level equal to the segregated items.
1.7.1 | Software Systems Engineering | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.2.1 Software Systems Engineering. The efforts which encompass software systems technologies, software engineering methods, and management techniques that improve the quality and delivery of software intensive systems and applications. Includes, for example: a. The application of a systematic, disciplined, quantifiable approach to the development and operations and support (O&S) of software b. The determination of software development or software test facility/environment requirements c. Application of systems engineering to software, that is, the systematic application of scientific and technical knowledge, methods, and experience to the design, implementation, testing, and documentation of software d. Analyzing the system requirements allocated to the software, developing the software requirements, developing the software architecture, designing the software, implementing the software in the code, integrating the software components, and testing the software to verify that the software satisfies the specified requirements allocated to the software component of a system or subsystem.
1.7.2 | Integrated Logistics Support (ILS) Systems Engineering | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.2.2 Integrated Logistics Support (ILS) Systems Engineering. The efforts to ensure the integrated planning and action of a number of disciplines in concert with one another to assure system availability. The planning of each element of ILS (e.g., integrated product support (IPS) elements) is developed in coordination with systems engineering and other efforts. Includes, for example: a. Product support management b. Design interface c. Sustaining engineering d. Supply support e. Maintenance planning and management f. Packaging, handling, storage, and transportation g. Technical data h. Support equipment i. Training and training support j. Manpower and personnel k. Facilities and infrastructure l. Computer resources
1.7.3 | Cybersecurity Systems Engineering | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.2.3 Cybersecurity Systems Engineering. The efforts to apply scientific and engineering principles to identify security vulnerabilities and minimize or contain risks associated with these vulnerabilities. Includes, for example: a. Cybersecurity requirements evaluation b. Cyberattack surface characterization c. Cooperative vulnerability identification d. Vulnerability analysis e. System cross-functional cyber analysis f. Advise on RMF compliance tasks/documents (security assessment plan, etc.) g. Security configuration management (assess planned services for risk and impact) h. Develop system-level security architecture i. Design, develop, and implement system security measures that meets technical requirements j. Develop and implement specific security countermeasures for the system k. Develop approaches to mitigate system vulnerabilities l. Ensure the design of hardware, operating systems, and software applications adequately address cybersecurity requirements for the system
1.7.4 | Core Systems Engineering | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.2.4 Core Systems Engineering. The technical and management efforts that establish the technical framework for delivering materiel capabilities and ensure the effective development and delivery of capability through the implementation of a balanced approach with respect to cost, schedule, performance, and risk. This effort uses integrated, disciplined and consistent systems engineering activities and processes for development of resilient systems that are trusted, assured and easily modified. Systems engineering is composed of 16 processes: eight technical processes and eight technical management processes. These processes provide a structured approach to increasing the technical maturity of a system and increasing the likelihood that the capability being developed balances mission performance with cost, schedule, risk, and design constraints. To fulfill that purpose, a program implements the systems engineering technical processes to support the iterative maturation of the system solution or operational need. The technical processes enable the systems engineering team to ensure that the delivered capability accurately reflects the operational needs of the stakeholders. The technical processes include top down design processes such as stakeholder requirements definition, requirements analysis, and architecture design, as well as bottom-up realization processes such as transition, validation, verification, integration, and implementation. The eight technical management processes are implemented across the acquisition life cycle and provide insight and control to assist the program manager and systems engineer to meet performance, schedule, and cost goals. The eight technical processes closely align with the acquisition life cycle phases and include the top-down design processes and bottom-up realization processes that support transformation of operational needs into operational capabilities. The eight technical management processes are: decision analysis, technical planning, technical assessment, requirements management, risk management, configuration management, technical data management, and interface management. Also included are specialty engineering disciplines which bring together the hardware, software, and human elements of the systems. Includes, for example: a. System safety which is applicable to most DoD systems; this reflects the ubiquitous nature of software-driven functions, network connectivity, and systems of systems; specific certifications include safety, security, cybersecurity and airworthiness b. Reliability and maintainability – ensure that design interface and integration of the quantitative systems engineering design characteristics (i.e., reliability, maintainability, etc.) with the functional integrated product support elements c. Quality – ensures configuration item level requirements for the systems and subsystems meet critical functions and key quality attributes. d. Manufacturing and producibility – ensure manufacturing and producibility readiness, processes assessed and demonstrated, and risks identified, managed and reduced throughout the program’s life cycle e. Human systems integration – optimize total system performance and total ownership costs, while ensuring that the system is designed, operated, and maintained to effectively provide the user with the ability to complete their mission; ensure ergonomics, human factors engineering, and cognitive engineering is employed to provide for effective human-machine interfaces; define the human performance characteristics of the user based on the system description, projected characteristics of target occupational specialties, and recruitment and retention trends; establish requirements for the physical environment; determine the most efficient and cost-effective mix of DoD manpower and contract support; develop training options for operators, maintenance and support personnel; ensure that appropriate environmental safety and occupational health; assess risks to personnel and address, in terms of system design, protection from direct threat events and accidents (such as chemical, biological, and nuclear threats). f. System of systems (SoS) and system level architecting, modeling and simulation, verification and validation and external interface definition and management g. For sea systems; the Expanded Ship Work Breakdown Structure (ESWBS), configuration management (811), human factors (892), standardization (893), value engineering (894), and reliability and maintainability (895) elements Excludes, for example: a. Actual design engineering and the production engineering directly related to the WBS element with which it is associated b. Any systems engineering efforts that are called out in software systems engineering, ILS systems engineering, cybersecurity systems engineering, or “other” systems engineering effort separately identified in the WBS.
1.7.5 | Other Systems Engineering 1...n (Specify) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.2.5 Other Systems Engineering 1...n (Specify). This element should be replaced with other systems engineering elements that cannot be categorized into one of the above elements or need to be separately identified due to high cost, high risk concerns within systems engineering. Each additional element is to be clearly identified and defined.
1.8 | Program Management | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.3 Program Management. The business and administrative planning, organizing, directing, coordinating, controlling, and approval actions designated to accomplish overall program objectives, which are not associated with specific hardware elements and are not included in systems engineering. If required, one or more areas of effort (e.g., software program management, cybersecurity program management, etc.,) may be identified at the next level below program management. In those cases, the remaining totality of program management efforts will be defined as “core program management” at the level equal to the segregated items.
1.8.1 | Software Program Management | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.3.1 Software Program Management. The software program management encompasses the management of the full software life cycle, from conception to deployment. The function focuses at the system level of applying business and project management skills needed to produce high-quality software products. Includes, for example: a. Overseeing requirements analysis and design, and effective implementation and delivery of all fully-tested software b. Ensure sufficient end-user involvement c. Maintain communication among customers, developers, users, and project managers d. Establish realistic or articulated project goals e. Develop accurate estimates of needed resources f. Define system requirements and specifications g. Assure reporting of the project’s status h. Proper management of risks i. Ensure the use of mature technology and handle the project’s complexity
1.8.2 | Integrated Logistics Support (ILS) Program Management | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.3.2 Integrated Logistics Support Program Management. The efforts to manage the planning and execution of the ILS disciplines to assure system acquisition logistics availability. Includes, for example: a. Support element management, defined as the logistics tasks management effort and technical control, and the business management of the support elements. The logistics management function encompasses the support evaluation and supportability assurance required to produce an affordable and supportable defense materiel system. b. Planning and management of all the functions of logistics. Examples are: maintenance support planning and support facilities planning; other support requirements determination; support equipment requirements determination; supply support; packaging, handling, storage, and transportation; provisioning requirements determination and planning; training system requirements determination; computer resource determination; organizational, intermediate, and depot maintenance determination management; and data management
1.8.3 | Cybersecurity Management | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.3.3 Cybersecurity Program Management. The management and understanding of cybersecurity program and its ramifications across the organization (only if costs are collected in this manner). Includes, for example: a. Overseeing cybersecurity risk assessment, management, and mediation b. Cybersecurity threat vectors and mitigation processes c. Ensuring design and management of secure information systems d. Emerging tools and resources for organizational and platform security
1.8.4 | Core Program Management | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.3.4 Core Program Management. The efforts to understand and manage multiple discipline areas in order the successfully accomplish program objectives for development, production, and sustainment of systems to meet the user’s operational needs Includes, for example: a. Cost, schedule, performance measurement management, warranty administration, contract management, vendor liaison, subcontract management, etc. b. For sea systems; the Expanded Ship Work Breakdown Structure (ESWBS), project management (897); data management (896); and supply support (853) elements Excludes, for example: a. Actual program management directly related to another WBS element b. Any program management efforts that are called out in software program management, cybersecurity program management, or “other” program management effort separately identified in the WBS.
1.8.5 | Other Program Management 1...n (Specify) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.3.5 Other Program Management 1...n (Specify). This element should be replaced with other program management elements that cannot be categorized into one of the above elements or need to be separately identified due to high cost or high risk concerns within program management. Each additional element is to be clearly identified and defined.
1.8 | System Test and Evaluation | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.4 System Test and Evaluation. The use of pilot, prototype, production, or specifically fabricated hardware/software to obtain or validate engineering data on the performance of the system during the developmental phase of the program. It also includes all effort associated with the development of any specialized tools or data in support of the system level test program. Includes, for example: a. Detailed planning, conduct, support, data reduction and reports (excluding the contract data requirements list data) from such testing, and test articles that are functionally configured to represent and test subsystems/components of the defense materiel end item being developed or produced b. Design and production of models, specimens, fixtures and instrumentation c. System level labs that integrate both hardware and software NOTE: Test articles that are functionally configured to represent and test the complete defense materiel end item being developed or produced, are excluded from this WBS element. Excludes, for example: a. All formal and informal testing up through the subsystem level, which can be associated with the hardware/software element acceptance testing NOTE: These excluded efforts are to be included with the appropriate hardware or software elements.
1.9.1 | Development Test and Evaluation | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.4.1 Development Test and Evaluation. The test and evaluation conducted by the developing agency of the DoD component. It includes test and evaluation conducted to: a. Demonstrate that the engineering design and development process is complete b. Demonstrate that the design risks have been minimized c. Demonstrate that the system will meet specifications d. Assess the system’s military utility when introduced e. Determine whether the engineering design is supportable (practical, maintainable, safe, etc.) for operational use f. Provide test data with which to examine and evaluate trade-offs against specification requirements, life cycle cost, and schedule g. Perform the logistics testing efforts to evaluate the achievement of supportability goals, the adequacy of the support package for the system, (e.g., deliverable maintenance tools, test equipment, technical publications, maintenance instructions, and personnel skills and training requirements, etc.) Includes, for example: a. All contractor/system developer in-house effort b. Where applicable, models, tests and associated simulations (e.g., such as wind tunnel, static, drop, and fatigue); integration ground tests; test bed aircraft and associated support; qualification test and evaluation, development flight test, test instrumentation, environmental tests, ballistics, radiological, range and accuracy demonstrations, test facility operations, test equipment (including its support equipment), chase and calibrated pacer aircraft and support thereto, and logistics testing c. For aircraft; avionics integration test composed of the following: i. Test bench/laboratory, including design, acquisition, and installation of basic computers and test equipment that will provide an ability to simulate in the laboratory the operational environment of the avionics system/subsystem ii. Air vehicle equipment, consisting of the avionics and/or other air vehicle subsystem modules that are required by the bench/lab or flying test bed in order to provide a compatible airframe avionics system/subsystem for evaluation purposes iii. Flying test bed, including requirements analysis, design of modifications, lease or purchase of test bed aircraft, modification of aircraft, installation of avionics equipment and instrumentation, and checkout of an existing aircraft used essentially as a flying avionics laboratory iv. Avionics test program, consisting of the effort required to develop test plans/procedures, conduct tests, and analyze hardware and software test results to verify the avionics equipment’s operational capability and compatibility as an integrated air vehicle subsystem v. Software, referring to the effort required to design, code, de-bug, and document software programs necessary to direct the avionics integration test d. For engines: engine military qualification tests and engine preliminary flight rating tests e. For sea systems: model basin, hydrostatic, fatigue, shock, special sea tests and trials, etc., including the Expanded Ship Work Breakdown Structure (ESWBS), trials agenda preparation, data collection and analysis (842); dock and sea trials (9823); and hull vibration survey (9825) elements f. For missiles: test articles such as inert measurement vehicles, launch separation vehicles, separation and control test vehicles, boost test vehicles g. For ordnance: test articles such as ballistic test rounds, inert measurement rounds, dummy rounds, launch separation rounds, etc.
1.9.2 | Operational Test and Evaluation | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.4.2 Operational Test and Evaluation. The test and evaluation conducted by agencies other than the developing command to assess the prospective system’s military utility, operational effectiveness, operational suitability, logistics supportability (including compatibility, inter-operability, reliability, maintainability, logistic requirements, etc.), cost of ownership, and need for any modifications. Includes, for example: a. Initial operational test and evaluation conducted during the development of a system b. Such tests as system demonstration, flight tests, sea trials, mobility demonstrations, on-orbit tests, spin demonstration, stability tests, qualification operational test and evaluation, etc., and support thereto, required to prove the operational capability of the deliverable system. c. Contractor support (e.g., technical assistance, maintenance, labor, material, etc.) consumed during this phase of testing d. Logistics testing efforts to evaluate the achievement of supportability goals and the adequacy of the support for the system (e.g., deliverable maintenance tools, test equipment, technical publications, maintenance instructions, personnel skills and training requirements, and software support facility/environment elements)
1.9.3 | Cybersecurity Test and Evaluation | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.4.3 Cybersecurity System Test and Evaluation. The developmental test and evaluation and operational test and evaluation conducted and monitored by the developing agency of the DoD. The technical efforts of ensuring the confidentiality, integrity, and availability of information and technology by monitoring and defending against cyber (network) attacks. Includes, for example: a. Vulnerability scanning and interpretation b. Vulnerability testing and penetration testing (usually linked to patch management) c. Security information and event management d. Destructive and non-destructive exploitation e. Test conducted in an operational environment with certified red teams f. Cybersecurity compliance tracking and reporting g. Malware scanning, detection, and prevention services h. Security, IT certification, and accreditation compliance services
1.9.4 | Mock-ups/System Integration Labs (SILs) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.4.4 Mock-ups/System Integration Labs (SILs). The design engineering and production of system or subsystem mock-ups that have special contractual or engineering significance or that are not required solely for the conduct of one of the above elements of testing. SILs are often used in lieu of (or in addition to) mock-ups. SILs are risk reduction facilities where software and hardware can be developed, integrated, tested, and evaluated for both standalone functionality and/or interoperability prior to being fielded. Includes, for example: a. Hardware/lab equipment b. SIL Software (written to simulate the operating environment or written to operate the SIL)
1.9.5 | Test and Evaluation Support | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.4.5 Test and Evaluation Support. The support elements necessary to operate and maintain, during test and evaluation, systems and subsystems, which are not consumed during the testing phase and are not allocated to a specific phase of testing. Includes, for example: a. Repairable spares, repair of reparables, repair parts, consumables, warehousing and distribution of spares and repair parts, test and support equipment, test bed vehicles, drones, surveillance aircraft/chase aircraft, tracking vessels, contractor technical support Excludes, for example: a. Operational and maintenance personnel, special fixtures, special instrumentation, etc., that are utilized and/or consumed in a single element of testing and that should be included under that element of testing
1.9.6 | Test Facilities | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.4.6 Test Facilities. The special test facilities required for performance of the various developmental tests necessary to prove the design and reliability of the system or subsystem. Includes, for example: a. Test tank test fixtures, propulsion test fixtures, white rooms, test chambers, range/targeting facilities Excludes, for example: a. Brick and mortar-type facilities identified as industrial facilities
1.1 | Training | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.5 Training. Deliverable training services, devices, accessories, aids, equipment, and parts used to facilitate instruction through which personnel will learn to operate and maintain the system with maximum efficiency. Includes, for example: a. All effort associated with the design, development, and production of deliverable training equipment and its associated software as well as the execution of training services Excludes, for example: a. Overall planning, management, and task analysis functions inherent in the WBS element systems engineering/program management
1.10.1 | Equipment | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.5.1 Equipment. Distinctive deliverable end items of training equipment, assigned by either a contractor or military service, required to meet specific training objectives. Includes, for example: a. Operational and Maintenance Trainers and training equipment including items such as cutaways, mock-ups, and models (e.g. Operator Instructional Equipment, Maintainer Instructional Equipment)
1.10.1.1 | Operator Instructional Equipment | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | [Blank]
1.10.1.2 | Maintainer Instructional Equipment | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | [Blank]
1.10.2 | Services | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.5.2 Services. Deliverable training services, accessories, and courseware aids necessary to accomplish the objectives of training. Includes, for example: a. Operational and Maintenance Training Services including courses, course materials; and curriculum required to design, execute, and produce a contractor developed training program and related software programs (e.g. operator instructional services, maintainer instructional services) Excludes, for example: a. Deliverable training data associated with support data (see Data Deliverables 1...n (Specify), Support Data)
1.10.2.1 | Operator Instructional Services | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | [Blank]
1.10.2.2 | Maintainer Instructional Services | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | [Blank]
1.10.3 | Facilities | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.5.3 Facilities. The special construction necessary to accomplish training objectives. Includes, for example: a. Modification or rehabilitation of existing training facilities and infrastructure used to accomplish training objectives Excludes, for example: a. Installed equipment used to acquaint the trainee with the system or establish trainee proficiency b. The brick and mortar-type facilities identified as industrial facilities
1.10.4 | Training Software 1...n (Specify) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.5.4 Training Software Release 1...n (Specify). Updated/upgraded software for training purposes delivered to the field during the acquisition phase.
1.11 | Data | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.6 Data. The deliverable data required to be listed on a contract data requirements list. Includes, for example: a. Only such effort that can be reduced or avoided if the data item is eliminated b. Government-peculiar data; acquiring, assembling, reproducing, packaging and shipping the data c. Transforming data into Government
1.11.1 | Data Deliverables 1...n (Specify) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.6.1 Data Deliverables 1...n (Specify). Deliverable data which provides technical, engineering, management, support, or other data required for contract delivery. Includes, for example: a. Technical Publications. Technical data, providing instructions for installation, operation, maintenance, training, and support, formatted into a technical manual. Data may be presented in any form regardless of the form or method of recording. Technical orders that meet the criteria of this definition may also be classified as technical manuals. For sea systems: Expanded Ship Work Breakdown Structure (ESWBS), technical manuals and other data (856) element. b. Engineering Data. Recorded scientific or technical information (regardless of the form or method of recording) including computer software documentation. Engineering data defines and documents an engineering design or product configuration (sufficient to allow duplication of the original items) and is used to support production, engineering, and logistics activities. For sea systems; Expanded Ship Work Breakdown Structure (ESWBS), design support, ship’s selected records (8302); design support, services, reproduction (8303); and engineering drawings and specifications (855) elements. c. Management Data. The data items necessary for configuration management, cost, schedule, contractual data management, program management, etc., required by the Government. For sea systems; Expanded Ship Work Breakdown Structure (ESWBS), contract data requirements (988) element. d. Support Data. The data items designed to document support planning in accordance with functional categories
1.11.2 | Data Repository | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.6.2 Data Repository. The activity and enterprise data storage entity (or sometimes entities) for Government approved documents that are the property of the Government into which data has been specifically partitioned for analytical or reporting purposes. As custodian for the Government, the repository, authorized by approved change orders, maintains master documents at the latest approved revision level. Includes, for example: a. All effort necessary to maintain documents
1.11.3 | Data Rights 1...n (Specify) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.6.3 Data Rights 1...n (Specify). Government’s license rights of valuable intellectual property including technical data of any recorded information of a scientific or technical nature (e.g., product design or maintenance data, computer databases, and computer software documentation); and computer software including executable code, source code, code listings, design details, processes, flow charts, and related material. Includes, for example: a. Unlimited Rights. Developed exclusively at Government expense, and certain types of data (e.g., Form, Fit, and Function data (FFF); Operation, Maintenance, Installation, and Training (OMIT)). These rights involve the right to use, modify, reproduce, display, release, or disclose technical data in whole or in part, in any manner, and for any purpose whatsoever, and to have or authorize others to do so. b. Government Purpose Rights. This right involves the right to use, duplicate, or disclose technical data for Government purposes only, and to have or permit others to do so for Government purposes only. Government purposes include competitive procurement, but do not include the right to permit others to use the data for commercial purposes. c. Limited Rights. A limited rights agreement permits the Government to use proprietary technical data in whole or in part. It also means that the Government has to obtain the expressed permission of the party providing the technical data to release it, or disclose it, outside the Government.
1.12 | Peculiar Support Equipment | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.7 Peculiar Support Equipment. The design, development, and production of those deliverable items and associated software required to support and maintain the system or portions of the system while the system is not directly engaged in the performance of its mission, and which are not common support equipment. Items should be designated by commodity subassembly (airframe, engine, avionics, etc.). Includes, for example: a. Vehicles, equipment, tools, etc., used to fuel, service, transport, hoist, repair, overhaul, assemble, disassemble, test, inspect, or otherwise maintain mission equipment b. Any production of duplicate or modified factory test or tooling equipment delivered to the Government for use in maintaining the system. (Factory test and tooling equipment initially used by the contractor in the production process but subsequently delivered to the Government will be included as cost of the item produced.) c. Any additional equipment or software required to maintain or modify the software portions of the system Excludes, for example: a. Overall planning, management, and task analysis functions inherent in the work breakdown structure elements Systems Engineering and Program Management b. Common support equipment, presently in the DoD inventory or commercially available, bought by the using command, not by the acquiring command
1.12.1 | Test and Measurement Equipment | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.7.1 Test and Measurement Equipment. The peculiar or unique testing and measurement equipment that allows an operator or maintenance function to evaluate operational conditions of a system or equipment by performing specific diagnostics, screening, or quality assurance effort at an organizational, intermediate, or depot level of equipment support. Includes, for example: a. Test measurement and diagnostic equipment, precision measuring equipment, automatic test equipment, manual test equipment, automatic test systems, test program sets, appropriate interconnect devices, automated load modules, tapes, and related software, firmware and support hardware (power supply equipment, etc.) used at all levels of maintenance b. Packages that enable line or shop replaceable units, printed circuit boards, or similar items to be diagnosed using automatic test equipment
1.12.1.1 | Test and Measurement Equipment (Airframe/Hull/Vehicle) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.7.1.1 Test and Measurement Equipment (Airframe/Hull/Vehicle). This element captures the cost of the airframe, ship hull, or ground vehicle hull/frame related test and measurement equipment. Identify the related WBS subassemblies associated with the airframe/hull/vehicle. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested
1.12.1.2 | Test and Measurement Equipment (Propulsion) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.7.1.2 Test and Measurement Equipment (Propulsion). This element captures the cost of the propulsion system, engines, prime movers, turbines, etc. related test and measurement equipment. Identify the related WBS subassemblies associated with propulsion. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.12.1.3 | Test and Measurement Equipment (Electronics/Avionics) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.7.1.3 Test and Measurement Equipment (Electronics/Avionics). This element captures the cost of the electronics/avionics related test and measurement equipment. Identify the related WBS subassemblies associated with electronics/avionics. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.12.1.4 | Test and Measurement Equipment (Other Major Subsystems 1...n (Specify)) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.7.1.4 Test and Measurement Equipment (Other Major Subsystem 1...n (Specify)). This element captures the cost of other major subsystems (e.g., armament, weapons, vehicle subsystems, etc.) not captured above related test and measurement equipment. Identify the related WBS subassemblies associated with the other major subsystems. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.12.2 | Support and Handling Equipment | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.7.2 Support and Handling Equipment. The peculiar or unique tools and handling equipment used for support of the mission system at an organizational, intermediate, or depot level Includes, for example: a. Ground support equipment, vehicular support equipment, powered support equipment, non-powered support equipment, munitions material handling equipment, materiel handling equipment, and software support equipment (hardware and software)
1.12.2.1 | Support and Handling Equipment (Airframe/Hull/Vehicle) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.7.2.1 Support and Handling Equipment (Airframe/Hull/Vehicle). This element captures the cost of the airframe, ship hull, or ground vehicle hull/frame related support and handling equipment. Identify the related WBS subassemblies associated with airframe/hull/vehicle. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.12.2.2 | Support and Handling Equipment (Propulsion) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.7.2.2 Support and Handling Equipment (Propulsion). This element captures the cost of propulsion related support and handling equipment. Identify the related WBS subassemblies associated with propulsion. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.12.2.3 | Support and Handling Equipment (Electronics/Avionics) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.7.2.3 Support and Handling Equipment (Electronics/Avionics). This element captures the cost of the electronics/avionics related support and handling equipment. Identify the related WBS subassemblies associated with electronics/avionics. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.12.2.4 | Support and Handling Equipment (Other Major Subsystems 1...n (Specify)) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.7.2.4 Support and Handling Equipment (Other Major Subsystem 1...n (Specify)). This element captures the cost of other major subsystems (e.g., armament, weapons, vehicle subsystems, etc.) not captured above related support and handling equipment. Identify the related WBS subassemblies associated with the other major subsystems. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.13 | Common Support Equipment | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.8 Common Support Equipment. The items required to support and maintain the system or portions of the system while not directly engaged in the performance of its mission, and which are presently in the DoD inventory for support of other systems. Includes, for example: a. Acquisition of additional quantities of this equipment needed to support the item b. All efforts required to assure the availability of this equipment to support the item
1.13.1 | Test and Measurement Equipment | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.8.1 Test and Measurement Equipment. The common testing and measurement equipment that allows an operator or maintenance function to evaluate operational conditions of a system or equipment by performing specific diagnostics, screening, or quality assurance effort at an organizational, intermediate, or depot level of equipment support. Includes, for example: a. Test measurement and diagnostic equipment, precision measuring equipment, automatic test equipment, manual test equipment, automatic test systems, test program sets, appropriate interconnect devices, automated load modules, tapes, and related software, firmware, and support hardware (power supply equipment, etc.) Used at all levels of maintenance b. Packages that enable line or shop replaceable units, printed circuit boards, or similar items to be diagnosed using automatic test equipment
1.13.1.1 | Test and Measurement Equipment (Airframe/Hull/Vehicle) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.8.1.1 Test and Measurement Equipment (Airframe/Hull/Vehicle). This element captures the cost of the airframe, ship hull, or ground vehicle hull/frame related test and measurement equipment. Identify the related WBS subassemblies associated with the airframe/hull/vehicle. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.13.1.2 | Test and Measurement Equipment (Propulsion) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.8.1.2 Test and Measurement Equipment (Propulsion). This element captures the cost of the propulsion system, engines, prime movers, turbines, etc. related test and measurement equipment. Identify the related WBS subassemblies associated with propulsion. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.13.1.3 | Test and Measurement Equipment (Electronics/Avionics) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.8.1.3 Test and Measurement Equipment (Electronics/Avionics). This element captures the cost of the electronics/avionics related test and measurement equipment. Identify the related WBS subassemblies associated with electronics/avionics. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.13.1.4 | Test and Measurement Equipment (Other Major Subsystems 1...n (Specify)) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.8.1.4 Test and Measurement Equipment (Other Major Subsystem 1...n (Specify)). This element captures the cost of other major subsystems (e.g., armament, weapons, vehicle subsystems, etc.) not captured above related test and measurement equipment. Identify the related WBS subassemblies associated with the other major subsystems. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.13.2 | Support and Handling Equipment | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.8.2 Support and Handling Equipment. The common tools and handling equipment used for support of the mission system at an organizational, intermediate, or depot level Includes, for example: a. Ground support equipment, vehicular support equipment, powered support equipment, non-powered support equipment, munitions material handling equipment, materiel handling equipment, and software support equipment (hardware/software)
1.13.2.1 | Support and Handling Equipment (Airframe/Hull/Vehicle) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.8.2.1 Support and Handling Equipment (Airframe/Hull/Vehicle). This element captures the cost of the airframe, ship hull, or ground vehicle hull/frame related support and handling equipment. Identify the related WBS subassemblies associated with airframe/hull/vehicle. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.13.2.2 | Support and Handling Equipment (Propulsion) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.8.2.2 Support and Handling Equipment (Propulsion). This element captures the cost of propulsion related support and handling equipment. Identify the related WBS subassemblies associated with propulsion. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.13.2.3 | Support and Handling Equipment (Electronics/Avionics) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.8.2.3 Support and Handling Equipment (Electronics/Avionics). This element captures the cost of the electronics/avionics related support and handling equipment. Identify the related WBS subassemblies associated with electronics/avionics. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.13.2.4 | Support and Handling Equipment (Other Major Subsystems 1...n (Specify)) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.8.2.4 Support and Handling Equipment (Other Major Subsystem 1...n (Specify)). This element captures the cost of other major subsystems (e.g., armament, weapons, vehicle subsystems, etc.) not captured above related support and handling equipment. Identify the related WBS subassemblies associated with the other major subsystems. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.14 | Operational/Site Activation by Site 1...n (Specify) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.9 Operational/Site Activation by Site 1...n (Specify). The real estate, construction, conversion, utilities, and equipment to provide all facilities required to house, service, and launch prime mission equipment at the organizational and intermediate level. Includes, for example: a. Conversion of site, ship, or vehicle b. System assembly, checkout, and installation (of mission and support equipment) into site facility or ship to achieve operational status c. Contractor support in relation to operational/site activation
1.14.1 | System Assembly, Installation, and Checkout | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.9.1 System Assembly, Installation, and Checkout. The materials and services involved in the assembly of mission equipment at the site. Includes, for example: a. Installation of mission and support equipment in the operations or support facilities and complete system checkout or shakedown to ensure operational status. Where appropriate, specify by site, ship, or vehicle. b. The efforts and activities associated with shipping the system from contractor facility to customer site. That site could be a DT&E site, an installation and checkout site, or any similar site that is outside the direct control of the contractor. Excludes, for example: a. Field team installation
1.14.2 | Contractor Technical Support | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.9.2 Contractor Technical Support. The materials and services provided by the contractor related to activation. Includes, for example: a. Repair of reparables, standby services, and final turnover
1.14.3 | Site Construction | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.9.3 Site Construction. Real estate, site planning and preparation, construction, and other special-purpose facilities necessary to achieve system operational status. Includes, for example: a. Construction of utilities, roads, and interconnecting cabling
1.14.4 | Site/Ship/Vehicle Conversion | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.9.4 Site/Ship/Vehicle Conversion. The materials and services required to convert existing sites, ships, or vehicles to accommodate the mission equipment and selected support equipment directly related to the specific system. Includes, for example: a. Operations, support, and other special purpose facilities conversion necessary to achieve system operational status, e.g., launch. Where appropriate, specify by site, ship, or vehicle
1.14.5 | Interim Contractor Support (ICS) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.9.5 Interim Contractor Support (ICS). The effort required to provide temporary contractor support in lieu of a permanent support solution (organic or commercial) for a predetermined time, while a permanent support capability is put in place. Interim support is usually required for support of prototypes and early test and production assets during development and initial fielding (i.e., Initial Operating Capability (IOC)). Includes, for example: a. Providing life cycle logistics in accordance with the integrated product support (IPS) elements in support of the prime mission product. Excludes, for example: a. The development and production of the original prime mission product.
1.15 | Contractor Logistics Support (CLS) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.10 Contractor Logistics Support (CLS). Contracted weapon system sustainment including performance of maintenance and/or materiel management functions for a DoD weapon system by a commercial activity or contractor sustainment of a weapon system that is intended to start after a permanent decision is made to cover the operations and support efforts of the weapon system. CLS generally starts before FOC (final operating capability) or when performance based logistics (PBL) is implemented in the operating and support (O&S) phase. Includes, for example: a. Prime Mission Product (PMP) maintenance and refurbishment. The cost for this element includes maintenance and refurbishment (including the development and production) of existing operational systems. b. Support functions required to maintain the system, such as sustaining engineering, program management, logistics support, and supply chain management c. Test and evaluation for system and subsystem modifications d. Repair of reparable items; replacement of condemned items (including all PMP, support equipment, and training equipment) e. Operational, maintenance and other personnel required at the operational unit level f. Unit operations costs, including operating material and support services at the operating unit g. Installation and personnel support functions in support of the unit level manpower Excludes, for example: a. Does not include interim contractor support (ICS), a temporary measure for a system’s initial period of operation before a permanent form of support is in place. b. Contractor sustainment support for a specific sustainment task that a service would otherwise conduct itself.
1.16 | Industrial Facilities | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.11 Industrial Facilities. The construction, conversion, or expansion of industrial facilities for production, inventory, and contractor depot maintenance required when that service is for the specific system. Includes, for example: a. Equipment acquisition or modernization, where applicable b. Maintenance of these facilities or equipment c. Industrial facilities for hazardous waste management to satisfy environmental standards Excludes, for example: a. Capital equipment
1.16.1 | Construction/Conversion/Expansion | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.11.1 Construction/Conversion/Expansion. The real estate and preparation of system peculiar industrial facilities for production, inventory, depot maintenance, and other related activities.
1.16.2 | Equipment Acquisition or Modernization | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.11.2 Equipment Acquisition or Modernization. The production equipment acquisition, modernization, or transfer of equipment for the particular system. This pertains to Government owned and leased equipment under facilities contract.
1.16.3 | Maintenance (Industrial Facilities) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.11.3 Maintenance (Industrial Facilities). The maintenance, preservation, and repair of industrial facilities and equipment.
1.17 | Initial Spares and Repair Parts | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.12 Initial Spares and Repair Parts. The deliverable spare components, assemblies, and subassemblies used for initial replacement purposes in the materiel system equipment end item. Includes, for example: a. Repairable spares (reparables) and repair parts required as initial stockage to support and maintain newly fielded systems or subsystems during the initial phase of service, including pipeline and war reserve quantities, at all levels of maintenance and support. Lower level WBS breakouts should be by subsystem. b. Spare training and support equipment items c. The combination of resources, processes, planning, procedures, design, considerations, methods, and all hardware to ensure that all system, equipment, and support items are preserved, packaged, handled, and transported properly, including environmental considerations, equipment preservation for short and long term storage, and transportability. This includes requirements such as special environmentally controlled, shock isolated containers for transport to and from repair facilities and ensuring proper Care of Supplies in Storage (COSIS) program requirements are followed. Excludes, for example: a. Development test spares and spares provided specifically for use during installation, assembly, and checkout on site

## D
WBS # | WBS Nomenclature | Appendix | WBS Definition
1 | Strategic Missile Systems | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.1 | Strategic Missile Systems Integration, Assembly, Test, and Checkout | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2 | Air Vehicle Equipment (AVE)/Flight Vehicle Equipment (FVE) | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.1 | AVE/FVE SEIT/PM and Support Equipment | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.2 | Aero-Structures (Non-Stage Related) | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.3 | Stage (1...3) Interstage | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.3.1 | Stage 1 Interstage | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.3.1.1 | Stage 1 Interstage SEIT/PM and Support Equipment | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.3.1.2 | Structures and Mechanisms | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.3.1.3 | Separation Ordnance | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.3.1.4 | Attitude Control System (ACS) | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.3.1.5 | Interstage Peculiar Avionics | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.3.1.6 | Cable and Harness Assembly | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.3.1.7 | Flight Termination/Mission Termination | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.3.1.8 | Instrumentation/Telemetry | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.3.2 | Stage 2 Interstage | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.3.3 | Stage 3 Interstage | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.4 | Other AVE/FVE Structures 1...n (Specify) | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.5 | Stage (1...3) | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.5.1 | Stage 1 | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.5.1.1 | Stage SEIT/PM and Support Equipment | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.5.1.2 | Structures and Mechanisms | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.5.1.3 | Propulsion System | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.5.1.4 | Attitude Control System | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.5.1.5 | Stage Peculiar Avionics | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.5.1.6 | Cable Assembly | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.5.1.7 | Flight Termination/Mission Termination | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.5.1.8 | Instrumentation/Telemetry | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.5.2 | Stage 2 | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.5.3 | Stage 3 | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.6 | Power and Distribution | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.6.1 | Power and Distribution SEIT/PM and Support Equipment | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.6.2 | Primary Power | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.6.3 | Power Conditioning Electronics | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.6.4 | Distribution Harness | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.6.5 | Power and Distribution Software Release 1...n (Specify) | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.7 | Guidance and Control | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.7.1 | Guidance and Control SEIT/PM and Support Equipment | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.7.2 | Guidance Computer | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.7.3 | Guidance and Control Electronics | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.7.4 | Navigation/Inertial Measurement Unit (IMU) | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.7.5 | Guidance and Control Cooling System | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.7.6 | Computer Memory Battery | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.7.7 | Guidance and Control Cables | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.7.8 | Guidance and Control Software Release 1...n (Specify) | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.8 | Communications | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.8.1 | Communications SEIT/PM and Support Equipment | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.8.2 | Antenna Assembly 1...n (Specify) | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.8.3 | Transceiver Assembly 1...n (Specify) | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.8.4 | Communications Software Release 1...n (Specify) | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.9 | Post Boost/Attitude Control Module (PBACM) | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.9.1 | PBACM SEIT/PM and Support Equipment | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.9.2 | Structures and Mechanisms | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.9.3 | Propulsion System | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.9.4 | Countermeasures | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.9.5 | PBACM Peculiar Avionics | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.9.6 | Cable Assembly | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.9.7 | Flight Termination/Mission Termination | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.9.8 | Instrumentation/Telemetry | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.10 | Payload/Reentry Systems | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.10.1 | Payload/Reentry Systems SEIT/PM and Support Equipment | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.10.2 | Payload/Reentry Vehicle 1...n (Specify) | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.10.3 | Countermeasures | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.10.4 | Deployment Housing/Bulkheads | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.11 | Ordnance Initiation Set | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.2.12 | On Board Test Equipment | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.3 | Encasement Device | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.3.1 | Encasement Device SEIT/PM and Support Equipment | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.3.2 | Encasement Device Structure | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.3.3 | Encasement Device Software Release 1...n (Specify) | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.3.4 | Other Encasement Device Subsystems 1...n (Specify) | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.4 | Command and Launch | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.4.1 | Command and Launch SEIT/PM and Support Equipment | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.4.2 | Launch and Guidance Control/Fire Control | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.4.3 | Communications | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.4.4 | Launch and Encasement Equipment | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.4.5 | Auxiliary Equipment | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.4.6 | Command and Launch (Ground) Software Release 1...n (Specify) | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.4.7 | Infrastructure | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.4.8 | Other Command and Launch 1...n (Specify) | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.5 | Systems Engineering | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.2 Systems Engineering. The technical and management efforts of directing and controlling a totally integrated engineering effort of a system or program. The following represent many, but not all, of the systems engineering efforts needed for a system or program. If required, one or more areas of effort (e.g., software systems engineering, cybersecurity, etc., may be identified at the next level below systems engineering. In those cases, the remaining totality of systems engineering efforts will be defined as “core systems engineering” at the level equal to the segregated items.
1.5.1 | Software Systems Engineering | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.2.1 Software Systems Engineering. The efforts which encompass software systems technologies, software engineering methods, and management techniques that improve the quality and delivery of software intensive systems and applications. Includes, for example: a. The application of a systematic, disciplined, quantifiable approach to the development and operations and support (O&S) of software b. The determination of software development or software test facility/environment requirements c. Application of systems engineering to software, that is, the systematic application of scientific and technical knowledge, methods, and experience to the design, implementation, testing, and documentation of software d. Analyzing the system requirements allocated to the software, developing the software requirements, developing the software architecture, designing the software, implementing the software in the code, integrating the software components, and testing the software to verify that the software satisfies the specified requirements allocated to the software component of a system or subsystem.
1.5.2 | Integrated Logistics Support (ILS) Systems Engineering | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.2.2 Integrated Logistics Support (ILS) Systems Engineering. The efforts to ensure the integrated planning and action of a number of disciplines in concert with one another to assure system availability. The planning of each element of ILS (e.g., integrated product support (IPS) elements) is developed in coordination with systems engineering and other efforts. Includes, for example: a. Product support management b. Design interface c. Sustaining engineering d. Supply support e. Maintenance planning and management f. Packaging, handling, storage, and transportation g. Technical data h. Support equipment i. Training and training support j. Manpower and personnel k. Facilities and infrastructure l. Computer resources
1.5.3 | Cybersecurity Systems Engineering | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.2.3 Cybersecurity Systems Engineering. The efforts to apply scientific and engineering principles to identify security vulnerabilities and minimize or contain risks associated with these vulnerabilities. Includes, for example: a. Cybersecurity requirements evaluation b. Cyberattack surface characterization c. Cooperative vulnerability identification d. Vulnerability analysis e. System cross-functional cyber analysis f. Advise on RMF compliance tasks/documents (security assessment plan, etc.) g. Security configuration management (assess planned services for risk and impact) h. Develop system-level security architecture i. Design, develop, and implement system security measures that meets technical requirements j. Develop and implement specific security countermeasures for the system k. Develop approaches to mitigate system vulnerabilities l. Ensure the design of hardware, operating systems, and software applications adequately address cybersecurity requirements for the system
1.5.4 | Nuclear Hardening and Survivability (NH&S) | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.5.5 | System Safety | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.5.6 | Nuclear Surety | APPENDIX D: STRATEGIC MISSILE SYSTEMS
1.5.7 | Core Systems Engineering | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.2.4 Core Systems Engineering. The technical and management efforts that establish the technical framework for delivering materiel capabilities and ensure the effective development and delivery of capability through the implementation of a balanced approach with respect to cost, schedule, performance, and risk. This effort uses integrated, disciplined and consistent systems engineering activities and processes for development of resilient systems that are trusted, assured and easily modified. Systems engineering is composed of 16 processes: eight technical processes and eight technical management processes. These processes provide a structured approach to increasing the technical maturity of a system and increasing the likelihood that the capability being developed balances mission performance with cost, schedule, risk, and design constraints. To fulfill that purpose, a program implements the systems engineering technical processes to support the iterative maturation of the system solution or operational need. The technical processes enable the systems engineering team to ensure that the delivered capability accurately reflects the operational needs of the stakeholders. The technical processes include top down design processes such as stakeholder requirements definition, requirements analysis, and architecture design, as well as bottom-up realization processes such as transition, validation, verification, integration, and implementation. The eight technical management processes are implemented across the acquisition life cycle and provide insight and control to assist the program manager and systems engineer to meet performance, schedule, and cost goals. The eight technical processes closely align with the acquisition life cycle phases and include the top-down design processes and bottom-up realization processes that support transformation of operational needs into operational capabilities. The eight technical management processes are: decision analysis, technical planning, technical assessment, requirements management, risk management, configuration management, technical data management, and interface management. Also included are specialty engineering disciplines which bring together the hardware, software, and human elements of the systems. Includes, for example: a. System safety which is applicable to most DoD systems; this reflects the ubiquitous nature of software-driven functions, network connectivity, and systems of systems; specific certifications include safety, security, cybersecurity and airworthiness b. Reliability and maintainability – ensure that design interface and integration of the quantitative systems engineering design characteristics (i.e., reliability, maintainability, etc.) with the functional integrated product support elements c. Quality – ensures configuration item level requirements for the systems and subsystems meet critical functions and key quality attributes. d. Manufacturing and producibility – ensure manufacturing and producibility readiness, processes assessed and demonstrated, and risks identified, managed and reduced throughout the program’s life cycle e. Human systems integration – optimize total system performance and total ownership costs, while ensuring that the system is designed, operated, and maintained to effectively provide the user with the ability to complete their mission; ensure ergonomics, human factors engineering, and cognitive engineering is employed to provide for effective human-machine interfaces; define the human performance characteristics of the user based on the system description, projected characteristics of target occupational specialties, and recruitment and retention trends; establish requirements for the physical environment; determine the most efficient and cost-effective mix of DoD manpower and contract support; develop training options for operators, maintenance and support personnel; ensure that appropriate environmental safety and occupational health; assess risks to personnel and address, in terms of system design, protection from direct threat events and accidents (such as chemical, biological, and nuclear threats). f. System of systems (SoS) and system level architecting, modeling and simulation, verification and validation and external interface definition and management g. For sea systems; the Expanded Ship Work Breakdown Structure (ESWBS), configuration management (811), human factors (892), standardization (893), value engineering (894), and reliability and maintainability (895) elements Excludes, for example: a. Actual design engineering and the production engineering directly related to the WBS element with which it is associated b. Any systems engineering efforts that are called out in software systems engineering, ILS systems engineering, cybersecurity systems engineering, or “other” systems engineering effort separately identified in the WBS.
1.5.8 | Other Systems Engineering 1...n (Specify) | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.2.5 Other Systems Engineering 1...n (Specify). This element should be replaced with other systems engineering elements that cannot be categorized into one of the above elements or need to be separately identified due to high cost, high risk concerns within systems engineering. Each additional element is to be clearly identified and defined.
1.6 | Program Management | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.3 Program Management. The business and administrative planning, organizing, directing, coordinating, controlling, and approval actions designated to accomplish overall program objectives, which are not associated with specific hardware elements and are not included in systems engineering. If required, one or more areas of effort (e.g., software program management, cybersecurity program management, etc.,) may be identified at the next level below program management. In those cases, the remaining totality of program management efforts will be defined as “core program management” at the level equal to the segregated items.
1.6.1 | Software Program Management | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.3.1 Software Program Management. The software program management encompasses the management of the full software life cycle, from conception to deployment. The function focuses at the system level of applying business and project management skills needed to produce high-quality software products. Includes, for example: a. Overseeing requirements analysis and design, and effective implementation and delivery of all fully-tested software b. Ensure sufficient end-user involvement c. Maintain communication among customers, developers, users, and project managers d. Establish realistic or articulated project goals e. Develop accurate estimates of needed resources f. Define system requirements and specifications g. Assure reporting of the project’s status h. Proper management of risks i. Ensure the use of mature technology and handle the project’s complexity
1.6.2 | Integrated Logistics Support (ILS) Program Management | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.3.2 Integrated Logistics Support Program Management. The efforts to manage the planning and execution of the ILS disciplines to assure system acquisition logistics availability. Includes, for example: a. Support element management, defined as the logistics tasks management effort and technical control, and the business management of the support elements. The logistics management function encompasses the support evaluation and supportability assurance required to produce an affordable and supportable defense materiel system. b. Planning and management of all the functions of logistics. Examples are: maintenance support planning and support facilities planning; other support requirements determination; support equipment requirements determination; supply support; packaging, handling, storage, and transportation; provisioning requirements determination and planning; training system requirements determination; computer resource determination; organizational, intermediate, and depot maintenance determination management; and data management
1.6.3 | Cybersecurity Management | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.3.3 Cybersecurity Program Management. The management and understanding of cybersecurity program and its ramifications across the organization (only if costs are collected in this manner). Includes, for example: a. Overseeing cybersecurity risk assessment, management, and mediation b. Cybersecurity threat vectors and mitigation processes c. Ensuring design and management of secure information systems d. Emerging tools and resources for organizational and platform security
1.6.4 | Program Control | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.3.4 Core Program Management. The efforts to understand and manage multiple discipline areas in order the successfully accomplish program objectives for development, production, and sustainment of systems to meet the user’s operational needs Includes, for example: a. Cost, schedule, performance measurement management, warranty administration, contract management, vendor liaison, subcontract management, etc. b. For sea systems; the Expanded Ship Work Breakdown Structure (ESWBS), project management (897); data management (896); and supply support (853) elements Excludes, for example: a. Actual program management directly related to another WBS element b. Any program management efforts that are called out in software program management, cybersecurity program management, or “other” program management effort separately identified in the WBS.
1.6.5 | Core Program Management | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.3.5 Other Program Management 1...n (Specify). This element should be replaced with other program management elements that cannot be categorized into one of the above elements or need to be separately identified due to high cost or high risk concerns within program management. Each additional element is to be clearly identified and defined.
1.6.6 | Other Program Management 1...n (Specify) | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.4 System Test and Evaluation. The use of pilot, prototype, production, or specifically fabricated hardware/software to obtain or validate engineering data on the performance of the system during the developmental phase of the program. It also includes all effort associated with the development of any specialized tools or data in support of the system level test program. Includes, for example: a. Detailed planning, conduct, support, data reduction and reports (excluding the contract data requirements list data) from such testing, and test articles that are functionally configured to represent and test subsystems/components of the defense materiel end item being developed or produced b. Design and production of models, specimens, fixtures and instrumentation c. System level labs that integrate both hardware and software NOTE: Test articles that are functionally configured to represent and test the complete defense materiel end item being developed or produced, are excluded from this WBS element. Excludes, for example: a. All formal and informal testing up through the subsystem level, which can be associated with the hardware/software element acceptance testing NOTE: These excluded efforts are to be included with the appropriate hardware or software elements.
1.7 | System Test and Evaluation | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.4.1 Development Test and Evaluation. The test and evaluation conducted by the developing agency of the DoD component. It includes test and evaluation conducted to: a. Demonstrate that the engineering design and development process is complete b. Demonstrate that the design risks have been minimized c. Demonstrate that the system will meet specifications d. Assess the system’s military utility when introduced e. Determine whether the engineering design is supportable (practical, maintainable, safe, etc.) for operational use f. Provide test data with which to examine and evaluate trade-offs against specification requirements, life cycle cost, and schedule g. Perform the logistics testing efforts to evaluate the achievement of supportability goals, the adequacy of the support package for the system, (e.g., deliverable maintenance tools, test equipment, technical publications, maintenance instructions, and personnel skills and training requirements, etc.) Includes, for example: a. All contractor/system developer in-house effort b. Where applicable, models, tests and associated simulations (e.g., such as wind tunnel, static, drop, and fatigue); integration ground tests; test bed aircraft and associated support; qualification test and evaluation, development flight test, test instrumentation, environmental tests, ballistics, radiological, range and accuracy demonstrations, test facility operations, test equipment (including its support equipment), chase and calibrated pacer aircraft and support thereto, and logistics testing c. For aircraft; avionics integration test composed of the following: i. Test bench/laboratory, including design, acquisition, and installation of basic computers and test equipment that will provide an ability to simulate in the laboratory the operational environment of the avionics system/subsystem ii. Air vehicle equipment, consisting of the avionics and/or other air vehicle subsystem modules that are required by the bench/lab or flying test bed in order to provide a compatible airframe avionics system/subsystem for evaluation purposes iii. Flying test bed, including requirements analysis, design of modifications, lease or purchase of test bed aircraft, modification of aircraft, installation of avionics equipment and instrumentation, and checkout of an existing aircraft used essentially as a flying avionics laboratory iv. Avionics test program, consisting of the effort required to develop test plans/procedures, conduct tests, and analyze hardware and software test results to verify the avionics equipment’s operational capability and compatibility as an integrated air vehicle subsystem v. Software, referring to the effort required to design, code, de-bug, and document software programs necessary to direct the avionics integration test d. For engines: engine military qualification tests and engine preliminary flight rating tests e. For sea systems: model basin, hydrostatic, fatigue, shock, special sea tests and trials, etc., including the Expanded Ship Work Breakdown Structure (ESWBS), trials agenda preparation, data collection and analysis (842); dock and sea trials (9823); and hull vibration survey (9825) elements f. For missiles: test articles such as inert measurement vehicles, launch separation vehicles, separation and control test vehicles, boost test vehicles g. For ordnance: test articles such as ballistic test rounds, inert measurement rounds, dummy rounds, launch separation rounds, etc.
1.7.1 | Development Test and Evaluation | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.4.2 Operational Test and Evaluation. The test and evaluation conducted by agencies other than the developing command to assess the prospective system’s military utility, operational effectiveness, operational suitability, logistics supportability (including compatibility, inter-operability, reliability, maintainability, logistic requirements, etc.), cost of ownership, and need for any modifications. Includes, for example: a. Initial operational test and evaluation conducted during the development of a system b. Such tests as system demonstration, flight tests, sea trials, mobility demonstrations, on-orbit tests, spin demonstration, stability tests, qualification operational test and evaluation, etc., and support thereto, required to prove the operational capability of the deliverable system. c. Contractor support (e.g., technical assistance, maintenance, labor, material, etc.) consumed during this phase of testing d. Logistics testing efforts to evaluate the achievement of supportability goals and the adequacy of the support for the system (e.g., deliverable maintenance tools, test equipment, technical publications, maintenance instructions, personnel skills and training requirements, and software support facility/environment elements)
1.7.2 | Operational Test and Evaluation | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.4.3 Cybersecurity System Test and Evaluation. The developmental test and evaluation and operational test and evaluation conducted and monitored by the developing agency of the DoD. The technical efforts of ensuring the confidentiality, integrity, and availability of information and technology by monitoring and defending against cyber (network) attacks. Includes, for example: a. Vulnerability scanning and interpretation b. Vulnerability testing and penetration testing (usually linked to patch management) c. Security information and event management d. Destructive and non-destructive exploitation e. Test conducted in an operational environment with certified red teams f. Cybersecurity compliance tracking and reporting g. Malware scanning, detection, and prevention services h. Security, IT certification, and accreditation compliance services
1.7.3 | Cybersecurity Test and Evaluation | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.4.4 Mock-ups/System Integration Labs (SILs). The design engineering and production of system or subsystem mock-ups that have special contractual or engineering significance or that are not required solely for the conduct of one of the above elements of testing. SILs are often used in lieu of (or in addition to) mock-ups. SILs are risk reduction facilities where software and hardware can be developed, integrated, tested, and evaluated for both standalone functionality and/or interoperability prior to being fielded. Includes, for example: a. Hardware/lab equipment b. SIL Software (written to simulate the operating environment or written to operate the SIL)
1.7.4 | Mock-ups/System Integration Labs (SILs) | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.4.5 Test and Evaluation Support. The support elements necessary to operate and maintain, during test and evaluation, systems and subsystems, which are not consumed during the testing phase and are not allocated to a specific phase of testing. Includes, for example: a. Repairable spares, repair of reparables, repair parts, consumables, warehousing and distribution of spares and repair parts, test and support equipment, test bed vehicles, drones, surveillance aircraft/chase aircraft, tracking vessels, contractor technical support Excludes, for example: a. Operational and maintenance personnel, special fixtures, special instrumentation, etc., that are utilized and/or consumed in a single element of testing and that should be included under that element of testing
1.7.5 | Test and Evaluation Support | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.4.6 Test Facilities. The special test facilities required for performance of the various developmental tests necessary to prove the design and reliability of the system or subsystem. Includes, for example: a. Test tank test fixtures, propulsion test fixtures, white rooms, test chambers, range/targeting facilities Excludes, for example: a. Brick and mortar-type facilities identified as industrial facilities
1.7.6 | Test Facilities | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.5 Training. Deliverable training services, devices, accessories, aids, equipment, and parts used to facilitate instruction through which personnel will learn to operate and maintain the system with maximum efficiency. Includes, for example: a. All effort associated with the design, development, and production of deliverable training equipment and its associated software as well as the execution of training services Excludes, for example: a. Overall planning, management, and task analysis functions inherent in the WBS element systems engineering/program management
1.8 | Training | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.5.1 Equipment. Distinctive deliverable end items of training equipment, assigned by either a contractor or military service, required to meet specific training objectives. Includes, for example: a. Operational and Maintenance Trainers and training equipment including items such as cutaways, mock-ups, and models (e.g. Operator Instructional Equipment, Maintainer Instructional Equipment)
1.8.1 | Equipment | APPENDIX D: STRATEGIC MISSILE SYSTEMS | [Blank]
1.8.1.1 | Operator Instructional Equipment | APPENDIX D: STRATEGIC MISSILE SYSTEMS | [Blank]
1.8.1.2 | Maintainer Instructional Equipment | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.5.2 Services. Deliverable training services, accessories, and courseware aids necessary to accomplish the objectives of training. Includes, for example: a. Operational and Maintenance Training Services including courses, course materials; and curriculum required to design, execute, and produce a contractor developed training program and related software programs (e.g. operator instructional services, maintainer instructional services) Excludes, for example: a. Deliverable training data associated with support data (see Data Deliverables 1...n (Specify), Support Data)
1.8.2 | Services | APPENDIX D: STRATEGIC MISSILE SYSTEMS | [Blank]
1.8.2.1 | Operator Instructional Services | APPENDIX D: STRATEGIC MISSILE SYSTEMS | [Blank]
1.8.2.2 | Maintainer Instructional Services | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.5.3 Facilities. The special construction necessary to accomplish training objectives. Includes, for example: a. Modification or rehabilitation of existing training facilities and infrastructure used to accomplish training objectives Excludes, for example: a. Installed equipment used to acquaint the trainee with the system or establish trainee proficiency b. The brick and mortar-type facilities identified as industrial facilities
1.8.3 | Facilities | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.5.4 Training Software Release 1...n (Specify). Updated/upgraded software for training purposes delivered to the field during the acquisition phase.
1.8.4 | Training Software Release 1...n (Specify) | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.6 Data. The deliverable data required to be listed on a contract data requirements list. Includes, for example: a. Only such effort that can be reduced or avoided if the data item is eliminated b. Government-peculiar data; acquiring, assembling, reproducing, packaging and shipping the data c. Transforming data into Government
1.9 | Data | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.6.1 Data Deliverables 1...n (Specify). Deliverable data which provides technical, engineering, management, support, or other data required for contract delivery. Includes, for example: a. Technical Publications. Technical data, providing instructions for installation, operation, maintenance, training, and support, formatted into a technical manual. Data may be presented in any form regardless of the form or method of recording. Technical orders that meet the criteria of this definition may also be classified as technical manuals. For sea systems: Expanded Ship Work Breakdown Structure (ESWBS), technical manuals and other data (856) element. b. Engineering Data. Recorded scientific or technical information (regardless of the form or method of recording) including computer software documentation. Engineering data defines and documents an engineering design or product configuration (sufficient to allow duplication of the original items) and is used to support production, engineering, and logistics activities. For sea systems; Expanded Ship Work Breakdown Structure (ESWBS), design support, ship’s selected records (8302); design support, services, reproduction (8303); and engineering drawings and specifications (855) elements. c. Management Data. The data items necessary for configuration management, cost, schedule, contractual data management, program management, etc., required by the Government. For sea systems; Expanded Ship Work Breakdown Structure (ESWBS), contract data requirements (988) element. d. Support Data. The data items designed to document support planning in accordance with functional categories
1.9.1 | Data Deliverables 1...n (Specify) | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.6.2 Data Repository. The activity and enterprise data storage entity (or sometimes entities) for Government approved documents that are the property of the Government into which data has been specifically partitioned for analytical or reporting purposes. As custodian for the Government, the repository, authorized by approved change orders, maintains master documents at the latest approved revision level. Includes, for example: a. All effort necessary to maintain documents
1.9.2 | Data Repository | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.6.3 Data Rights 1...n (Specify). Government’s license rights of valuable intellectual property including technical data of any recorded information of a scientific or technical nature (e.g., product design or maintenance data, computer databases, and computer software documentation); and computer software including executable code, source code, code listings, design details, processes, flow charts, and related material. Includes, for example: a. Unlimited Rights. Developed exclusively at Government expense, and certain types of data (e.g., Form, Fit, and Function data (FFF); Operation, Maintenance, Installation, and Training (OMIT)). These rights involve the right to use, modify, reproduce, display, release, or disclose technical data in whole or in part, in any manner, and for any purpose whatsoever, and to have or authorize others to do so. b. Government Purpose Rights. This right involves the right to use, duplicate, or disclose technical data for Government purposes only, and to have or permit others to do so for Government purposes only. Government purposes include competitive procurement, but do not include the right to permit others to use the data for commercial purposes. c. Limited Rights. A limited rights agreement permits the Government to use proprietary technical data in whole or in part. It also means that the Government has to obtain the expressed permission of the party providing the technical data to release it, or disclose it, outside the Government.
1.9.3 | Data Rights 1...n (Specify) | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | K.3.7 Peculiar Support Equipment. The design, development, and production of those deliverable items and associated software required to support and maintain the system or portions of the system while the system is not directly engaged in the performance of its mission, and which are not common support equipment. Items should be designated by commodity subassembly (airframe, engine, avionics, etc.). Includes, for example: a. Vehicles, equipment, tools, etc., used to fuel, service, transport, hoist, repair, overhaul, assemble, disassemble, test, inspect, or otherwise maintain mission equipment b. Any production of duplicate or modified factory test or tooling equipment delivered to the Government for use in maintaining the system. (Factory test and tooling equipment initially used by the contractor in the production process but subsequently delivered to the Government will be included as cost of the item produced.) c. Any additional equipment or software required to maintain or modify the software portions of the system Excludes, for example: a. Overall planning, management, and task analysis functions inherent in the work breakdown structure elements Systems Engineering and Program Management b. Common support equipment, presently in the DoD inventory or commercially available, bought by the using command, not by the acquiring command
1.1 | Peculiar Support Equipment | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.7.1 Test and Measurement Equipment. The peculiar or unique testing and measurement equipment that allows an operator or maintenance function to evaluate operational conditions of a system or equipment by performing specific diagnostics, screening, or quality assurance effort at an organizational, intermediate, or depot level of equipment support. Includes, for example: a. Test measurement and diagnostic equipment, precision measuring equipment, automatic test equipment, manual test equipment, automatic test systems, test program sets, appropriate interconnect devices, automated load modules, tapes, and related software, firmware and support hardware (power supply equipment, etc.) used at all levels of maintenance b. Packages that enable line or shop replaceable units, printed circuit boards, or similar items to be diagnosed using automatic test equipment
1.10.1 | Test and Measurement Equipment | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.7.1.1 Test and Measurement Equipment (Airframe/Hull/Vehicle). This element captures the cost of the airframe, ship hull, or ground vehicle hull/frame related test and measurement equipment. Identify the related WBS subassemblies associated with the airframe/hull/vehicle. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested
1.10.1.1 | Test and Measurement Equipment (Airframe/Hull/Vehicle) | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.7.1.2 Test and Measurement Equipment (Propulsion). This element captures the cost of the propulsion system, engines, prime movers, turbines, etc. related test and measurement equipment. Identify the related WBS subassemblies associated with propulsion. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.10.1.2 | Test and Measurement Equipment (Propulsion) | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.7.1.3 Test and Measurement Equipment (Electronics/Avionics). This element captures the cost of the electronics/avionics related test and measurement equipment. Identify the related WBS subassemblies associated with electronics/avionics. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.10.1.3 | Test and Measurement Equipment (Electronics/Avionics) | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.7.1.4 Test and Measurement Equipment (Other Major Subsystem 1...n (Specify)). This element captures the cost of other major subsystems (e.g., armament, weapons, vehicle subsystems, etc.) not captured above related test and measurement equipment. Identify the related WBS subassemblies associated with the other major subsystems. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.10.1.4 | Test and Measurement Equipment (Other Major Subsystem 1...n (Specify)) | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.7.2 Support and Handling Equipment. The peculiar or unique tools and handling equipment used for support of the mission system at an organizational, intermediate, or depot level Includes, for example: a. Ground support equipment, vehicular support equipment, powered support equipment, non-powered support equipment, munitions material handling equipment, materiel handling equipment, and software support equipment (hardware and software)
1.10.2 | Support and Handling Equipment | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.7.2.1 Support and Handling Equipment (Airframe/Hull/Vehicle). This element captures the cost of the airframe, ship hull, or ground vehicle hull/frame related support and handling equipment. Identify the related WBS subassemblies associated with airframe/hull/vehicle. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.10.2.1 | Support and Handling Equipment (Airframe/Hull/Vehicle) | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.7.2.2 Support and Handling Equipment (Propulsion). This element captures the cost of propulsion related support and handling equipment. Identify the related WBS subassemblies associated with propulsion. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.10.2.2 | Support and Handling Equipment (Propulsion) | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.7.2.3 Support and Handling Equipment (Electronics/Avionics). This element captures the cost of the electronics/avionics related support and handling equipment. Identify the related WBS subassemblies associated with electronics/avionics. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.10.2.3 | Support and Handling Equipment (Electronics/Avionics) | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.7.2.4 Support and Handling Equipment (Other Major Subsystem 1...n (Specify)). This element captures the cost of other major subsystems (e.g., armament, weapons, vehicle subsystems, etc.) not captured above related support and handling equipment. Identify the related WBS subassemblies associated with the other major subsystems. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.10.2.4 | Support and Handling Equipment (Other Major Subsystem 1...n (Specify)) | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.8 Common Support Equipment. The items required to support and maintain the system or portions of the system while not directly engaged in the performance of its mission, and which are presently in the DoD inventory for support of other systems. Includes, for example: a. Acquisition of additional quantities of this equipment needed to support the item b. All efforts required to assure the availability of this equipment to support the item
1.11 | Common Support Equipment | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.8.1 Test and Measurement Equipment. The common testing and measurement equipment that allows an operator or maintenance function to evaluate operational conditions of a system or equipment by performing specific diagnostics, screening, or quality assurance effort at an organizational, intermediate, or depot level of equipment support. Includes, for example: a. Test measurement and diagnostic equipment, precision measuring equipment, automatic test equipment, manual test equipment, automatic test systems, test program sets, appropriate interconnect devices, automated load modules, tapes, and related software, firmware, and support hardware (power supply equipment, etc.) Used at all levels of maintenance b. Packages that enable line or shop replaceable units, printed circuit boards, or similar items to be diagnosed using automatic test equipment
1.11.1 | Test and Measurement Equipment | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.8.1.1 Test and Measurement Equipment (Airframe/Hull/Vehicle). This element captures the cost of the airframe, ship hull, or ground vehicle hull/frame related test and measurement equipment. Identify the related WBS subassemblies associated with the airframe/hull/vehicle. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.11.1.1 | Test and Measurement Equipment (Airframe/Hull/Vehicle) | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.8.1.2 Test and Measurement Equipment (Propulsion). This element captures the cost of the propulsion system, engines, prime movers, turbines, etc. related test and measurement equipment. Identify the related WBS subassemblies associated with propulsion. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.11.1.2 | Test and Measurement Equipment (Propulsion) | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.8.1.3 Test and Measurement Equipment (Electronics/Avionics). This element captures the cost of the electronics/avionics related test and measurement equipment. Identify the related WBS subassemblies associated with electronics/avionics. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.11.1.3 | Test and Measurement Equipment (Electronics/Avionics) | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.8.1.4 Test and Measurement Equipment (Other Major Subsystem 1...n (Specify)). This element captures the cost of other major subsystems (e.g., armament, weapons, vehicle subsystems, etc.) not captured above related test and measurement equipment. Identify the related WBS subassemblies associated with the other major subsystems. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.11.1.4 | Test and Measurement Equipment (Other Major Subsystem 1...n (Specify)) | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.8.2 Support and Handling Equipment. The common tools and handling equipment used for support of the mission system at an organizational, intermediate, or depot level Includes, for example: a. Ground support equipment, vehicular support equipment, powered support equipment, non-powered support equipment, munitions material handling equipment, materiel handling equipment, and software support equipment (hardware/software)
1.11.2 | Support and Handling Equipment | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.8.2.1 Support and Handling Equipment (Airframe/Hull/Vehicle). This element captures the cost of the airframe, ship hull, or ground vehicle hull/frame related support and handling equipment. Identify the related WBS subassemblies associated with airframe/hull/vehicle. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.11.2.1 | Support and Handling Equipment (Airframe/Hull/Vehicle) | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.8.2.2 Support and Handling Equipment (Propulsion). This element captures the cost of propulsion related support and handling equipment. Identify the related WBS subassemblies associated with propulsion. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.11.2.2 | Support and Handling Equipment (Propulsion) | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.8.2.3 Support and Handling Equipment (Electronics/Avionics). This element captures the cost of the electronics/avionics related support and handling equipment. Identify the related WBS subassemblies associated with electronics/avionics. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.11.2.3 | Support and Handling Equipment (Electronics/Avionics) | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.8.2.4 Support and Handling Equipment (Other Major Subsystem 1...n (Specify)). This element captures the cost of other major subsystems (e.g., armament, weapons, vehicle subsystems, etc.) not captured above related support and handling equipment. Identify the related WBS subassemblies associated with the other major subsystems. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.11.2.4 | Support and Handling Equipment (Other Major Subsystem 1...n (Specify)) | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.9 Operational/Site Activation by Site 1...n (Specify). The real estate, construction, conversion, utilities, and equipment to provide all facilities required to house, service, and launch prime mission equipment at the organizational and intermediate level. Includes, for example: a. Conversion of site, ship, or vehicle b. System assembly, checkout, and installation (of mission and support equipment) into site facility or ship to achieve operational status c. Contractor support in relation to operational/site activation
1.12 | Operational/Site Activation by Site 1...n (Specify) | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.9.1 System Assembly, Installation, and Checkout. The materials and services involved in the assembly of mission equipment at the site. Includes, for example: a. Installation of mission and support equipment in the operations or support facilities and complete system checkout or shakedown to ensure operational status. Where appropriate, specify by site, ship, or vehicle. b. The efforts and activities associated with shipping the system from contractor facility to customer site. That site could be a DT&E site, an installation and checkout site, or any similar site that is outside the direct control of the contractor. Excludes, for example: a. Field team installation
1.12.1 | System Assembly, Installation, and Checkout | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.9.2 Contractor Technical Support. The materials and services provided by the contractor related to activation. Includes, for example: a. Repair of reparables, standby services, and final turnover
1.12.2 | Contractor Technical Support | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.9.3 Site Construction. Real estate, site planning and preparation, construction, and other special-purpose facilities necessary to achieve system operational status. Includes, for example: a. Construction of utilities, roads, and interconnecting cabling
1.12.3 | Site Construction | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.9.4 Site/Ship/Vehicle Conversion. The materials and services required to convert existing sites, ships, or vehicles to accommodate the mission equipment and selected support equipment directly related to the specific system. Includes, for example: a. Operations, support, and other special purpose facilities conversion necessary to achieve system operational status, e.g., launch. Where appropriate, specify by site, ship, or vehicle
1.12.4 | Site/Ship/Vehicle Conversion | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.9.5 Interim Contractor Support (ICS). The effort required to provide temporary contractor support in lieu of a permanent support solution (organic or commercial) for a predetermined time, while a permanent support capability is put in place. Interim support is usually required for support of prototypes and early test and production assets during development and initial fielding (i.e., Initial Operating Capability (IOC)). Includes, for example: a. Providing life cycle logistics in accordance with the integrated product support (IPS) elements in support of the prime mission product. Excludes, for example: a. The development and production of the original prime mission product.
1.12.5 | Deployment Planning | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.10 Contractor Logistics Support (CLS). Contracted weapon system sustainment including performance of maintenance and/or materiel management functions for a DoD weapon system by a commercial activity or contractor sustainment of a weapon system that is intended to start after a permanent decision is made to cover the operations and support efforts of the weapon system. CLS generally starts before FOC (final operating capability) or when performance based logistics (PBL) is implemented in the operating and support (O&S) phase. Includes, for example: a. Prime Mission Product (PMP) maintenance and refurbishment. The cost for this element includes maintenance and refurbishment (including the development and production) of existing operational systems. b. Support functions required to maintain the system, such as sustaining engineering, program management, logistics support, and supply chain management c. Test and evaluation for system and subsystem modifications d. Repair of reparable items; replacement of condemned items (including all PMP, support equipment, and training equipment) e. Operational, maintenance and other personnel required at the operational unit level f. Unit operations costs, including operating material and support services at the operating unit g. Installation and personnel support functions in support of the unit level manpower Excludes, for example: a. Does not include interim contractor support (ICS), a temporary measure for a system’s initial period of operation before a permanent form of support is in place. b. Contractor sustainment support for a specific sustainment task that a service would otherwise conduct itself.
1.12.6 | Aerospace Ground Equipment | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.11 Industrial Facilities. The construction, conversion, or expansion of industrial facilities for production, inventory, and contractor depot maintenance required when that service is for the specific system. Includes, for example: a. Equipment acquisition or modernization, where applicable b. Maintenance of these facilities or equipment c. Industrial facilities for hazardous waste management to satisfy environmental standards Excludes, for example: a. Capital equipment
1.12.7 | Real Property Installed Equipment | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.11.1 Construction/Conversion/Expansion. The real estate and preparation of system peculiar industrial facilities for production, inventory, depot maintenance, and other related activities.
1.12.8 | Interim Contractor Support (ICS) | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.11.2 Equipment Acquisition or Modernization. The production equipment acquisition, modernization, or transfer of equipment for the particular system. This pertains to Government owned and leased equipment under facilities contract.
1.13 | Contractor Logistics Support (CLS) | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.11.3 Maintenance (Industrial Facilities). The maintenance, preservation, and repair of industrial facilities and equipment.
1.14 | Initial Spares/Repair Parts | APPENDIX D: STRATEGIC MISSILE SYSTEMS | K.3.12 Initial Spares and Repair Parts. The deliverable spare components, assemblies, and subassemblies used for initial replacement purposes in the materiel system equipment end item. Includes, for example: a. Repairable spares (reparables) and repair parts required as initial stockage to support and maintain newly fielded systems or subsystems during the initial phase of service, including pipeline and war reserve quantities, at all levels of maintenance and support. Lower level WBS breakouts should be by subsystem. b. Spare training and support equipment items c. The combination of resources, processes, planning, procedures, design, considerations, methods, and all hardware to ensure that all system, equipment, and support items are preserved, packaged, handled, and transported properly, including environmental considerations, equipment preservation for short and long term storage, and transportability. This includes requirements such as special environmentally controlled, shock isolated containers for transport to and from repair facilities and ensuring proper Care of Supplies in Storage (COSIS) program requirements are followed. Excludes, for example: a. Development test spares and spares provided specifically for use during installation, assembly, and checkout on site

## E
WBS # | WBS Nomenclature | Appendix | WBS Definition
1 | Sea System | APPENDIX E: SEA SYSTEMS
1.1 | Ship | APPENDIX E: SEA SYSTEMS
1.1.1 | Hull Structure | APPENDIX E: SEA SYSTEMS
1.1.2 | Propulsion Plant | APPENDIX E: SEA SYSTEMS
1.1.3 | Electric Plant | APPENDIX E: SEA SYSTEMS
1.1.4 | Command, Communications, and Surveillance | APPENDIX E: SEA SYSTEMS
1.1.5 | Auxiliary Systems | APPENDIX E: SEA SYSTEMS
1.1.6 | Outfit and Furnishings | APPENDIX E: SEA SYSTEMS
1.1.7 | Armament | APPENDIX E: SEA SYSTEMS
1.1.8 | Total Ship Integration/Engineering | APPENDIX E: SEA SYSTEMS
1.1.9 | Ship Assembly and Support Services | APPENDIX E: SEA SYSTEMS
1.2 | Systems Engineering | APPENDIX E: SEA SYSTEMS | K.3.2 Systems Engineering. The technical and management efforts of directing and controlling a totally integrated engineering effort of a system or program. The following represent many, but not all, of the systems engineering efforts needed for a system or program. If required, one or more areas of effort (e.g., software systems engineering, cybersecurity, etc., may be identified at the next level below systems engineering. In those cases, the remaining totality of systems engineering efforts will be defined as “core systems engineering” at the level equal to the segregated items.
1.2.1 | Software Systems Engineering | APPENDIX E: SEA SYSTEMS | K.3.2.1 Software Systems Engineering. The efforts which encompass software systems technologies, software engineering methods, and management techniques that improve the quality and delivery of software intensive systems and applications. Includes, for example: a. The application of a systematic, disciplined, quantifiable approach to the development and operations and support (O&S) of software b. The determination of software development or software test facility/environment requirements c. Application of systems engineering to software, that is, the systematic application of scientific and technical knowledge, methods, and experience to the design, implementation, testing, and documentation of software d. Analyzing the system requirements allocated to the software, developing the software requirements, developing the software architecture, designing the software, implementing the software in the code, integrating the software components, and testing the software to verify that the software satisfies the specified requirements allocated to the software component of a system or subsystem.
1.2.2 | Integrated Logistics Support (ILS) Systems Engineering | APPENDIX E: SEA SYSTEMS | K.3.2.2 Integrated Logistics Support (ILS) Systems Engineering. The efforts to ensure the integrated planning and action of a number of disciplines in concert with one another to assure system availability. The planning of each element of ILS (e.g., integrated product support (IPS) elements) is developed in coordination with systems engineering and other efforts. Includes, for example: a. Product support management b. Design interface c. Sustaining engineering d. Supply support e. Maintenance planning and management f. Packaging, handling, storage, and transportation g. Technical data h. Support equipment i. Training and training support j. Manpower and personnel k. Facilities and infrastructure l. Computer resources
1.2.3 | Cybersecurity Systems Engineering | APPENDIX E: SEA SYSTEMS | K.3.2.3 Cybersecurity Systems Engineering. The efforts to apply scientific and engineering principles to identify security vulnerabilities and minimize or contain risks associated with these vulnerabilities. Includes, for example: a. Cybersecurity requirements evaluation b. Cyberattack surface characterization c. Cooperative vulnerability identification d. Vulnerability analysis e. System cross-functional cyber analysis f. Advise on RMF compliance tasks/documents (security assessment plan, etc.) g. Security configuration management (assess planned services for risk and impact) h. Develop system-level security architecture i. Design, develop, and implement system security measures that meets technical requirements j. Develop and implement specific security countermeasures for the system k. Develop approaches to mitigate system vulnerabilities l. Ensure the design of hardware, operating systems, and software applications adequately address cybersecurity requirements for the system
1.2.4 | Core Systems Engineering | APPENDIX E: SEA SYSTEMS | K.3.2.4 Core Systems Engineering. The technical and management efforts that establish the technical framework for delivering materiel capabilities and ensure the effective development and delivery of capability through the implementation of a balanced approach with respect to cost, schedule, performance, and risk. This effort uses integrated, disciplined and consistent systems engineering activities and processes for development of resilient systems that are trusted, assured and easily modified. Systems engineering is composed of 16 processes: eight technical processes and eight technical management processes. These processes provide a structured approach to increasing the technical maturity of a system and increasing the likelihood that the capability being developed balances mission performance with cost, schedule, risk, and design constraints. To fulfill that purpose, a program implements the systems engineering technical processes to support the iterative maturation of the system solution or operational need. The technical processes enable the systems engineering team to ensure that the delivered capability accurately reflects the operational needs of the stakeholders. The technical processes include top down design processes such as stakeholder requirements definition, requirements analysis, and architecture design, as well as bottom-up realization processes such as transition, validation, verification, integration, and implementation. The eight technical management processes are implemented across the acquisition life cycle and provide insight and control to assist the program manager and systems engineer to meet performance, schedule, and cost goals. The eight technical processes closely align with the acquisition life cycle phases and include the top-down design processes and bottom-up realization processes that support transformation of operational needs into operational capabilities. The eight technical management processes are: decision analysis, technical planning, technical assessment, requirements management, risk management, configuration management, technical data management, and interface management. Also included are specialty engineering disciplines which bring together the hardware, software, and human elements of the systems. Includes, for example: a. System safety which is applicable to most DoD systems; this reflects the ubiquitous nature of software-driven functions, network connectivity, and systems of systems; specific certifications include safety, security, cybersecurity and airworthiness b. Reliability and maintainability – ensure that design interface and integration of the quantitative systems engineering design characteristics (i.e., reliability, maintainability, etc.) with the functional integrated product support elements c. Quality – ensures configuration item level requirements for the systems and subsystems meet critical functions and key quality attributes. d. Manufacturing and producibility – ensure manufacturing and producibility readiness, processes assessed and demonstrated, and risks identified, managed and reduced throughout the program’s life cycle e. Human systems integration – optimize total system performance and total ownership costs, while ensuring that the system is designed, operated, and maintained to effectively provide the user with the ability to complete their mission; ensure ergonomics, human factors engineering, and cognitive engineering is employed to provide for effective human-machine interfaces; define the human performance characteristics of the user based on the system description, projected characteristics of target occupational specialties, and recruitment and retention trends; establish requirements for the physical environment; determine the most efficient and cost-effective mix of DoD manpower and contract support; develop training options for operators, maintenance and support personnel; ensure that appropriate environmental safety and occupational health; assess risks to personnel and address, in terms of system design, protection from direct threat events and accidents (such as chemical, biological, and nuclear threats). f. System of systems (SoS) and system level architecting, modeling and simulation, verification and validation and external interface definition and management g. For sea systems; the Expanded Ship Work Breakdown Structure (ESWBS), configuration management (811), human factors (892), standardization (893), value engineering (894), and reliability and maintainability (895) elements Excludes, for example: a. Actual design engineering and the production engineering directly related to the WBS element with which it is associated b. Any systems engineering efforts that are called out in software systems engineering, ILS systems engineering, cybersecurity systems engineering, or “other” systems engineering effort separately identified in the WBS.
1.2.5 | Other Systems Engineering 1...n (Specify) | APPENDIX E: SEA SYSTEMS | K.3.2.5 Other Systems Engineering 1...n (Specify). This element should be replaced with other systems engineering elements that cannot be categorized into one of the above elements or need to be separately identified due to high cost, high risk concerns within systems engineering. Each additional element is to be clearly identified and defined.
1.3 | Program Management | APPENDIX E: SEA SYSTEMS | K.3.3 Program Management. The business and administrative planning, organizing, directing, coordinating, controlling, and approval actions designated to accomplish overall program objectives, which are not associated with specific hardware elements and are not included in systems engineering. If required, one or more areas of effort (e.g., software program management, cybersecurity program management, etc.,) may be identified at the next level below program management. In those cases, the remaining totality of program management efforts will be defined as “core program management” at the level equal to the segregated items.
1.3.1 | Software Program Management | APPENDIX E: SEA SYSTEMS | K.3.3.1 Software Program Management. The software program management encompasses the management of the full software life cycle, from conception to deployment. The function focuses at the system level of applying business and project management skills needed to produce high-quality software products. Includes, for example: a. Overseeing requirements analysis and design, and effective implementation and delivery of all fully-tested software b. Ensure sufficient end-user involvement c. Maintain communication among customers, developers, users, and project managers d. Establish realistic or articulated project goals e. Develop accurate estimates of needed resources f. Define system requirements and specifications g. Assure reporting of the project’s status h. Proper management of risks i. Ensure the use of mature technology and handle the project’s complexity
1.3.2 | Integrated Logistics Support (ILS) Program Management | APPENDIX E: SEA SYSTEMS | K.3.3.2 Integrated Logistics Support Program Management. The efforts to manage the planning and execution of the ILS disciplines to assure system acquisition logistics availability. Includes, for example: a. Support element management, defined as the logistics tasks management effort and technical control, and the business management of the support elements. The logistics management function encompasses the support evaluation and supportability assurance required to produce an affordable and supportable defense materiel system. b. Planning and management of all the functions of logistics. Examples are: maintenance support planning and support facilities planning; other support requirements determination; support equipment requirements determination; supply support; packaging, handling, storage, and transportation; provisioning requirements determination and planning; training system requirements determination; computer resource determination; organizational, intermediate, and depot maintenance determination management; and data management
1.3.3 | Cybersecurity Management | APPENDIX E: SEA SYSTEMS | K.3.3.3 Cybersecurity Program Management. The management and understanding of cybersecurity program and its ramifications across the organization (only if costs are collected in this manner). Includes, for example: a. Overseeing cybersecurity risk assessment, management, and mediation b. Cybersecurity threat vectors and mitigation processes c. Ensuring design and management of secure information systems d. Emerging tools and resources for organizational and platform security
1.3.4 | Core Program Management | APPENDIX E: SEA SYSTEMS | K.3.3.4 Core Program Management. The efforts to understand and manage multiple discipline areas in order the successfully accomplish program objectives for development, production, and sustainment of systems to meet the user’s operational needs Includes, for example: a. Cost, schedule, performance measurement management, warranty administration, contract management, vendor liaison, subcontract management, etc. b. For sea systems; the Expanded Ship Work Breakdown Structure (ESWBS), project management (897); data management (896); and supply support (853) elements Excludes, for example: a. Actual program management directly related to another WBS element b. Any program management efforts that are called out in software program management, cybersecurity program management, or “other” program management effort separately identified in the WBS.
1.3.5 | Other Program Management 1...n (Specify) | APPENDIX E: SEA SYSTEMS | K.3.3.5 Other Program Management 1...n (Specify). This element should be replaced with other program management elements that cannot be categorized into one of the above elements or need to be separately identified due to high cost or high risk concerns within program management. Each additional element is to be clearly identified and defined.
1.4 | System Test and Evaluation | APPENDIX E: SEA SYSTEMS | K.3.4 System Test and Evaluation. The use of pilot, prototype, production, or specifically fabricated hardware/software to obtain or validate engineering data on the performance of the system during the developmental phase of the program. It also includes all effort associated with the development of any specialized tools or data in support of the system level test program. Includes, for example: a. Detailed planning, conduct, support, data reduction and reports (excluding the contract data requirements list data) from such testing, and test articles that are functionally configured to represent and test subsystems/components of the defense materiel end item being developed or produced b. Design and production of models, specimens, fixtures and instrumentation c. System level labs that integrate both hardware and software NOTE: Test articles that are functionally configured to represent and test the complete defense materiel end item being developed or produced, are excluded from this WBS element. Excludes, for example: a. All formal and informal testing up through the subsystem level, which can be associated with the hardware/software element acceptance testing NOTE: These excluded efforts are to be included with the appropriate hardware or software elements.
1.4.1 | Development Test and Evaluation | APPENDIX E: SEA SYSTEMS | K.3.4.1 Development Test and Evaluation. The test and evaluation conducted by the developing agency of the DoD component. It includes test and evaluation conducted to: a. Demonstrate that the engineering design and development process is complete b. Demonstrate that the design risks have been minimized c. Demonstrate that the system will meet specifications d. Assess the system’s military utility when introduced e. Determine whether the engineering design is supportable (practical, maintainable, safe, etc.) for operational use f. Provide test data with which to examine and evaluate trade-offs against specification requirements, life cycle cost, and schedule g. Perform the logistics testing efforts to evaluate the achievement of supportability goals, the adequacy of the support package for the system, (e.g., deliverable maintenance tools, test equipment, technical publications, maintenance instructions, and personnel skills and training requirements, etc.) Includes, for example: a. All contractor/system developer in-house effort b. Where applicable, models, tests and associated simulations (e.g., such as wind tunnel, static, drop, and fatigue); integration ground tests; test bed aircraft and associated support; qualification test and evaluation, development flight test, test instrumentation, environmental tests, ballistics, radiological, range and accuracy demonstrations, test facility operations, test equipment (including its support equipment), chase and calibrated pacer aircraft and support thereto, and logistics testing c. For aircraft; avionics integration test composed of the following: i. Test bench/laboratory, including design, acquisition, and installation of basic computers and test equipment that will provide an ability to simulate in the laboratory the operational environment of the avionics system/subsystem ii. Air vehicle equipment, consisting of the avionics and/or other air vehicle subsystem modules that are required by the bench/lab or flying test bed in order to provide a compatible airframe avionics system/subsystem for evaluation purposes iii. Flying test bed, including requirements analysis, design of modifications, lease or purchase of test bed aircraft, modification of aircraft, installation of avionics equipment and instrumentation, and checkout of an existing aircraft used essentially as a flying avionics laboratory iv. Avionics test program, consisting of the effort required to develop test plans/procedures, conduct tests, and analyze hardware and software test results to verify the avionics equipment’s operational capability and compatibility as an integrated air vehicle subsystem v. Software, referring to the effort required to design, code, de-bug, and document software programs necessary to direct the avionics integration test d. For engines: engine military qualification tests and engine preliminary flight rating tests e. For sea systems: model basin, hydrostatic, fatigue, shock, special sea tests and trials, etc., including the Expanded Ship Work Breakdown Structure (ESWBS), trials agenda preparation, data collection and analysis (842); dock and sea trials (9823); and hull vibration survey (9825) elements f. For missiles: test articles such as inert measurement vehicles, launch separation vehicles, separation and control test vehicles, boost test vehicles g. For ordnance: test articles such as ballistic test rounds, inert measurement rounds, dummy rounds, launch separation rounds, etc.
1.4.2 | Operational Test and Evaluation | APPENDIX E: SEA SYSTEMS | K.3.4.2 Operational Test and Evaluation. The test and evaluation conducted by agencies other than the developing command to assess the prospective system’s military utility, operational effectiveness, operational suitability, logistics supportability (including compatibility, inter-operability, reliability, maintainability, logistic requirements, etc.), cost of ownership, and need for any modifications. Includes, for example: a. Initial operational test and evaluation conducted during the development of a system b. Such tests as system demonstration, flight tests, sea trials, mobility demonstrations, on-orbit tests, spin demonstration, stability tests, qualification operational test and evaluation, etc., and support thereto, required to prove the operational capability of the deliverable system. c. Contractor support (e.g., technical assistance, maintenance, labor, material, etc.) consumed during this phase of testing d. Logistics testing efforts to evaluate the achievement of supportability goals and the adequacy of the support for the system (e.g., deliverable maintenance tools, test equipment, technical publications, maintenance instructions, personnel skills and training requirements, and software support facility/environment elements)
1.4.3 | Cybersecurity Test and Evaluation | APPENDIX E: SEA SYSTEMS | K.3.4.3 Cybersecurity System Test and Evaluation. The developmental test and evaluation and operational test and evaluation conducted and monitored by the developing agency of the DoD. The technical efforts of ensuring the confidentiality, integrity, and availability of information and technology by monitoring and defending against cyber (network) attacks. Includes, for example: a. Vulnerability scanning and interpretation b. Vulnerability testing and penetration testing (usually linked to patch management) c. Security information and event management d. Destructive and non-destructive exploitation e. Test conducted in an operational environment with certified red teams f. Cybersecurity compliance tracking and reporting g. Malware scanning, detection, and prevention services h. Security, IT certification, and accreditation compliance services
1.4.4 | Mock-ups/System Integration Labs (SILs) | APPENDIX E: SEA SYSTEMS | K.3.4.4 Mock-ups/System Integration Labs (SILs). The design engineering and production of system or subsystem mock-ups that have special contractual or engineering significance or that are not required solely for the conduct of one of the above elements of testing. SILs are often used in lieu of (or in addition to) mock-ups. SILs are risk reduction facilities where software and hardware can be developed, integrated, tested, and evaluated for both standalone functionality and/or interoperability prior to being fielded. Includes, for example: a. Hardware/lab equipment b. SIL Software (written to simulate the operating environment or written to operate the SIL)
1.4.5 | Test and Evaluation Support | APPENDIX E: SEA SYSTEMS | K.3.4.5 Test and Evaluation Support. The support elements necessary to operate and maintain, during test and evaluation, systems and subsystems, which are not consumed during the testing phase and are not allocated to a specific phase of testing. Includes, for example: a. Repairable spares, repair of reparables, repair parts, consumables, warehousing and distribution of spares and repair parts, test and support equipment, test bed vehicles, drones, surveillance aircraft/chase aircraft, tracking vessels, contractor technical support Excludes, for example: a. Operational and maintenance personnel, special fixtures, special instrumentation, etc., that are utilized and/or consumed in a single element of testing and that should be included under that element of testing
1.4.6 | Test Facilities | APPENDIX E: SEA SYSTEMS | K.3.4.6 Test Facilities. The special test facilities required for performance of the various developmental tests necessary to prove the design and reliability of the system or subsystem. Includes, for example: a. Test tank test fixtures, propulsion test fixtures, white rooms, test chambers, range/targeting facilities Excludes, for example: a. Brick and mortar-type facilities identified as industrial facilities
1.5 | Training | APPENDIX E: SEA SYSTEMS | K.3.5 Training. Deliverable training services, devices, accessories, aids, equipment, and parts used to facilitate instruction through which personnel will learn to operate and maintain the system with maximum efficiency. Includes, for example: a. All effort associated with the design, development, and production of deliverable training equipment and its associated software as well as the execution of training services Excludes, for example: a. Overall planning, management, and task analysis functions inherent in the WBS element systems engineering/program management
1.5.1 | Equipment | APPENDIX E: SEA SYSTEMS | K.3.5.1 Equipment. Distinctive deliverable end items of training equipment, assigned by either a contractor or military service, required to meet specific training objectives. Includes, for example: a. Operational and Maintenance Trainers and training equipment including items such as cutaways, mock-ups, and models (e.g. Operator Instructional Equipment, Maintainer Instructional Equipment)
1.5.1.1 | Operator Instructional Equipment | APPENDIX E: SEA SYSTEMS | [Blank]
1.5.1.2 | Maintainer Instructional Equipment | APPENDIX E: SEA SYSTEMS | [Blank]
1.5.2 | Services | APPENDIX E: SEA SYSTEMS | K.3.5.2 Services. Deliverable training services, accessories, and courseware aids necessary to accomplish the objectives of training. Includes, for example: a. Operational and Maintenance Training Services including courses, course materials; and curriculum required to design, execute, and produce a contractor developed training program and related software programs (e.g. operator instructional services, maintainer instructional services) Excludes, for example: a. Deliverable training data associated with support data (see Data Deliverables 1...n (Specify), Support Data)
1.5.2.1 | Operator Instructional Services | APPENDIX E: SEA SYSTEMS | [Blank]
1.5.2.2 | Maintainer Instructional Services | APPENDIX E: SEA SYSTEMS | [Blank]
1.5.3 | Facilities | APPENDIX E: SEA SYSTEMS | K.3.5.3 Facilities. The special construction necessary to accomplish training objectives. Includes, for example: a. Modification or rehabilitation of existing training facilities and infrastructure used to accomplish training objectives Excludes, for example: a. Installed equipment used to acquaint the trainee with the system or establish trainee proficiency b. The brick and mortar-type facilities identified as industrial facilities
1.5.4 | Training Software 1...n (Specify) | APPENDIX E: SEA SYSTEMS | K.3.5.4 Training Software Release 1...n (Specify). Updated/upgraded software for training purposes delivered to the field during the acquisition phase.
1.6 | Data | APPENDIX E: SEA SYSTEMS | K.3.6 Data. The deliverable data required to be listed on a contract data requirements list. Includes, for example: a. Only such effort that can be reduced or avoided if the data item is eliminated b. Government-peculiar data; acquiring, assembling, reproducing, packaging and shipping the data c. Transforming data into Government
1.6.1 | Data Deliverables 1...n (Specify) | APPENDIX E: SEA SYSTEMS | K.3.6.1 Data Deliverables 1...n (Specify). Deliverable data which provides technical, engineering, management, support, or other data required for contract delivery. Includes, for example: a. Technical Publications. Technical data, providing instructions for installation, operation, maintenance, training, and support, formatted into a technical manual. Data may be presented in any form regardless of the form or method of recording. Technical orders that meet the criteria of this definition may also be classified as technical manuals. For sea systems: Expanded Ship Work Breakdown Structure (ESWBS), technical manuals and other data (856) element. b. Engineering Data. Recorded scientific or technical information (regardless of the form or method of recording) including computer software documentation. Engineering data defines and documents an engineering design or product configuration (sufficient to allow duplication of the original items) and is used to support production, engineering, and logistics activities. For sea systems; Expanded Ship Work Breakdown Structure (ESWBS), design support, ship’s selected records (8302); design support, services, reproduction (8303); and engineering drawings and specifications (855) elements. c. Management Data. The data items necessary for configuration management, cost, schedule, contractual data management, program management, etc., required by the Government. For sea systems; Expanded Ship Work Breakdown Structure (ESWBS), contract data requirements (988) element. d. Support Data. The data items designed to document support planning in accordance with functional categories
1.6.2 | Data Repository | APPENDIX E: SEA SYSTEMS | K.3.6.2 Data Repository. The activity and enterprise data storage entity (or sometimes entities) for Government approved documents that are the property of the Government into which data has been specifically partitioned for analytical or reporting purposes. As custodian for the Government, the repository, authorized by approved change orders, maintains master documents at the latest approved revision level. Includes, for example: a. All effort necessary to maintain documents
1.6.3 | Data Rights 1...n (Specify) | APPENDIX E: SEA SYSTEMS | K.3.6.3 Data Rights 1...n (Specify). Government’s license rights of valuable intellectual property including technical data of any recorded information of a scientific or technical nature (e.g., product design or maintenance data, computer databases, and computer software documentation); and computer software including executable code, source code, code listings, design details, processes, flow charts, and related material. Includes, for example: a. Unlimited Rights. Developed exclusively at Government expense, and certain types of data (e.g., Form, Fit, and Function data (FFF); Operation, Maintenance, Installation, and Training (OMIT)). These rights involve the right to use, modify, reproduce, display, release, or disclose technical data in whole or in part, in any manner, and for any purpose whatsoever, and to have or authorize others to do so. b. Government Purpose Rights. This right involves the right to use, duplicate, or disclose technical data for Government purposes only, and to have or permit others to do so for Government purposes only. Government purposes include competitive procurement, but do not include the right to permit others to use the data for commercial purposes. c. Limited Rights. A limited rights agreement permits the Government to use proprietary technical data in whole or in part. It also means that the Government has to obtain the expressed permission of the party providing the technical data to release it, or disclose it, outside the Government.
1.7 | Peculiar Support Equipment | APPENDIX E: SEA SYSTEMS | K.3.7 Peculiar Support Equipment. The design, development, and production of those deliverable items and associated software required to support and maintain the system or portions of the system while the system is not directly engaged in the performance of its mission, and which are not common support equipment. Items should be designated by commodity subassembly (airframe, engine, avionics, etc.). Includes, for example: a. Vehicles, equipment, tools, etc., used to fuel, service, transport, hoist, repair, overhaul, assemble, disassemble, test, inspect, or otherwise maintain mission equipment b. Any production of duplicate or modified factory test or tooling equipment delivered to the Government for use in maintaining the system. (Factory test and tooling equipment initially used by the contractor in the production process but subsequently delivered to the Government will be included as cost of the item produced.) c. Any additional equipment or software required to maintain or modify the software portions of the system Excludes, for example: a. Overall planning, management, and task analysis functions inherent in the work breakdown structure elements Systems Engineering and Program Management b. Common support equipment, presently in the DoD inventory or commercially available, bought by the using command, not by the acquiring command
1.7.1 | Test and Measurement Equipment | APPENDIX E: SEA SYSTEMS | K.3.7.1 Test and Measurement Equipment. The peculiar or unique testing and measurement equipment that allows an operator or maintenance function to evaluate operational conditions of a system or equipment by performing specific diagnostics, screening, or quality assurance effort at an organizational, intermediate, or depot level of equipment support. Includes, for example: a. Test measurement and diagnostic equipment, precision measuring equipment, automatic test equipment, manual test equipment, automatic test systems, test program sets, appropriate interconnect devices, automated load modules, tapes, and related software, firmware and support hardware (power supply equipment, etc.) used at all levels of maintenance b. Packages that enable line or shop replaceable units, printed circuit boards, or similar items to be diagnosed using automatic test equipment
1.7.1.1 | Test and Measurement Equipment (Airframe/Hull/Vehicle) | APPENDIX E: SEA SYSTEMS | K.3.7.1.1 Test and Measurement Equipment (Airframe/Hull/Vehicle). This element captures the cost of the airframe, ship hull, or ground vehicle hull/frame related test and measurement equipment. Identify the related WBS subassemblies associated with the airframe/hull/vehicle. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested
1.7.1.2 | Test and Measurement Equipment (Propulsion) | APPENDIX E: SEA SYSTEMS | K.3.7.1.2 Test and Measurement Equipment (Propulsion). This element captures the cost of the propulsion system, engines, prime movers, turbines, etc. related test and measurement equipment. Identify the related WBS subassemblies associated with propulsion. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.7.1.3 | Test and Measurement Equipment (Electronics/Avionics) | APPENDIX E: SEA SYSTEMS | K.3.7.1.3 Test and Measurement Equipment (Electronics/Avionics). This element captures the cost of the electronics/avionics related test and measurement equipment. Identify the related WBS subassemblies associated with electronics/avionics. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.7.1.4 | Test and Measurement Equipment (Other Major Subsystem 1...n (Specify)) | APPENDIX E: SEA SYSTEMS | K.3.7.1.4 Test and Measurement Equipment (Other Major Subsystem 1...n (Specify)). This element captures the cost of other major subsystems (e.g., armament, weapons, vehicle subsystems, etc.) not captured above related test and measurement equipment. Identify the related WBS subassemblies associated with the other major subsystems. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.7.2 | Support and Handling Equipment | APPENDIX E: SEA SYSTEMS | K.3.7.2 Support and Handling Equipment. The peculiar or unique tools and handling equipment used for support of the mission system at an organizational, intermediate, or depot level Includes, for example: a. Ground support equipment, vehicular support equipment, powered support equipment, non-powered support equipment, munitions material handling equipment, materiel handling equipment, and software support equipment (hardware and software)
1.7.2.1 | Support and Handling Equipment (Airframe/Hull/Vehicle) | APPENDIX E: SEA SYSTEMS | K.3.7.2.1 Support and Handling Equipment (Airframe/Hull/Vehicle). This element captures the cost of the airframe, ship hull, or ground vehicle hull/frame related support and handling equipment. Identify the related WBS subassemblies associated with airframe/hull/vehicle. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.7.2.2 | Support and Handling Equipment (Propulsion) | APPENDIX E: SEA SYSTEMS | K.3.7.2.2 Support and Handling Equipment (Propulsion). This element captures the cost of propulsion related support and handling equipment. Identify the related WBS subassemblies associated with propulsion. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.7.2.3 | Support and Handling Equipment (Electronics/Avionics) | APPENDIX E: SEA SYSTEMS | K.3.7.2.3 Support and Handling Equipment (Electronics/Avionics). This element captures the cost of the electronics/avionics related support and handling equipment. Identify the related WBS subassemblies associated with electronics/avionics. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.7.2.4 | Support and Handling Equipment (Other Major Subsystem 1...n (Specify)) | APPENDIX E: SEA SYSTEMS | K.3.7.2.4 Support and Handling Equipment (Other Major Subsystem 1...n (Specify)). This element captures the cost of other major subsystems (e.g., armament, weapons, vehicle subsystems, etc.) not captured above related support and handling equipment. Identify the related WBS subassemblies associated with the other major subsystems. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.8 | Common Support Equipment | APPENDIX E: SEA SYSTEMS | K.3.8 Common Support Equipment. The items required to support and maintain the system or portions of the system while not directly engaged in the performance of its mission, and which are presently in the DoD inventory for support of other systems. Includes, for example: a. Acquisition of additional quantities of this equipment needed to support the item b. All efforts required to assure the availability of this equipment to support the item
1.8.1 | Test and Measurement Equipment | APPENDIX E: SEA SYSTEMS | K.3.8.1 Test and Measurement Equipment. The common testing and measurement equipment that allows an operator or maintenance function to evaluate operational conditions of a system or equipment by performing specific diagnostics, screening, or quality assurance effort at an organizational, intermediate, or depot level of equipment support. Includes, for example: a. Test measurement and diagnostic equipment, precision measuring equipment, automatic test equipment, manual test equipment, automatic test systems, test program sets, appropriate interconnect devices, automated load modules, tapes, and related software, firmware, and support hardware (power supply equipment, etc.) Used at all levels of maintenance b. Packages that enable line or shop replaceable units, printed circuit boards, or similar items to be diagnosed using automatic test equipment
1.8.1.1 | Test and Measurement Equipment (Airframe/Hull/Vehicle) | APPENDIX E: SEA SYSTEMS | K.3.8.1.1 Test and Measurement Equipment (Airframe/Hull/Vehicle). This element captures the cost of the airframe, ship hull, or ground vehicle hull/frame related test and measurement equipment. Identify the related WBS subassemblies associated with the airframe/hull/vehicle. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.8.1.2 | Test and Measurement Equipment (Propulsion) | APPENDIX E: SEA SYSTEMS | K.3.8.1.2 Test and Measurement Equipment (Propulsion). This element captures the cost of the propulsion system, engines, prime movers, turbines, etc. related test and measurement equipment. Identify the related WBS subassemblies associated with propulsion. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.8.1.3 | Test and Measurement Equipment (Electronics/Avionics) | APPENDIX E: SEA SYSTEMS | K.3.8.1.3 Test and Measurement Equipment (Electronics/Avionics). This element captures the cost of the electronics/avionics related test and measurement equipment. Identify the related WBS subassemblies associated with electronics/avionics. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.8.1.4 | Test and Measurement Equipment (Other Major Subsystem 1...n (Specify)) | APPENDIX E: SEA SYSTEMS | K.3.8.1.4 Test and Measurement Equipment (Other Major Subsystem 1...n (Specify)). This element captures the cost of other major subsystems (e.g., armament, weapons, vehicle subsystems, etc.) not captured above related test and measurement equipment. Identify the related WBS subassemblies associated with the other major subsystems. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.8.2 | Support and Handling Equipment | APPENDIX E: SEA SYSTEMS | K.3.8.2 Support and Handling Equipment. The common tools and handling equipment used for support of the mission system at an organizational, intermediate, or depot level Includes, for example: a. Ground support equipment, vehicular support equipment, powered support equipment, non-powered support equipment, munitions material handling equipment, materiel handling equipment, and software support equipment (hardware/software)
1.8.2.1 | Support and Handling Equipment (Airframe/Hull/Vehicle) | APPENDIX E: SEA SYSTEMS | K.3.8.2.1 Support and Handling Equipment (Airframe/Hull/Vehicle). This element captures the cost of the airframe, ship hull, or ground vehicle hull/frame related support and handling equipment. Identify the related WBS subassemblies associated with airframe/hull/vehicle. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.8.2.2 | Support and Handling Equipment (Propulsion) | APPENDIX E: SEA SYSTEMS | K.3.8.2.2 Support and Handling Equipment (Propulsion). This element captures the cost of propulsion related support and handling equipment. Identify the related WBS subassemblies associated with propulsion. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.8.2.3 | Support and Handling Equipment (Electronics/Avionics) | APPENDIX E: SEA SYSTEMS | K.3.8.2.3 Support and Handling Equipment (Electronics/Avionics). This element captures the cost of the electronics/avionics related support and handling equipment. Identify the related WBS subassemblies associated with electronics/avionics. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.8.2.4 | Support and Handling Equipment (Other Major Subsystem 1...n (Specify)) | APPENDIX E: SEA SYSTEMS | K.3.8.2.4 Support and Handling Equipment (Other Major Subsystem 1...n (Specify)). This element captures the cost of other major subsystems (e.g., armament, weapons, vehicle subsystems, etc.) not captured above related support and handling equipment. Identify the related WBS subassemblies associated with the other major subsystems. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.9 | Operational/Site Activation by Site 1...n (Specify) | APPENDIX E: SEA SYSTEMS | K.3.9 Operational/Site Activation by Site 1...n (Specify). The real estate, construction, conversion, utilities, and equipment to provide all facilities required to house, service, and launch prime mission equipment at the organizational and intermediate level. Includes, for example: a. Conversion of site, ship, or vehicle b. System assembly, checkout, and installation (of mission and support equipment) into site facility or ship to achieve operational status c. Contractor support in relation to operational/site activation
1.9.1 | System Assembly, Installation, and Checkout | APPENDIX E: SEA SYSTEMS | K.3.9.1 System Assembly, Installation, and Checkout. The materials and services involved in the assembly of mission equipment at the site. Includes, for example: a. Installation of mission and support equipment in the operations or support facilities and complete system checkout or shakedown to ensure operational status. Where appropriate, specify by site, ship, or vehicle. b. The efforts and activities associated with shipping the system from contractor facility to customer site. That site could be a DT&E site, an installation and checkout site, or any similar site that is outside the direct control of the contractor. Excludes, for example: a. Field team installation
1.9.2 | Contractor Technical Support | APPENDIX E: SEA SYSTEMS | K.3.9.2 Contractor Technical Support. The materials and services provided by the contractor related to activation. Includes, for example: a. Repair of reparables, standby services, and final turnover
1.9.3 | Site Construction | APPENDIX E: SEA SYSTEMS | K.3.9.3 Site Construction. Real estate, site planning and preparation, construction, and other special-purpose facilities necessary to achieve system operational status. Includes, for example: a. Construction of utilities, roads, and interconnecting cabling
1.9.4 | Site/Ship/Vehicle Conversion | APPENDIX E: SEA SYSTEMS | K.3.9.4 Site/Ship/Vehicle Conversion. The materials and services required to convert existing sites, ships, or vehicles to accommodate the mission equipment and selected support equipment directly related to the specific system. Includes, for example: a. Operations, support, and other special purpose facilities conversion necessary to achieve system operational status, e.g., launch. Where appropriate, specify by site, ship, or vehicle
1.9.5 | Interim Contractor Support (ICS) | APPENDIX E: SEA SYSTEMS | K.3.9.5 Interim Contractor Support (ICS). The effort required to provide temporary contractor support in lieu of a permanent support solution (organic or commercial) for a predetermined time, while a permanent support capability is put in place. Interim support is usually required for support of prototypes and early test and production assets during development and initial fielding (i.e., Initial Operating Capability (IOC)). Includes, for example: a. Providing life cycle logistics in accordance with the integrated product support (IPS) elements in support of the prime mission product. Excludes, for example: a. The development and production of the original prime mission product.
1.1 | Contractor Logistics Support (CLS) | APPENDIX E: SEA SYSTEMS | K.3.10 Contractor Logistics Support (CLS). Contracted weapon system sustainment including performance of maintenance and/or materiel management functions for a DoD weapon system by a commercial activity or contractor sustainment of a weapon system that is intended to start after a permanent decision is made to cover the operations and support efforts of the weapon system. CLS generally starts before FOC (final operating capability) or when performance based logistics (PBL) is implemented in the operating and support (O&S) phase. Includes, for example: a. Prime Mission Product (PMP) maintenance and refurbishment. The cost for this element includes maintenance and refurbishment (including the development and production) of existing operational systems. b. Support functions required to maintain the system, such as sustaining engineering, program management, logistics support, and supply chain management c. Test and evaluation for system and subsystem modifications d. Repair of reparable items; replacement of condemned items (including all PMP, support equipment, and training equipment) e. Operational, maintenance and other personnel required at the operational unit level f. Unit operations costs, including operating material and support services at the operating unit g. Installation and personnel support functions in support of the unit level manpower Excludes, for example: a. Does not include interim contractor support (ICS), a temporary measure for a system’s initial period of operation before a permanent form of support is in place. b. Contractor sustainment support for a specific sustainment task that a service would otherwise conduct itself.
1.11 | Industrial Facilities | APPENDIX E: SEA SYSTEMS | K.3.11 Industrial Facilities. The construction, conversion, or expansion of industrial facilities for production, inventory, and contractor depot maintenance required when that service is for the specific system. Includes, for example: a. Equipment acquisition or modernization, where applicable b. Maintenance of these facilities or equipment c. Industrial facilities for hazardous waste management to satisfy environmental standards Excludes, for example: a. Capital equipment
1.11.1 | Construction/Conversion/Expansion | APPENDIX E: SEA SYSTEMS | K.3.11.1 Construction/Conversion/Expansion. The real estate and preparation of system peculiar industrial facilities for production, inventory, depot maintenance, and other related activities.
1.11.2 | Equipment Acquisition or Modernization | APPENDIX E: SEA SYSTEMS | K.3.11.2 Equipment Acquisition or Modernization. The production equipment acquisition, modernization, or transfer of equipment for the particular system. This pertains to Government owned and leased equipment under facilities contract.
1.11.3 | Maintenance (Industrial Facilities) | APPENDIX E: SEA SYSTEMS | K.3.11.3 Maintenance (Industrial Facilities). The maintenance, preservation, and repair of industrial facilities and equipment.
1.12 | Initial Spares and Repair Parts | APPENDIX E: SEA SYSTEMS | K.3.12 Initial Spares and Repair Parts. The deliverable spare components, assemblies, and subassemblies used for initial replacement purposes in the materiel system equipment end item. Includes, for example: a. Repairable spares (reparables) and repair parts required as initial stockage to support and maintain newly fielded systems or subsystems during the initial phase of service, including pipeline and war reserve quantities, at all levels of maintenance and support. Lower level WBS breakouts should be by subsystem. b. Spare training and support equipment items c. The combination of resources, processes, planning, procedures, design, considerations, methods, and all hardware to ensure that all system, equipment, and support items are preserved, packaged, handled, and transported properly, including environmental considerations, equipment preservation for short and long term storage, and transportability. This includes requirements such as special environmentally controlled, shock isolated containers for transport to and from repair facilities and ensuring proper Care of Supplies in Storage (COSIS) program requirements are followed. Excludes, for example: a. Development test spares and spares provided specifically for use during installation, assembly, and checkout on site

## F
WBS # | WBS Nomenclature | Appendix | WBS Definition
1 | Space System | APPENDIX F: SPACE SYSTEMS
1.1 | SEIT/PM and Support Equipment | APPENDIX F: SPACE SYSTEMS
1.1.1 | Systems Engineering | APPENDIX F: SPACE SYSTEMS
1.1.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.1.3 | Program Management | APPENDIX F: SPACE SYSTEMS
1.1.4 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.2 | Space Vehicle 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.1 | SEIT/PM and Support Equipment | APPENDIX F: SPACE SYSTEMS
1.2.1.1 | Systems Engineering | APPENDIX F: SPACE SYSTEMS
1.2.1.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.2.1.3 | Program Management | APPENDIX F: SPACE SYSTEMS
1.2.1.4 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.2.2 | Bus | APPENDIX F: SPACE SYSTEMS
1.2.2.1 | SEIT/PM and Support Equipment | APPENDIX F: SPACE SYSTEMS
1.2.2.1.1 | Systems Engineering | APPENDIX F: SPACE SYSTEMS
1.2.2.1.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.2.2.1.3 | Program Management | APPENDIX F: SPACE SYSTEMS
1.2.2.1.4 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.2.2.2 | Structures and Mechanisms Subsystem (SMS) | APPENDIX F: SPACE SYSTEMS
1.2.2.2.1 | SEPM | APPENDIX F: SPACE SYSTEMS
1.2.2.2.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.2.2.2.3 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.2.2.2.4 | Structures | APPENDIX F: SPACE SYSTEMS
1.2.2.2.5 | Mechanisms and Pyrotechnics | APPENDIX F: SPACE SYSTEMS
1.2.2.2.6 | SMS Other | APPENDIX F: SPACE SYSTEMS
1.2.2.3 | Thermal Control Subsystem (TCS) | APPENDIX F: SPACE SYSTEMS
1.2.2.3.1 | SEPM | APPENDIX F: SPACE SYSTEMS
1.2.2.3.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.2.2.3.3 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.2.2.3.4 | Cryogenic Devices | APPENDIX F: SPACE SYSTEMS
1.2.2.3.5 | Liquid Loops | APPENDIX F: SPACE SYSTEMS
1.2.2.3.6 | Electric Coolers | APPENDIX F: SPACE SYSTEMS
1.2.2.3.7 | Heaters, Thermisters, and Thermostats | APPENDIX F: SPACE SYSTEMS
1.2.2.3.8 | Passive Devices | APPENDIX F: SPACE SYSTEMS
1.2.2.3.9 | TCS Other | APPENDIX F: SPACE SYSTEMS
1.2.2.4 | Electrical Power Subsystem (EPS) | APPENDIX F: SPACE SYSTEMS
1.2.2.4.1 | SEPM | APPENDIX F: SPACE SYSTEMS
1.2.2.4.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.2.2.4.3 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.2.2.4.4 | Solar Array | APPENDIX F: SPACE SYSTEMS
1.2.2.4.5 | Solar Array Positioner | APPENDIX F: SPACE SYSTEMS
1.2.2.4.6 | Radioisotope Thermionic Generator | APPENDIX F: SPACE SYSTEMS
1.2.2.4.7 | Other Power Sources | APPENDIX F: SPACE SYSTEMS
1.2.2.4.8 | Power Control, Switching, and Distribution Electronics | APPENDIX F: SPACE SYSTEMS
1.2.2.4.9 | Power Conditioning, Conversion, and Regulation | APPENDIX F: SPACE SYSTEMS
1.2.2.4.10 | Power Dissipation Devices | APPENDIX F: SPACE SYSTEMS
1.2.2.4.11 | Rechargeable Batteries | APPENDIX F: SPACE SYSTEMS
1.2.2.4.12 | Charge Control Electronics | APPENDIX F: SPACE SYSTEMS
1.2.2.4.13 | Harnesses and Cables | APPENDIX F: SPACE SYSTEMS
1.2.2.4.14 | EPS Other | APPENDIX F: SPACE SYSTEMS
1.2.2.5 | Attitude Control Subsystem (ACS) | APPENDIX F: SPACE SYSTEMS
1.2.2.5.1 | SEPM | APPENDIX F: SPACE SYSTEMS
1.2.2.5.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.2.2.5.3 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.2.2.5.4 | Star Tracker/Sensors 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.2.5.5 | Earth (Horizon) Sensors 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.2.5.6 | Sun Sensors 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.2.5.7 | Magnetometers | APPENDIX F: SPACE SYSTEMS
1.2.2.5.8 | Global Positioning System (GPS) Receiver | APPENDIX F: SPACE SYSTEMS
1.2.2.5.9 | Inertial Reference Unit (IRU)/Inertial Measurement Unit (IMU) 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.2.5.10 | Rate Gyros 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.2.5.11 | Accelerometers 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.2.5.12 | Bearing and Power Transfer Assembly (BAPTA) | APPENDIX F: SPACE SYSTEMS
1.2.2.5.13 | Attitude Control Wheels 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.2.5.14 | Magnetic Control Devices | APPENDIX F: SPACE SYSTEMS
1.2.2.5.15 | Spin Control Devices | APPENDIX F: SPACE SYSTEMS
1.2.2.5.16 | Control Electronics 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.2.5.17 | ACS Other | APPENDIX F: SPACE SYSTEMS
1.2.2.6 | Propulsion Subsystem 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.2.6.1 | SEPM | APPENDIX F: SPACE SYSTEMS
1.2.2.6.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.2.2.6.3 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.2.2.6.4 | Tanks 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.2.6.5 | Plumbing | APPENDIX F: SPACE SYSTEMS
1.2.2.6.6 | Thrusters 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.2.6.7 | Solid Rocket Motors | APPENDIX F: SPACE SYSTEMS
1.2.2.6.8 | Liquid Propellant and Pressurant | APPENDIX F: SPACE SYSTEMS
1.2.2.6.9 | Power Electronics | APPENDIX F: SPACE SYSTEMS
1.2.2.6.10 | Propulsion Other | APPENDIX F: SPACE SYSTEMS
1.2.2.7 | Telemetry, Tracking, and Command Subsystem (TT&C) | APPENDIX F: SPACE SYSTEMS
1.2.2.7.1 | SEPM | APPENDIX F: SPACE SYSTEMS
1.2.2.7.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.2.2.7.3 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.2.2.7.4 | Antennas | APPENDIX F: SPACE SYSTEMS
1.2.2.7.5 | Passive Signal Flow Control | APPENDIX F: SPACE SYSTEMS
1.2.2.7.6 | Transmitter/Receiver/Transceiver/Transponder 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.2.7.7 | Modulators/Demodulators/Modems | APPENDIX F: SPACE SYSTEMS
1.2.2.7.8 | Amplifiers | APPENDIX F: SPACE SYSTEMS
1.2.2.7.9 | Frequency Upconverter/Downconverter | APPENDIX F: SPACE SYSTEMS
1.2.2.7.10 | Computers and Processors 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.2.7.11 | Command/Telemetry Units 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.2.7.12 | Command Sensors 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.2.7.13 | Frequency and Timing | APPENDIX F: SPACE SYSTEMS
1.2.2.7.14 | Signal Conditioners | APPENDIX F: SPACE SYSTEMS
1.2.2.7.15 | Communications Security 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.2.7.16 | Data Storage, Handling and Interface 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.2.7.17 | TT&C Other | APPENDIX F: SPACE SYSTEMS
1.2.2.8 | Bus Flight Software | APPENDIX F: SPACE SYSTEMS
1.2.2.8.1 | SEPM | APPENDIX F: SPACE SYSTEMS
1.2.2.8.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.2.2.8.3 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.2.2.8.4 | CSCI 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.3 | SEIT/PM and Support Equipment (If applicable for integration of Multiple Payloads) | APPENDIX F: SPACE SYSTEMS
1.2.3.1 | Systems Engineering | APPENDIX F: SPACE SYSTEMS
1.2.3.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.2.3.3 | Program Management | APPENDIX F: SPACE SYSTEMS
1.2.3.4 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.2.4 | Payload 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.1 | SEIT/PM and Support Equipment | APPENDIX F: SPACE SYSTEMS
1.2.4.1.1 | Systems Engineering | APPENDIX F: SPACE SYSTEMS
1.2.4.1.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.2.4.1.3 | Program Management | APPENDIX F: SPACE SYSTEMS
1.2.4.1.4 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.2.4.2 | Structures and Mechanisms | APPENDIX F: SPACE SYSTEMS
1.2.4.2.1 | SEPM | APPENDIX F: SPACE SYSTEMS
1.2.4.2.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.2.4.2.3 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.2.4.2.4 | Structures | APPENDIX F: SPACE SYSTEMS
1.2.4.2.5 | Mechanisms and Pyrotechnics | APPENDIX F: SPACE SYSTEMS
1.2.4.2.6 | Structures and Mechanisms Other | APPENDIX F: SPACE SYSTEMS
1.2.4.3 | Thermal Control | APPENDIX F: SPACE SYSTEMS
1.2.4.3.1 | SEPM | APPENDIX F: SPACE SYSTEMS
1.2.4.3.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.2.4.3.3 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.2.4.3.4 | Cryogenic Devices | APPENDIX F: SPACE SYSTEMS
1.2.4.3.5 | Liquid Loops | APPENDIX F: SPACE SYSTEMS
1.2.4.3.6 | Electric Coolers | APPENDIX F: SPACE SYSTEMS
1.2.4.3.7 | Electric Heaters, Thermisters, and Thermostats | APPENDIX F: SPACE SYSTEMS
1.2.4.3.8 | Passive Devices | APPENDIX F: SPACE SYSTEMS
1.2.4.3.9 | Sun Shields | APPENDIX F: SPACE SYSTEMS
1.2.4.3.10 | Thermal Control Other | APPENDIX F: SPACE SYSTEMS
1.2.4.4 | Electrical Power | APPENDIX F: SPACE SYSTEMS
1.2.4.4.1 | SEPM | APPENDIX F: SPACE SYSTEMS
1.2.4.4.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.2.4.4.3 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.2.4.4.4 | Power Sources | APPENDIX F: SPACE SYSTEMS
1.2.4.4.5 | Power Control, Switching, and Distribution Electronics | APPENDIX F: SPACE SYSTEMS
1.2.4.4.6 | Power Conditioning, Conversion, and Regulation | APPENDIX F: SPACE SYSTEMS
1.2.4.4.7 | Harnesses and Cables | APPENDIX F: SPACE SYSTEMS
1.2.4.4.8 | Electrical Power Other | APPENDIX F: SPACE SYSTEMS
1.2.4.5 | Pointing, Command, and Control Interface System | APPENDIX F: SPACE SYSTEMS
1.2.4.5.1 | SEPM | APPENDIX F: SPACE SYSTEMS
1.2.4.5.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.2.4.5.3 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.2.4.5.4 | Computers and Processors 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.5.5 | Command/Telemetry Units 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.5.6 | Control Electronics 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.5.7 | Pointing Sensors 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.5.8 | Payload Positioners1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.5.9 | Security, Encryption and Decryption Devices 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.5.10 | Data Storage, Handling and Interface 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.5.11 | Multifunctional Digital Electronic Boxes 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.5.12 | Pointing, Command, and Control Interface Other | APPENDIX F: SPACE SYSTEMS
1.2.4.6 | Payload Antenna 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.6.1 | SEPM | APPENDIX F: SPACE SYSTEMS
1.2.4.6.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.2.4.6.3 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.2.4.6.4 | Structures and Mechanisms | APPENDIX F: SPACE SYSTEMS
1.2.4.6.5 | Antenna Positioners | APPENDIX F: SPACE SYSTEMS
1.2.4.6.6 | Reflector/Horn 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.6.7 | Feed 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.6.8 | Waveguide/Coax/Cabling | APPENDIX F: SPACE SYSTEMS
1.2.4.6.9 | Transmit/Receive Modules | APPENDIX F: SPACE SYSTEMS
1.2.4.6.10 | Antenna Other | APPENDIX F: SPACE SYSTEMS
1.2.4.7 | Payload Signal Electronics | APPENDIX F: SPACE SYSTEMS
1.2.4.7.1 | SEPM | APPENDIX F: SPACE SYSTEMS
1.2.4.7.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.2.4.7.3 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.2.4.7.4 | Passive Signal Flow Control | APPENDIX F: SPACE SYSTEMS
1.2.4.7.5 | Transmitter/Receiver/Transceiver/Transponder 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.7.6 | Modulators/Demodulators/Modems 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.7.7 | Multiplexers/Demultiplexers 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.7.8 | Amplifiers 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.7.9 | Frequency Upconverters/Downconverters 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.7.10 | Frequency and Timing 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.7.11 | Signal Conditioners 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.7.12 | Multifunctional Signal Electronic Boxes 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.7.13 | Signal Electronics Other | APPENDIX F: SPACE SYSTEMS
1.2.4.8 | Optical Assembly | APPENDIX F: SPACE SYSTEMS
1.2.4.8.1 | SEPM | APPENDIX F: SPACE SYSTEMS
1.2.4.8.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.2.4.8.3 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.2.4.8.4 | Structure/Outerbarrel/Cover | APPENDIX F: SPACE SYSTEMS
1.2.4.8.5 | Mirrors/Optics 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.8.6 | Aft Optics Assembly | APPENDIX F: SPACE SYSTEMS
1.2.4.8.7 | Alignment and Calibration 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.8.8 | Thermal 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.8.9 | Control Electronics 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.8.10 | Optical Assembly Other | APPENDIX F: SPACE SYSTEMS
1.2.4.9 | Sensor | APPENDIX F: SPACE SYSTEMS
1.2.4.9.1 | SEPM | APPENDIX F: SPACE SYSTEMS
1.2.4.9.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.2.4.9.3 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.2.4.9.4 | Enclosure 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.9.5 | Focal Plane Array 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.9.6 | Sensor Positioners 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.9.7 | Sensor Electronics 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.9.8 | Alignment and Calibration 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.9.9 | Magnetometer 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.9.10 | Spectrometer 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.9.11 | Radiometer 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.9.12 | Camera 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.9.13 | Sounder 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.9.14 | Other Sensor Types 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.9.15 | Mission Sensor Other | APPENDIX F: SPACE SYSTEMS
1.2.4.10 | Payload Flight Software | APPENDIX F: SPACE SYSTEMS
1.2.4.10.1 | SEPM | APPENDIX F: SPACE SYSTEMS
1.2.4.10.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.2.4.10.3 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.2.4.10.4 | CSCI 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.2.4.11 | Payload Other | APPENDIX F: SPACE SYSTEMS
1.2.5 | Booster Adapter | APPENDIX F: SPACE SYSTEMS
1.2.6 | Space Vehicle Storage | APPENDIX F: SPACE SYSTEMS
1.2.7 | Launch Systems Integration (LSI) | APPENDIX F: SPACE SYSTEMS
1.2.8 | Launch Operations | APPENDIX F: SPACE SYSTEMS
1.2.9 | Mission Operations Support | APPENDIX F: SPACE SYSTEMS
1.2.10 | Space Vehicle Other | APPENDIX F: SPACE SYSTEMS
1.3 | Ground Segment | APPENDIX F: SPACE SYSTEMS
1.3.1 | SEIT/PM and Support Equipment | APPENDIX F: SPACE SYSTEMS
1.3.1.1 | Systems Engineering | APPENDIX F: SPACE SYSTEMS
1.3.1.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.3.1.3 | Program Management | APPENDIX F: SPACE SYSTEMS
1.3.1.4 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.3.2 | Ground Functions 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.2.1 | SEIT/PM and Support Equipment | APPENDIX F: SPACE SYSTEMS
1.3.2.1.1 | Systems Engineering | APPENDIX F: SPACE SYSTEMS
1.3.2.1.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.3.2.1.3 | Program Management | APPENDIX F: SPACE SYSTEMS
1.3.2.1.4 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.3.2.2 | COTS Hardware 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.2.2.1 | SEPM | APPENDIX F: SPACE SYSTEMS
1.3.2.2.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.3.2.2.3 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.3.2.2.4 | Workstations 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.2.2.5 | Servers 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.2.2.6 | Storage and Archive 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.2.2.7 | Network Equipment | APPENDIX F: SPACE SYSTEMS
1.3.2.2.8 | Interface Equipment | APPENDIX F: SPACE SYSTEMS
1.3.2.2.9 | Security Encryption/Decryption 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.2.2.10 | Data Processing 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.2.2.11 | COTS Hardware Other | APPENDIX F: SPACE SYSTEMS
1.3.2.2.12 | Pre-Operations Maintenance 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.2.2.13 | Environments 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.2.3 | Custom Hardware 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.2.3.1 | SEPM | APPENDIX F: SPACE SYSTEMS
1.3.2.3.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.3.2.3.3 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.3.2.3.4 | Custom Hardware Configured Item 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.2.3.5 | Pre-Operations Maintenance 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.2.4 | Ground Function Software | APPENDIX F: SPACE SYSTEMS
1.3.2.4.1 | SEPM | APPENDIX F: SPACE SYSTEMS
1.3.2.4.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.3.2.4.3 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.3.2.4.4 | GF Software CSCI 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.2.4.5 | Pre-Operations Maintenance 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.2.5 | Pre-Operations Mission Support | APPENDIX F: SPACE SYSTEMS
1.3.3 | Ground Terminal/Gateway (GT) 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.3.1 | SEIT/PM and Support Equipment | APPENDIX F: SPACE SYSTEMS
1.3.3.1.1 | Systems Engineering | APPENDIX F: SPACE SYSTEMS
1.3.3.1.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.3.3.1.3 | Program Management | APPENDIX F: SPACE SYSTEMS
1.3.3.1.4 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.3.3.2 | Antenna 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.3.2.1 | SEPM | APPENDIX F: SPACE SYSTEMS
1.3.3.2.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.3.3.2.3 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.3.3.2.4 | Pedestal | APPENDIX F: SPACE SYSTEMS
1.3.3.2.5 | Radome | APPENDIX F: SPACE SYSTEMS
1.3.3.2.6 | Other Structure and Mechanisms | APPENDIX F: SPACE SYSTEMS
1.3.3.2.7 | Aperture | APPENDIX F: SPACE SYSTEMS
1.3.3.2.8 | Feed 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.3.2.9 | Waveguide/Coax/Cabling | APPENDIX F: SPACE SYSTEMS
1.3.3.2.10 | Antenna Other | APPENDIX F: SPACE SYSTEMS
1.3.3.3 | Optical Communication Assembly 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.3.3.1 | SEPM | APPENDIX F: SPACE SYSTEMS
1.3.3.3.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.3.3.3.3 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.3.3.3.4 | Structure/Outerbarrel/Cover | APPENDIX F: SPACE SYSTEMS
1.3.3.3.5 | Mirrors/Optics 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.3.3.6 | Aft Optics and Bench | APPENDIX F: SPACE SYSTEMS
1.3.3.3.7 | Alignment Sensors/Calibration | APPENDIX F: SPACE SYSTEMS
1.3.3.3.8 | Optical Assembly Other | APPENDIX F: SPACE SYSTEMS
1.3.3.4 | RF Electronics Band 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.3.4.1 | SEPM | APPENDIX F: SPACE SYSTEMS
1.3.3.4.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.3.3.4.3 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.3.3.4.4 | Passive Signal Flow Control | APPENDIX F: SPACE SYSTEMS
1.3.3.4.5 | Transmitter/Receiver/Transceiver/Transponder 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.3.4.6 | Modulators/Demodulators/Modems 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.3.4.7 | Multiplexers/Demultiplexers 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.3.4.8 | Power Amplifiers 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.3.4.9 | Frequency Upconverters/Downconverters 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.3.4.10 | Signal Conditioners 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.3.4.11 | Signal Electronic Boxes 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.3.4.12 | Focal Plane Array 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.3.4.13 | RF Electronics Other | APPENDIX F: SPACE SYSTEMS
1.3.3.5 | Timing | APPENDIX F: SPACE SYSTEMS
1.3.3.5.1 | SEPM | APPENDIX F: SPACE SYSTEMS
1.3.3.5.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.3.3.5.3 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.3.3.5.4 | Receiver | APPENDIX F: SPACE SYSTEMS
1.3.3.5.5 | Antenna 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.3.5.6 | Frequency and Timing Generators | APPENDIX F: SPACE SYSTEMS
1.3.3.5.7 | Amplifier and Distribution 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.3.5.8 | Timing Other | APPENDIX F: SPACE SYSTEMS
1.3.3.6 | Baseband-Network | APPENDIX F: SPACE SYSTEMS
1.3.3.6.1 | SEPM | APPENDIX F: SPACE SYSTEMS
1.3.3.6.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.3.3.6.3 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.3.3.6.4 | Switches/Hubs and Routers | APPENDIX F: SPACE SYSTEMS
1.3.3.6.5 | Network Interface and Other Hardware | APPENDIX F: SPACE SYSTEMS
1.3.3.6.6 | Modems | APPENDIX F: SPACE SYSTEMS
1.3.3.6.7 | Security/Encryption and Decryption Devices 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.3.6.8 | Baseband-Network Electronic Boxes 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.3.6.9 | Baseband-Network Other | APPENDIX F: SPACE SYSTEMS
1.3.3.7 | Monitor and Control Hardware | APPENDIX F: SPACE SYSTEMS
1.3.3.7.1 | SEPM | APPENDIX F: SPACE SYSTEMS
1.3.3.7.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.3.3.7.3 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.3.3.7.4 | Workstations 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.3.7.5 | Servers 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.3.7.6 | Storage and Archive 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.3.7.7 | Hardware Configured Item 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.3.8 | GT Software | APPENDIX F: SPACE SYSTEMS
1.3.3.8.1 | SEPM | APPENDIX F: SPACE SYSTEMS
1.3.3.8.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.3.3.8.3 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.3.3.8.4 | CSCI 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.3.9 | Pre-Operations Maintenance 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.3.10 | Pre-Operations Mission Support | APPENDIX F: SPACE SYSTEMS
1.3.4 | External Network (T-COMM) | APPENDIX F: SPACE SYSTEMS
1.3.4.1 | SEIT/PM and Support Equipment | APPENDIX F: SPACE SYSTEMS
1.3.4.1.1 | Systems Engineering | APPENDIX F: SPACE SYSTEMS
1.3.4.1.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.3.4.1.3 | Program Management | APPENDIX F: SPACE SYSTEMS
1.3.4.1.4 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.3.4.2 | Leased Circuit 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.4.3 | Purchased Circuits | APPENDIX F: SPACE SYSTEMS
1.3.4.3.1 | Purchased Circuit 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.4.3.2 | Pre-Operations Maintenance 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.5 | User Equipment | APPENDIX F: SPACE SYSTEMS
1.3.5.1 | SEIT/PM and Support Equipment | APPENDIX F: SPACE SYSTEMS
1.3.5.1.1 | Systems Engineering | APPENDIX F: SPACE SYSTEMS
1.3.5.1.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.3.5.1.3 | Program Management | APPENDIX F: SPACE SYSTEMS
1.3.5.1.4 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.3.5.2 | Equipment 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.5.2.1 | SEPM | APPENDIX F: SPACE SYSTEMS
1.3.5.2.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.3.5.2.3 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.3.5.2.4 | Hardware Configured Item 1…n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.5.2.5 | Equipment Software 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.5.3 | Pre-Operations Maintenance 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.6 | Facilities 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.6.1 | SEIT/PM and Support Equipment | APPENDIX F: SPACE SYSTEMS
1.3.6.1.1 | Systems Engineering | APPENDIX F: SPACE SYSTEMS
1.3.6.1.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.3.6.1.3 | Program Management | APPENDIX F: SPACE SYSTEMS
1.3.6.1.4 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.3.6.2 | Site Preparation | APPENDIX F: SPACE SYSTEMS
1.3.6.2.1 | SEPM | APPENDIX F: SPACE SYSTEMS
1.3.6.2.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.3.6.2.3 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.3.6.2.4 | Graded Land | APPENDIX F: SPACE SYSTEMS
1.3.6.2.5 | Roads | APPENDIX F: SPACE SYSTEMS
1.3.6.2.6 | Pads | APPENDIX F: SPACE SYSTEMS
1.3.6.2.7 | Retaining Walls/Fencing | APPENDIX F: SPACE SYSTEMS
1.3.6.2.8 | Utilities | APPENDIX F: SPACE SYSTEMS
1.3.6.2.9 | Site Preparation Other | APPENDIX F: SPACE SYSTEMS
1.3.6.3 | Landscape | APPENDIX F: SPACE SYSTEMS
1.3.6.4 | Buildings 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.6.4.1 | SEPM | APPENDIX F: SPACE SYSTEMS
1.3.6.4.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.3.6.4.3 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.3.6.4.4 | Foundation and Sub Structure | APPENDIX F: SPACE SYSTEMS
1.3.6.4.5 | Superstructure and Finishing | APPENDIX F: SPACE SYSTEMS
1.3.6.4.6 | Buildings Other | APPENDIX F: SPACE SYSTEMS
1.3.6.5 | Equipment and Building Fit Out 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.6.5.1 | SEPM | APPENDIX F: SPACE SYSTEMS
1.3.6.5.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.3.6.5.3 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.3.6.5.4 | Heating Venting and Air Conditioning (HVAC) | APPENDIX F: SPACE SYSTEMS
1.3.6.5.5 | Power Conditioning/UPS | APPENDIX F: SPACE SYSTEMS
1.3.6.5.6 | Network Wiring/Cable Trays | APPENDIX F: SPACE SYSTEMS
1.3.6.5.7 | Generators | APPENDIX F: SPACE SYSTEMS
1.3.6.5.8 | Computer Flooring | APPENDIX F: SPACE SYSTEMS
1.3.6.5.9 | Appliances | APPENDIX F: SPACE SYSTEMS
1.3.6.5.10 | Furniture | APPENDIX F: SPACE SYSTEMS
1.3.6.5.11 | Fire Protection | APPENDIX F: SPACE SYSTEMS
1.3.6.5.12 | Security Systems | APPENDIX F: SPACE SYSTEMS
1.3.6.5.13 | Equipment and Building Fit Out Other | APPENDIX F: SPACE SYSTEMS
1.3.6.6 | Pre-Operations Maintenance 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.7 | Vehicles and Shelters | APPENDIX F: SPACE SYSTEMS
1.3.7.1 | SEIT/PM and Support Equipment | APPENDIX F: SPACE SYSTEMS
1.3.7.1.1 | Systems Engineering | APPENDIX F: SPACE SYSTEMS
1.3.7.1.2 | Assembly, Integration and Test | APPENDIX F: SPACE SYSTEMS
1.3.7.1.3 | Program Management | APPENDIX F: SPACE SYSTEMS
1.3.7.1.4 | Support Equipment | APPENDIX F: SPACE SYSTEMS
1.3.7.2 | Vehicles 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.7.3 | Shelters 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.3.7.4 | Pre-Operations Maintenance 1...n (Specify) | APPENDIX F: SPACE SYSTEMS
1.4 | Orbital Transfer Vehicle (OTV) | APPENDIX F: SPACE SYSTEMS
1.5 | Launch Vehicle 1...n (Specify) | APPENDIX F: SPACE SYSTEMS

## G
WBS # | WBS Nomenclature | Appendix | WBS Definition
1 | Ground Vehicle System | APPENDIX G: GROUND VEHICLE SYSTEMS | G.4.1 Ground Vehicle System. The complex of vehicle electronics equipment, data, services, and facilities required to develop and produce a vehicle system with the capability to navigate over the surface or ground. Ground vehicle categories include vehicles primarily intended for general purpose applications and those intended for mating with specialized payloads. Includes, for example: a. Manned and unmanned cargo and logistics vehicles, trucks, mobile work units, and tactical vehicles b. Combat vehicles serving as armored weapons platforms, reconnaissance vehicles, and amphibians
1.1 | Family of Vehicles | APPENDIX G: GROUND VEHICLE SYSTEMS | G.4.2 Family of Vehicles. The mobile element of the system embodying means to meet the performing operational missions on its own. (Reference: Family of Systems description in Guidance, paragraph 3.2.2 for applications of the WBS when variants/family of vehicles exists.) Includes, for example: a. Means of propulsion and structure for adaptation of mission equipment or accommodations for disposable loads b. Design, development, and production of complete units (i.e., prototype or operationally configured units, which satisfy the requirements of their applicable specifications, regardless of end use)
1.1.1 | Lead Variant | APPENDIX G: GROUND VEHICLE SYSTEMS | G.4.2.1 Lead Variant. Family of vehicles typically have a significant amount of commonality between variants. When a family of vehicles is being developed it is more efficient to design a lead vehicle for the common design elements and then modify that design to be tailored to specific mission roles. The lead vehicle of the family of vehicle design may be referred to as a lead vehicle, lead variant, base vehicle or leader vehicle. For purposes of this Appendix, the term lead variant will be used. The lead variant is defined by the density or volume of the variant parts, parts commonality, parts percentage, or other like descriptions which make it the logical lead variant. Typically, this vehicle is the most common vehicle in the family of vehicles or used for generic purposes. When developing a WBS within the family of vehicles, the lead variant should be listed first in the listing of family of vehicle specific variant/configurations. For ground vehicle systems that are not a family of vehicles, the lead variant will be used for the only primary vehicle system and no Variant (2...n) WBS elements will be used.
1.1.1.1 | Lead Variant Integration, Assembly, Test, and Checkout | APPENDIX G: GROUND VEHICLE SYSTEMS | G.4.2.1.1 Lead Variant Integration, Assembly, Test, and Checkout. This element includes all effort of technical and functional activities associated with the design, development, and production of mating common surfaces, structures, equipment, parts, materials, and software required to assemble and test the vehicle subsystem parts and subsystems equipment (hardware/software) elements. Reference Appendix K: Common Elements, Work Breakdown Structure and Definitions for further detail.
1.1.1.2 | Hull/Frame/Body/Cab | APPENDIX G: GROUND VEHICLE SYSTEMS | G.4.2.1.2 Hull/Frame/Body/Cab. The vehicle’s primary load bearing component, which provides the structural integrity to withstand the operational loading stresses generated while traversing various terrain profiles (hull/frame), and (if applicable) the major component to be mated to a chassis to provide a complete vehicle having a defined mission capability (body/cab). Includes, for example: a. Simple wheeled vehicle frame or combat vehicle hull that satisfies the structural requirements including armor integral to the frame b. Structural subassemblies and appendages that attach directly to the primary structure c. Towing and lifting fittings, bumpers, hatches, and grilles d. Provision to accommodate other subsystems such as mountings for suspension, weapons, turret, truck body, cab, special equipment loads e. Accommodations for personnel, cargo, and such subsystems as need to be placed in proximity to operators Excludes, for example: a. Non-integral armor and radiological shielding (included in survivability element)
1.1.1.3 | System Survivability | APPENDIX G: GROUND VEHICLE SYSTEMS | G.4.2.1.3 System Survivability. The equipment required to maximize the survivability of the crew and the system. Includes, for example: a. Active protection systems and defensive aids for both short and long-range threats b. Radiological shielding for hull and turret. This includes supplemental ballistic protection, attachment approaches for external armor, liners, and behind armor debris shielding c. Signature management hardware associated with reducing system susceptibility and vulnerability d. Improvised explosive device (IED) countermeasure subsystems e. Fire detection and suppression f. Survivability systems control hardware. This includes electronics, sensors, and miscellaneous equipment that have functionality in more than one survivability WBS element g. Ballistic crew seats for crew protection during ballistic events h. Sensor subsystems, threat warning systems, and hostile weapon fire detection sensor subsystems i. Chemical, biological, radiological, and nuclear survivability j. Combat identification systems k. Anti-tamper systems
1.1.1.4 | Turret Assembly | APPENDIX G: GROUND VEHICLE SYSTEMS | G.4.2.1.4 Turret Assembly. The structure, including armor integral to the turret and equipment installations required to provide the fighting compartment element of combatant vehicles. Includes, for example: a. Turret rings, slip rings b. Attachments and appendages, such as hatches and cupolas c. Accommodations for personnel, weapons, and command and control d. Drive motors e. Turret drive stabilization system Excludes, for example: a. Non-integral armor and radiological shielding (included in survivability element)
1.1.1.5 | Suspension/Steering | APPENDIX G: GROUND VEHICLE SYSTEMS | G.4.2.1.5 Suspension/Steering. The means for generating tractive efforts, thrust, lift, and steering forces generally at or near the Earth’s surface and adapting the vehicle to the irregularities of the surface. Includes, for example: a. Wheels, tracks, brakes, and steering gears for traction and control functions b. Rudder thrust devices and trim vanes for amphibians c. Springs, shock absorbers, skirts, and other suspension members
1.1.1.6 | Vehicle Electronics | APPENDIX G: GROUND VEHICLE SYSTEMS | G.4.2.1.6 Vehicle Electronics. All electronic subsystems and components (hardware/software), distributed throughout the vehicle not directly attributable to other WBS Level 3 elements. Includes, for example: a. Computers and other devices for command and control b. Data control and distribution c. Controls and displays d. Power distribution and management e. Health management systems Excludes, for example: a. Hardware and software directly associated with other WBS elements NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.1.1.7 | Power Package/Drive Train | APPENDIX G: GROUND VEHICLE SYSTEMS | G.4.2.1.7 Power Package/Drive Train. The means for generating and delivering power. Includes, for example: a. Engine b. Engine-mounted auxiliaries such as air ducting and manifolds, controls and instrumentation, exhaust systems, and cooling means c. Power transport components as clutches, transmission, shafting assemblies, torque converters, differentials, final drivers, and power takeoffs d. Brakes and steering when integral to power transmission rather than in the suspension/steering element e. Hybrid electric drive systems f. Energy storage systems g. Raw power generators
1.1.1.8 | Auxiliary Automotive | APPENDIX G: GROUND VEHICLE SYSTEMS | G.4.2.1.8 Auxiliary Automotive. Hardware and software subsystems that provide services to all of the primary vehicle subsystems (as distinguished from the mission equipment subsystems). Includes, for example: a. On-board diagnostics/prognostics system not included in other subsystems b. Winch and power take-off, tools, and on-vehicle equipment c. Crew accommodations (when otherwise not provided for) d. Lighting systems Excludes, for example: a. Electrical subsystems and components that are now included in the vehicle electronics WBS element b. Fire detection and suppression system and controls associated with survivability
1.1.1.9 | Fire Control | APPENDIX G: GROUND VEHICLE SYSTEMS | G.4.2.1.9 Fire Control. The equipment (hardware and software) installed in the vehicle, which provides intelligence necessary for weapons delivery such as launching and firing. Includes, for example: a. Radars and other sensors necessary for search, recognition, and/or tracking b. Controls and displays c. Sights or scopes d. Range finders, computers, computer programs, gun drives, and stabilization systems NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.1.1.10 | Armament | APPENDIX G: GROUND VEHICLE SYSTEMS | G.4.2.1.10 Armament. The equipment (hardware and software) for vehicles to deliver fire on targets. Includes, for example: a. Main gun and secondary guns b. Missile launchers c. Non-lethal weapons d. Other offensive weapon systems Excludes, for example: a. Fire control systems
1.1.1.11 | Automatic Ammunition Handling | APPENDIX G: GROUND VEHICLE SYSTEMS | G.4.2.1.11 Automatic Ammunition Handling. The equipment (hardware and software) for selecting ammunition from a stored position in the vehicle, transferring it, and loading the armament system. Includes, for example: a. The means to eject spent cases and misfired rounds b. Ammunition storage racks, transfer/lift mechanisms, ramming and ejecting mechanisms, as well as specialized hydraulic and electrical controls
1.1.1.12 | Navigation and Remote Piloting Systems | APPENDIX G: GROUND VEHICLE SYSTEMS | G.4.2.1.12 Navigation and Remote Piloting Systems. The equipment (hardware and software) installed in the vehicle that enables the vehicle or its operators to plan and control vehicle speed and direction, determine vehicle location, plot the course of the vehicle and perform other mission functions. Includes, for example: a. Equipment that senses and processes imagery data such as vision systems, laser scanners, multiple sensor-fusion algorithms and processors, image-enhancement algorithms and processors, etc. b. Equipment that performs mobility intelligence analysis and planning functions such as automated route planners, image-understanding algorithms and processors, computer-aided-driving algorithms and processors, etc. c. Navigation systems such as dead reckoning, inertial, and global positioning systems d. Landmark recognition algorithms and processors NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.1.1.13 | Special Equipment | APPENDIX G: GROUND VEHICLE SYSTEMS | G.4.2.1.13 Special Equipment. The equipment (hardware and software) to be mated to a hull/frame/body/cab assembly to achieve a special mission capability. Includes, for example: a. All items required to convert basic vehicle configurations to special-purpose configurations b. Blades, booms, winches, robotic arms or manipulators, etc., to equip wreckers, recovery vehicles, supply vehicles and other field work units c. Furnishings and equipment for command, shop, medical and other special-purpose vehicles d. Specialized sensors not included elsewhere e. Mine detection, neutralization, and marking equipment
1.1.1.14 | Communications | APPENDIX G: GROUND VEHICLE SYSTEMS | G.4.2.1.14 Communications. The equipment (hardware and software) within the system for communicating information to systems and personnel interior and exterior to operating vehicles. Includes, for example: a. Radio frequency equipment, microwave and fiber optic communication links, networking equipment for multiple vehicle control, and intercom and external phone systems b. Means for supplementary communication like visual signaling devices c. Network integration equipment NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.1.1.15 | Lead Variant Software Release 1...n (Specify) | APPENDIX G: GROUND VEHICLE SYSTEMS | G.4.2.1.15 Lead Variant Software Release 1...n. All base variant vehicle software not associated with a specific Level 3 element. NOTE: Refer to Appendix B, Electronic/Generic Systems for further breakout and definitions for Software.
1.1.1.16 | Other Lead Variant Subsystems 1...n (Specify) | APPENDIX G: GROUND VEHICLE SYSTEMS | G.4.2.1.16 Other Lead Variant Subsystems 1...n (Specify). This element should be replaced with other product-oriented base variant subsystems that are either not listed above or that cannot be categorized into one of the above elements. Each additional element is to be clearly identified and defined. NOTE: If lower level information can be collected, use the structure and definitions in Appendix B, Electronic/Generic Systems.
1.1.2 | Variant 2...n (Specify) | APPENDIX G: GROUND VEHICLE SYSTEMS | G.4.2.2 Variant 2...n (Specify). This element includes all other units beyond the lead variant, within the family of vehicles and represents those characteristics unique to one or more other variants being developed. The work breakdown structure and definition for Variant 2...n is the same as those for the lead variant vehicle. (Note: These variants are derivatives of the base variant.)
1.1.3 | Equipment Kits 1...n (Specify) | APPENDIX G: GROUND VEHICLE SYSTEMS | G.4.2.3 Equipment Kits 1...n (Specify). An accessory which may be attached to a system to provide capability beyond that of the original design and is removable without detracting from the serviceability of the system. A kit can be installed during system build or after the system is fielded. Includes, for example: a. Non-integral armor (turret) b. Non-integral armor (hull/frame/body/cab)
1.2 | Secondary Vehicle | APPENDIX G: GROUND VEHICLE SYSTEMS | G.4.3 Secondary Vehicle. The vehicles required to supplement, expand, or otherwise contribute to the capabilities of primary vehicles to provide the vehicle system with the required operational characteristics. Secondary vehicles are not necessarily self-contained operational units capable of operating outside the system. Includes, for example: a. Cargo and tank trainers of truck-trailers systems; carriers and tanker units of articulated train-type systems; and transporters as employed in systems when the primary vehicle has limited roadability. NOTE: Work breakdown structure and definitions for Secondary Vehicle are the same as those for the lead variant vehicle.
1.3 | Systems Engineering | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.2 Systems Engineering. The technical and management efforts of directing and controlling a totally integrated engineering effort of a system or program. The following represent many, but not all, of the systems engineering efforts needed for a system or program. If required, one or more areas of effort (e.g., software systems engineering, cybersecurity, etc., may be identified at the next level below systems engineering. In those cases, the remaining totality of systems engineering efforts will be defined as “core systems engineering” at the level equal to the segregated items.
1.3.1 | Software Systems Engineering | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.2.1 Software Systems Engineering. The efforts which encompass software systems technologies, software engineering methods, and management techniques that improve the quality and delivery of software intensive systems and applications. Includes, for example: a. The application of a systematic, disciplined, quantifiable approach to the development and operations and support (O&S) of software b. The determination of software development or software test facility/environment requirements c. Application of systems engineering to software, that is, the systematic application of scientific and technical knowledge, methods, and experience to the design, implementation, testing, and documentation of software d. Analyzing the system requirements allocated to the software, developing the software requirements, developing the software architecture, designing the software, implementing the software in the code, integrating the software components, and testing the software to verify that the software satisfies the specified requirements allocated to the software component of a system or subsystem.
1.3.2 | Integrated Logistics Support (ILS) Systems Engineering | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.2.2 Integrated Logistics Support (ILS) Systems Engineering. The efforts to ensure the integrated planning and action of a number of disciplines in concert with one another to assure system availability. The planning of each element of ILS (e.g., integrated product support (IPS) elements) is developed in coordination with systems engineering and other efforts. Includes, for example: a. Product support management b. Design interface c. Sustaining engineering d. Supply support e. Maintenance planning and management f. Packaging, handling, storage, and transportation g. Technical data h. Support equipment i. Training and training support j. Manpower and personnel k. Facilities and infrastructure l. Computer resources
1.3.3 | Cybersecurity Systems Engineering | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.2.3 Cybersecurity Systems Engineering. The efforts to apply scientific and engineering principles to identify security vulnerabilities and minimize or contain risks associated with these vulnerabilities. Includes, for example: a. Cybersecurity requirements evaluation b. Cyberattack surface characterization c. Cooperative vulnerability identification d. Vulnerability analysis e. System cross-functional cyber analysis f. Advise on RMF compliance tasks/documents (security assessment plan, etc.) g. Security configuration management (assess planned services for risk and impact) h. Develop system-level security architecture i. Design, develop, and implement system security measures that meets technical requirements j. Develop and implement specific security countermeasures for the system k. Develop approaches to mitigate system vulnerabilities l. Ensure the design of hardware, operating systems, and software applications adequately address cybersecurity requirements for the system
1.3.4 | Core Systems Engineering | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.2.4 Core Systems Engineering. The technical and management efforts that establish the technical framework for delivering materiel capabilities and ensure the effective development and delivery of capability through the implementation of a balanced approach with respect to cost, schedule, performance, and risk. This effort uses integrated, disciplined and consistent systems engineering activities and processes for development of resilient systems that are trusted, assured and easily modified. Systems engineering is composed of 16 processes: eight technical processes and eight technical management processes. These processes provide a structured approach to increasing the technical maturity of a system and increasing the likelihood that the capability being developed balances mission performance with cost, schedule, risk, and design constraints. To fulfill that purpose, a program implements the systems engineering technical processes to support the iterative maturation of the system solution or operational need. The technical processes enable the systems engineering team to ensure that the delivered capability accurately reflects the operational needs of the stakeholders. The technical processes include top down design processes such as stakeholder requirements definition, requirements analysis, and architecture design, as well as bottom-up realization processes such as transition, validation, verification, integration, and implementation. The eight technical management processes are implemented across the acquisition life cycle and provide insight and control to assist the program manager and systems engineer to meet performance, schedule, and cost goals. The eight technical processes closely align with the acquisition life cycle phases and include the top-down design processes and bottom-up realization processes that support transformation of operational needs into operational capabilities. The eight technical management processes are: decision analysis, technical planning, technical assessment, requirements management, risk management, configuration management, technical data management, and interface management. Also included are specialty engineering disciplines which bring together the hardware, software, and human elements of the systems. Includes, for example: a. System safety which is applicable to most DoD systems; this reflects the ubiquitous nature of software-driven functions, network connectivity, and systems of systems; specific certifications include safety, security, cybersecurity and airworthiness b. Reliability and maintainability – ensure that design interface and integration of the quantitative systems engineering design characteristics (i.e., reliability, maintainability, etc.) with the functional integrated product support elements c. Quality – ensures configuration item level requirements for the systems and subsystems meet critical functions and key quality attributes. d. Manufacturing and producibility – ensure manufacturing and producibility readiness, processes assessed and demonstrated, and risks identified, managed and reduced throughout the program’s life cycle e. Human systems integration – optimize total system performance and total ownership costs, while ensuring that the system is designed, operated, and maintained to effectively provide the user with the ability to complete their mission; ensure ergonomics, human factors engineering, and cognitive engineering is employed to provide for effective human-machine interfaces; define the human performance characteristics of the user based on the system description, projected characteristics of target occupational specialties, and recruitment and retention trends; establish requirements for the physical environment; determine the most efficient and cost-effective mix of DoD manpower and contract support; develop training options for operators, maintenance and support personnel; ensure that appropriate environmental safety and occupational health; assess risks to personnel and address, in terms of system design, protection from direct threat events and accidents (such as chemical, biological, and nuclear threats). f. System of systems (SoS) and system level architecting, modeling and simulation, verification and validation and external interface definition and management g. For sea systems; the Expanded Ship Work Breakdown Structure (ESWBS), configuration management (811), human factors (892), standardization (893), value engineering (894), and reliability and maintainability (895) elements Excludes, for example: a. Actual design engineering and the production engineering directly related to the WBS element with which it is associated b. Any systems engineering efforts that are called out in software systems engineering, ILS systems engineering, cybersecurity systems engineering, or “other” systems engineering effort separately identified in the WBS.
1.3.5 | Other Systems Engineering 1...n (Specify) | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.2.5 Other Systems Engineering 1...n (Specify). This element should be replaced with other systems engineering elements that cannot be categorized into one of the above elements or need to be separately identified due to high cost, high risk concerns within systems engineering. Each additional element is to be clearly identified and defined.
1.4 | Program Management | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.3 Program Management. The business and administrative planning, organizing, directing, coordinating, controlling, and approval actions designated to accomplish overall program objectives, which are not associated with specific hardware elements and are not included in systems engineering. If required, one or more areas of effort (e.g., software program management, cybersecurity program management, etc.,) may be identified at the next level below program management. In those cases, the remaining totality of program management efforts will be defined as “core program management” at the level equal to the segregated items.
1.4.1 | Software Program Management | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.3.1 Software Program Management. The software program management encompasses the management of the full software life cycle, from conception to deployment. The function focuses at the system level of applying business and project management skills needed to produce high-quality software products. Includes, for example: a. Overseeing requirements analysis and design, and effective implementation and delivery of all fully-tested software b. Ensure sufficient end-user involvement c. Maintain communication among customers, developers, users, and project managers d. Establish realistic or articulated project goals e. Develop accurate estimates of needed resources f. Define system requirements and specifications g. Assure reporting of the project’s status h. Proper management of risks i. Ensure the use of mature technology and handle the project’s complexity
1.4.2 | Integrated Logistics Support (ILS) Program Management | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.3.2 Integrated Logistics Support Program Management. The efforts to manage the planning and execution of the ILS disciplines to assure system acquisition logistics availability. Includes, for example: a. Support element management, defined as the logistics tasks management effort and technical control, and the business management of the support elements. The logistics management function encompasses the support evaluation and supportability assurance required to produce an affordable and supportable defense materiel system. b. Planning and management of all the functions of logistics. Examples are: maintenance support planning and support facilities planning; other support requirements determination; support equipment requirements determination; supply support; packaging, handling, storage, and transportation; provisioning requirements determination and planning; training system requirements determination; computer resource determination; organizational, intermediate, and depot maintenance determination management; and data management
1.4.3 | Cybersecurity Management | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.3.3 Cybersecurity Program Management. The management and understanding of cybersecurity program and its ramifications across the organization (only if costs are collected in this manner). Includes, for example: a. Overseeing cybersecurity risk assessment, management, and mediation b. Cybersecurity threat vectors and mitigation processes c. Ensuring design and management of secure information systems d. Emerging tools and resources for organizational and platform security
1.4.4 | Core Program Management | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.3.4 Core Program Management. The efforts to understand and manage multiple discipline areas in order the successfully accomplish program objectives for development, production, and sustainment of systems to meet the user’s operational needs Includes, for example: a. Cost, schedule, performance measurement management, warranty administration, contract management, vendor liaison, subcontract management, etc. b. For sea systems; the Expanded Ship Work Breakdown Structure (ESWBS), project management (897); data management (896); and supply support (853) elements Excludes, for example: a. Actual program management directly related to another WBS element b. Any program management efforts that are called out in software program management, cybersecurity program management, or “other” program management effort separately identified in the WBS.
1.4.5 | Other Program Management 1...n (Specify) | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.3.5 Other Program Management 1...n (Specify). This element should be replaced with other program management elements that cannot be categorized into one of the above elements or need to be separately identified due to high cost or high risk concerns within program management. Each additional element is to be clearly identified and defined.
1.5 | System Test and Evaluation | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.4 System Test and Evaluation. The use of pilot, prototype, production, or specifically fabricated hardware/software to obtain or validate engineering data on the performance of the system during the developmental phase of the program. It also includes all effort associated with the development of any specialized tools or data in support of the system level test program. Includes, for example: a. Detailed planning, conduct, support, data reduction and reports (excluding the contract data requirements list data) from such testing, and test articles that are functionally configured to represent and test subsystems/components of the defense materiel end item being developed or produced b. Design and production of models, specimens, fixtures and instrumentation c. System level labs that integrate both hardware and software NOTE: Test articles that are functionally configured to represent and test the complete defense materiel end item being developed or produced, are excluded from this WBS element. Excludes, for example: a. All formal and informal testing up through the subsystem level, which can be associated with the hardware/software element acceptance testing NOTE: These excluded efforts are to be included with the appropriate hardware or software elements.
1.5.1 | Development Test and Evaluation | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.4.1 Development Test and Evaluation. The test and evaluation conducted by the developing agency of the DoD component. It includes test and evaluation conducted to: a. Demonstrate that the engineering design and development process is complete b. Demonstrate that the design risks have been minimized c. Demonstrate that the system will meet specifications d. Assess the system’s military utility when introduced e. Determine whether the engineering design is supportable (practical, maintainable, safe, etc.) for operational use f. Provide test data with which to examine and evaluate trade-offs against specification requirements, life cycle cost, and schedule g. Perform the logistics testing efforts to evaluate the achievement of supportability goals, the adequacy of the support package for the system, (e.g., deliverable maintenance tools, test equipment, technical publications, maintenance instructions, and personnel skills and training requirements, etc.) Includes, for example: a. All contractor/system developer in-house effort b. Where applicable, models, tests and associated simulations (e.g., such as wind tunnel, static, drop, and fatigue); integration ground tests; test bed aircraft and associated support; qualification test and evaluation, development flight test, test instrumentation, environmental tests, ballistics, radiological, range and accuracy demonstrations, test facility operations, test equipment (including its support equipment), chase and calibrated pacer aircraft and support thereto, and logistics testing c. For aircraft; avionics integration test composed of the following: i. Test bench/laboratory, including design, acquisition, and installation of basic computers and test equipment that will provide an ability to simulate in the laboratory the operational environment of the avionics system/subsystem ii. Air vehicle equipment, consisting of the avionics and/or other air vehicle subsystem modules that are required by the bench/lab or flying test bed in order to provide a compatible airframe avionics system/subsystem for evaluation purposes iii. Flying test bed, including requirements analysis, design of modifications, lease or purchase of test bed aircraft, modification of aircraft, installation of avionics equipment and instrumentation, and checkout of an existing aircraft used essentially as a flying avionics laboratory iv. Avionics test program, consisting of the effort required to develop test plans/procedures, conduct tests, and analyze hardware and software test results to verify the avionics equipment’s operational capability and compatibility as an integrated air vehicle subsystem v. Software, referring to the effort required to design, code, de-bug, and document software programs necessary to direct the avionics integration test d. For engines: engine military qualification tests and engine preliminary flight rating tests e. For sea systems: model basin, hydrostatic, fatigue, shock, special sea tests and trials, etc., including the Expanded Ship Work Breakdown Structure (ESWBS), trials agenda preparation, data collection and analysis (842); dock and sea trials (9823); and hull vibration survey (9825) elements f. For missiles: test articles such as inert measurement vehicles, launch separation vehicles, separation and control test vehicles, boost test vehicles g. For ordnance: test articles such as ballistic test rounds, inert measurement rounds, dummy rounds, launch separation rounds, etc.
1.5.2 | Operational Test and Evaluation | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.4.2 Operational Test and Evaluation. The test and evaluation conducted by agencies other than the developing command to assess the prospective system’s military utility, operational effectiveness, operational suitability, logistics supportability (including compatibility, inter-operability, reliability, maintainability, logistic requirements, etc.), cost of ownership, and need for any modifications. Includes, for example: a. Initial operational test and evaluation conducted during the development of a system b. Such tests as system demonstration, flight tests, sea trials, mobility demonstrations, on-orbit tests, spin demonstration, stability tests, qualification operational test and evaluation, etc., and support thereto, required to prove the operational capability of the deliverable system. c. Contractor support (e.g., technical assistance, maintenance, labor, material, etc.) consumed during this phase of testing d. Logistics testing efforts to evaluate the achievement of supportability goals and the adequacy of the support for the system (e.g., deliverable maintenance tools, test equipment, technical publications, maintenance instructions, personnel skills and training requirements, and software support facility/environment elements)
1.5.3 | Cybersecurity Test and Evaluation | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.4.3 Cybersecurity System Test and Evaluation. The developmental test and evaluation and operational test and evaluation conducted and monitored by the developing agency of the DoD. The technical efforts of ensuring the confidentiality, integrity, and availability of information and technology by monitoring and defending against cyber (network) attacks. Includes, for example: a. Vulnerability scanning and interpretation b. Vulnerability testing and penetration testing (usually linked to patch management) c. Security information and event management d. Destructive and non-destructive exploitation e. Test conducted in an operational environment with certified red teams f. Cybersecurity compliance tracking and reporting g. Malware scanning, detection, and prevention services h. Security, IT certification, and accreditation compliance services
1.5.4 | Mock-ups/System Integration Labs (SILs) | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.4.4 Mock-ups/System Integration Labs (SILs). The design engineering and production of system or subsystem mock-ups that have special contractual or engineering significance or that are not required solely for the conduct of one of the above elements of testing. SILs are often used in lieu of (or in addition to) mock-ups. SILs are risk reduction facilities where software and hardware can be developed, integrated, tested, and evaluated for both standalone functionality and/or interoperability prior to being fielded. Includes, for example: a. Hardware/lab equipment b. SIL Software (written to simulate the operating environment or written to operate the SIL)
1.5.5 | Test and Evaluation Support | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.4.5 Test and Evaluation Support. The support elements necessary to operate and maintain, during test and evaluation, systems and subsystems, which are not consumed during the testing phase and are not allocated to a specific phase of testing. Includes, for example: a. Repairable spares, repair of reparables, repair parts, consumables, warehousing and distribution of spares and repair parts, test and support equipment, test bed vehicles, drones, surveillance aircraft/chase aircraft, tracking vessels, contractor technical support Excludes, for example: a. Operational and maintenance personnel, special fixtures, special instrumentation, etc., that are utilized and/or consumed in a single element of testing and that should be included under that element of testing
1.5.6 | Test Facilities | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.4.6 Test Facilities. The special test facilities required for performance of the various developmental tests necessary to prove the design and reliability of the system or subsystem. Includes, for example: a. Test tank test fixtures, propulsion test fixtures, white rooms, test chambers, range/targeting facilities Excludes, for example: a. Brick and mortar-type facilities identified as industrial facilities
1.6 | Training | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.5 Training. Deliverable training services, devices, accessories, aids, equipment, and parts used to facilitate instruction through which personnel will learn to operate and maintain the system with maximum efficiency. Includes, for example: a. All effort associated with the design, development, and production of deliverable training equipment and its associated software as well as the execution of training services Excludes, for example: a. Overall planning, management, and task analysis functions inherent in the WBS element systems engineering/program management
1.6.1 | Equipment | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.5.1 Equipment. Distinctive deliverable end items of training equipment, assigned by either a contractor or military service, required to meet specific training objectives. Includes, for example: a. Operational and Maintenance Trainers and training equipment including items such as cutaways, mock-ups, and models (e.g. Operator Instructional Equipment, Maintainer Instructional Equipment)
1.6.1.1 | Operator Instructional Equipment | APPENDIX G: GROUND VEHICLE SYSTEMS | [Blank]
1.6.1.2 | Maintainer Instructional Equipment | APPENDIX G: GROUND VEHICLE SYSTEMS | [Blank]
1.6.2 | Services | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.5.2 Services. Deliverable training services, accessories, and courseware aids necessary to accomplish the objectives of training. Includes, for example: a. Operational and Maintenance Training Services including courses, course materials; and curriculum required to design, execute, and produce a contractor developed training program and related software programs (e.g. operator instructional services, maintainer instructional services) Excludes, for example: a. Deliverable training data associated with support data (see Data Deliverables 1...n (Specify), Support Data)
1.6.2.1 | Operator Instructional Services | APPENDIX G: GROUND VEHICLE SYSTEMS | [Blank]
1.6.2.2 | Maintainer Instructional Services | APPENDIX G: GROUND VEHICLE SYSTEMS | [Blank]
1.6.3 | Facilities | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.5.3 Facilities. The special construction necessary to accomplish training objectives. Includes, for example: a. Modification or rehabilitation of existing training facilities and infrastructure used to accomplish training objectives Excludes, for example: a. Installed equipment used to acquaint the trainee with the system or establish trainee proficiency b. The brick and mortar-type facilities identified as industrial facilities
1.6.4 | Training Software 1...n (Specify) | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.5.4 Training Software Release 1...n (Specify). Updated/upgraded software for training purposes delivered to the field during the acquisition phase.
1.7 | Data | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.6 Data. The deliverable data required to be listed on a contract data requirements list. Includes, for example: a. Only such effort that can be reduced or avoided if the data item is eliminated b. Government-peculiar data; acquiring, assembling, reproducing, packaging and shipping the data c. Transforming data into Government
1.7.1 | Data Deliverables 1...n (Specify) | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.6.1 Data Deliverables 1...n (Specify). Deliverable data which provides technical, engineering, management, support, or other data required for contract delivery. Includes, for example: a. Technical Publications. Technical data, providing instructions for installation, operation, maintenance, training, and support, formatted into a technical manual. Data may be presented in any form regardless of the form or method of recording. Technical orders that meet the criteria of this definition may also be classified as technical manuals. For sea systems: Expanded Ship Work Breakdown Structure (ESWBS), technical manuals and other data (856) element. b. Engineering Data. Recorded scientific or technical information (regardless of the form or method of recording) including computer software documentation. Engineering data defines and documents an engineering design or product configuration (sufficient to allow duplication of the original items) and is used to support production, engineering, and logistics activities. For sea systems; Expanded Ship Work Breakdown Structure (ESWBS), design support, ship’s selected records (8302); design support, services, reproduction (8303); and engineering drawings and specifications (855) elements. c. Management Data. The data items necessary for configuration management, cost, schedule, contractual data management, program management, etc., required by the Government. For sea systems; Expanded Ship Work Breakdown Structure (ESWBS), contract data requirements (988) element. d. Support Data. The data items designed to document support planning in accordance with functional categories
1.7.2 | Data Repository | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.6.2 Data Repository. The activity and enterprise data storage entity (or sometimes entities) for Government approved documents that are the property of the Government into which data has been specifically partitioned for analytical or reporting purposes. As custodian for the Government, the repository, authorized by approved change orders, maintains master documents at the latest approved revision level. Includes, for example: a. All effort necessary to maintain documents
1.7.3 | Data Rights 1...n (Specify) | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.6.3 Data Rights 1...n (Specify). Government’s license rights of valuable intellectual property including technical data of any recorded information of a scientific or technical nature (e.g., product design or maintenance data, computer databases, and computer software documentation); and computer software including executable code, source code, code listings, design details, processes, flow charts, and related material. Includes, for example: a. Unlimited Rights. Developed exclusively at Government expense, and certain types of data (e.g., Form, Fit, and Function data (FFF); Operation, Maintenance, Installation, and Training (OMIT)). These rights involve the right to use, modify, reproduce, display, release, or disclose technical data in whole or in part, in any manner, and for any purpose whatsoever, and to have or authorize others to do so. b. Government Purpose Rights. This right involves the right to use, duplicate, or disclose technical data for Government purposes only, and to have or permit others to do so for Government purposes only. Government purposes include competitive procurement, but do not include the right to permit others to use the data for commercial purposes. c. Limited Rights. A limited rights agreement permits the Government to use proprietary technical data in whole or in part. It also means that the Government has to obtain the expressed permission of the party providing the technical data to release it, or disclose it, outside the Government.
1.8 | Peculiar Support Equipment | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.7 Peculiar Support Equipment. The design, development, and production of those deliverable items and associated software required to support and maintain the system or portions of the system while the system is not directly engaged in the performance of its mission, and which are not common support equipment. Items should be designated by commodity subassembly (airframe, engine, avionics, etc.). Includes, for example: a. Vehicles, equipment, tools, etc., used to fuel, service, transport, hoist, repair, overhaul, assemble, disassemble, test, inspect, or otherwise maintain mission equipment b. Any production of duplicate or modified factory test or tooling equipment delivered to the Government for use in maintaining the system. (Factory test and tooling equipment initially used by the contractor in the production process but subsequently delivered to the Government will be included as cost of the item produced.) c. Any additional equipment or software required to maintain or modify the software portions of the system Excludes, for example: a. Overall planning, management, and task analysis functions inherent in the work breakdown structure elements Systems Engineering and Program Management b. Common support equipment, presently in the DoD inventory or commercially available, bought by the using command, not by the acquiring command
1.8.1 | Test and Measurement Equipment | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.7.1 Test and Measurement Equipment. The peculiar or unique testing and measurement equipment that allows an operator or maintenance function to evaluate operational conditions of a system or equipment by performing specific diagnostics, screening, or quality assurance effort at an organizational, intermediate, or depot level of equipment support. Includes, for example: a. Test measurement and diagnostic equipment, precision measuring equipment, automatic test equipment, manual test equipment, automatic test systems, test program sets, appropriate interconnect devices, automated load modules, tapes, and related software, firmware and support hardware (power supply equipment, etc.) used at all levels of maintenance b. Packages that enable line or shop replaceable units, printed circuit boards, or similar items to be diagnosed using automatic test equipment
1.8.1.1 | Test and Measurement Equipment (Airframe/Hull/Vehicle) | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.7.1.1 Test and Measurement Equipment (Airframe/Hull/Vehicle). This element captures the cost of the airframe, ship hull, or ground vehicle hull/frame related test and measurement equipment. Identify the related WBS subassemblies associated with the airframe/hull/vehicle. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested
1.8.1.2 | Test and Measurement Equipment (Propulsion) | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.7.1.2 Test and Measurement Equipment (Propulsion). This element captures the cost of the propulsion system, engines, prime movers, turbines, etc. related test and measurement equipment. Identify the related WBS subassemblies associated with propulsion. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.8.1.3 | Test and Measurement Equipment (Electronics/Avionics) | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.7.1.3 Test and Measurement Equipment (Electronics/Avionics). This element captures the cost of the electronics/avionics related test and measurement equipment. Identify the related WBS subassemblies associated with electronics/avionics. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.8.1.4 | Test and Measurement Equipment (Other Major Subsystems 1...n (Specify)) | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.7.1.4 Test and Measurement Equipment (Other Major Subsystem 1...n (Specify)). This element captures the cost of other major subsystems (e.g., armament, weapons, vehicle subsystems, etc.) not captured above related test and measurement equipment. Identify the related WBS subassemblies associated with the other major subsystems. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.8.2 | Support and Handling Equipment | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.7.2 Support and Handling Equipment. The peculiar or unique tools and handling equipment used for support of the mission system at an organizational, intermediate, or depot level Includes, for example: a. Ground support equipment, vehicular support equipment, powered support equipment, non-powered support equipment, munitions material handling equipment, materiel handling equipment, and software support equipment (hardware and software)
1.8.2.1 | Support and Handling Equipment (Airframe/Hull/Vehicle) | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.7.2.1 Support and Handling Equipment (Airframe/Hull/Vehicle). This element captures the cost of the airframe, ship hull, or ground vehicle hull/frame related support and handling equipment. Identify the related WBS subassemblies associated with airframe/hull/vehicle. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.8.2.2 | Support and Handling Equipment (Propulsion) | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.7.2.2 Support and Handling Equipment (Propulsion). This element captures the cost of propulsion related support and handling equipment. Identify the related WBS subassemblies associated with propulsion. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.8.2.3 | Support and Handling Equipment (Electronics/Avionics) | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.7.2.3 Support and Handling Equipment (Electronics/Avionics). This element captures the cost of the electronics/avionics related support and handling equipment. Identify the related WBS subassemblies associated with electronics/avionics. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.8.2.4 | Support and Handling Equipment (Other Major Subsystems 1...n (Specify)) | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.7.2.4 Support and Handling Equipment (Other Major Subsystem 1...n (Specify)). This element captures the cost of other major subsystems (e.g., armament, weapons, vehicle subsystems, etc.) not captured above related support and handling equipment. Identify the related WBS subassemblies associated with the other major subsystems. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.9 | Common Support Equipment | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.8 Common Support Equipment. The items required to support and maintain the system or portions of the system while not directly engaged in the performance of its mission, and which are presently in the DoD inventory for support of other systems. Includes, for example: a. Acquisition of additional quantities of this equipment needed to support the item b. All efforts required to assure the availability of this equipment to support the item
1.9.1 | Test and Measurement Equipment | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.8.1 Test and Measurement Equipment. The common testing and measurement equipment that allows an operator or maintenance function to evaluate operational conditions of a system or equipment by performing specific diagnostics, screening, or quality assurance effort at an organizational, intermediate, or depot level of equipment support. Includes, for example: a. Test measurement and diagnostic equipment, precision measuring equipment, automatic test equipment, manual test equipment, automatic test systems, test program sets, appropriate interconnect devices, automated load modules, tapes, and related software, firmware, and support hardware (power supply equipment, etc.) Used at all levels of maintenance b. Packages that enable line or shop replaceable units, printed circuit boards, or similar items to be diagnosed using automatic test equipment
1.9.1.1 | Test and Measurement Equipment (Airframe/Hull/Vehicle) | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.8.1.1 Test and Measurement Equipment (Airframe/Hull/Vehicle). This element captures the cost of the airframe, ship hull, or ground vehicle hull/frame related test and measurement equipment. Identify the related WBS subassemblies associated with the airframe/hull/vehicle. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.9.1.2 | Test and Measurement Equipment (Propulsion) | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.8.1.2 Test and Measurement Equipment (Propulsion). This element captures the cost of the propulsion system, engines, prime movers, turbines, etc. related test and measurement equipment. Identify the related WBS subassemblies associated with propulsion. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.9.1.3 | Test and Measurement Equipment (Electronics/Avionics) | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.8.1.3 Test and Measurement Equipment (Electronics/Avionics). This element captures the cost of the electronics/avionics related test and measurement equipment. Identify the related WBS subassemblies associated with electronics/avionics. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.9.1.4 | Test and Measurement Equipment (Other Major Subsystems 1...n (Specify)) | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.8.1.4 Test and Measurement Equipment (Other Major Subsystem 1...n (Specify)). This element captures the cost of other major subsystems (e.g., armament, weapons, vehicle subsystems, etc.) not captured above related test and measurement equipment. Identify the related WBS subassemblies associated with the other major subsystems. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.9.2 | Support and Handling Equipment | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.8.2 Support and Handling Equipment. The common tools and handling equipment used for support of the mission system at an organizational, intermediate, or depot level Includes, for example: a. Ground support equipment, vehicular support equipment, powered support equipment, non-powered support equipment, munitions material handling equipment, materiel handling equipment, and software support equipment (hardware/software)
1.9.2.1 | Support and Handling Equipment (Airframe/Hull/Vehicle) | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.8.2.1 Support and Handling Equipment (Airframe/Hull/Vehicle). This element captures the cost of the airframe, ship hull, or ground vehicle hull/frame related support and handling equipment. Identify the related WBS subassemblies associated with airframe/hull/vehicle. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.9.2.2 | Support and Handling Equipment (Propulsion) | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.8.2.2 Support and Handling Equipment (Propulsion). This element captures the cost of propulsion related support and handling equipment. Identify the related WBS subassemblies associated with propulsion. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.9.2.3 | Support and Handling Equipment (Electronics/Avionics) | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.8.2.3 Support and Handling Equipment (Electronics/Avionics). This element captures the cost of the electronics/avionics related support and handling equipment. Identify the related WBS subassemblies associated with electronics/avionics. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.9.2.4 | Support and Handling Equipment (Other Major Subsystems 1...n (Specify)) | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.8.2.4 Support and Handling Equipment (Other Major Subsystem 1...n (Specify)). This element captures the cost of other major subsystems (e.g., armament, weapons, vehicle subsystems, etc.) not captured above related support and handling equipment. Identify the related WBS subassemblies associated with the other major subsystems. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.1 | Operational/Site Activation by Site 1...n (Specify) | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.9 Operational/Site Activation by Site 1...n (Specify). The real estate, construction, conversion, utilities, and equipment to provide all facilities required to house, service, and launch prime mission equipment at the organizational and intermediate level. Includes, for example: a. Conversion of site, ship, or vehicle b. System assembly, checkout, and installation (of mission and support equipment) into site facility or ship to achieve operational status c. Contractor support in relation to operational/site activation
1.10.1 | System Assembly, Installation, and Checkout | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.9.1 System Assembly, Installation, and Checkout. The materials and services involved in the assembly of mission equipment at the site. Includes, for example: a. Installation of mission and support equipment in the operations or support facilities and complete system checkout or shakedown to ensure operational status. Where appropriate, specify by site, ship, or vehicle. b. The efforts and activities associated with shipping the system from contractor facility to customer site. That site could be a DT&E site, an installation and checkout site, or any similar site that is outside the direct control of the contractor. Excludes, for example: a. Field team installation
1.10.2 | Contractor Technical Support | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.9.2 Contractor Technical Support. The materials and services provided by the contractor related to activation. Includes, for example: a. Repair of reparables, standby services, and final turnover
1.10.3 | Site Construction | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.9.3 Site Construction. Real estate, site planning and preparation, construction, and other special-purpose facilities necessary to achieve system operational status. Includes, for example: a. Construction of utilities, roads, and interconnecting cabling
1.10.4 | Site/Ship/Vehicle Conversion | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.9.4 Site/Ship/Vehicle Conversion. The materials and services required to convert existing sites, ships, or vehicles to accommodate the mission equipment and selected support equipment directly related to the specific system. Includes, for example: a. Operations, support, and other special purpose facilities conversion necessary to achieve system operational status, e.g., launch. Where appropriate, specify by site, ship, or vehicle
1.10.5 | Interim Contractor Support | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.9.5 Interim Contractor Support (ICS). The effort required to provide temporary contractor support in lieu of a permanent support solution (organic or commercial) for a predetermined time, while a permanent support capability is put in place. Interim support is usually required for support of prototypes and early test and production assets during development and initial fielding (i.e., Initial Operating Capability (IOC)). Includes, for example: a. Providing life cycle logistics in accordance with the integrated product support (IPS) elements in support of the prime mission product. Excludes, for example: a. The development and production of the original prime mission product.
1.11 | Contractor Logistics Support (CLS) | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.10 Contractor Logistics Support (CLS). Contracted weapon system sustainment including performance of maintenance and/or materiel management functions for a DoD weapon system by a commercial activity or contractor sustainment of a weapon system that is intended to start after a permanent decision is made to cover the operations and support efforts of the weapon system. CLS generally starts before FOC (final operating capability) or when performance based logistics (PBL) is implemented in the operating and support (O&S) phase. Includes, for example: a. Prime Mission Product (PMP) maintenance and refurbishment. The cost for this element includes maintenance and refurbishment (including the development and production) of existing operational systems. b. Support functions required to maintain the system, such as sustaining engineering, program management, logistics support, and supply chain management c. Test and evaluation for system and subsystem modifications d. Repair of reparable items; replacement of condemned items (including all PMP, support equipment, and training equipment) e. Operational, maintenance and other personnel required at the operational unit level f. Unit operations costs, including operating material and support services at the operating unit g. Installation and personnel support functions in support of the unit level manpower Excludes, for example: a. Does not include interim contractor support (ICS), a temporary measure for a system’s initial period of operation before a permanent form of support is in place. b. Contractor sustainment support for a specific sustainment task that a service would otherwise conduct itself.
1.12 | Industrial Facilities | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.11 Industrial Facilities. The construction, conversion, or expansion of industrial facilities for production, inventory, and contractor depot maintenance required when that service is for the specific system. Includes, for example: a. Equipment acquisition or modernization, where applicable b. Maintenance of these facilities or equipment c. Industrial facilities for hazardous waste management to satisfy environmental standards Excludes, for example: a. Capital equipment
1.12.1 | Construction/Conversion/Expansion | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.11.1 Construction/Conversion/Expansion. The real estate and preparation of system peculiar industrial facilities for production, inventory, depot maintenance, and other related activities.
1.12.2 | Equipment Acquisition or Modernization | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.11.2 Equipment Acquisition or Modernization. The production equipment acquisition, modernization, or transfer of equipment for the particular system. This pertains to Government owned and leased equipment under facilities contract.
1.12.3 | Maintenance (Industrial Facilities) | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.11.3 Maintenance (Industrial Facilities). The maintenance, preservation, and repair of industrial facilities and equipment.
1.13 | Initial Spares and Repair Parts | APPENDIX G: GROUND VEHICLE SYSTEMS | K.3.12 Initial Spares and Repair Parts. The deliverable spare components, assemblies, and subassemblies used for initial replacement purposes in the materiel system equipment end item. Includes, for example: a. Repairable spares (reparables) and repair parts required as initial stockage to support and maintain newly fielded systems or subsystems during the initial phase of service, including pipeline and war reserve quantities, at all levels of maintenance and support. Lower level WBS breakouts should be by subsystem. b. Spare training and support equipment items c. The combination of resources, processes, planning, procedures, design, considerations, methods, and all hardware to ensure that all system, equipment, and support items are preserved, packaged, handled, and transported properly, including environmental considerations, equipment preservation for short and long term storage, and transportability. This includes requirements such as special environmentally controlled, shock isolated containers for transport to and from repair facilities and ensuring proper Care of Supplies in Storage (COSIS) program requirements are followed. Excludes, for example: a. Development test spares and spares provided specifically for use during installation, assembly, and checkout on site

## H
WBS # | WBS Nomenclature | Appendix | WBS Definition
1 | Unmanned Maritime System | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.1 | UMS Integration, Assembly, Test, and Checkout | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2 | Maritime Vehicle | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.1 | Vehicle Integration, Assembly, Test, and Checkout | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.2 | Hull and Structure | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.3 | Propulsion | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.4 | Energy/Storage/Conversion | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.5 | Electrical Power | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.6 | Vehicle Command and Control | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.6.1 | Vehicle Command and Control Integration, Assembly, Test, and Checkout | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.6.2 | Mission Control | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.6.3 | Navigation | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.6.4 | Guidance and Control | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.6.5 | Health Status Monitoring | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.6.6 | Rendezvous, Homing and Docking Systems | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.6.7 | Fire Control | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.6.8 | Vehicle Command and Control Software Release 1...n (Specify) | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.6.9 | Other Vehicle Command and Control 1...n (Specify) | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.7 | Surveillance | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.8 | Communications/Identification | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.9 | Ship Control Systems | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.9.1 | Ship Control System Integration, Assembly, Test, and Checkout | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.9.2 | Steering and Dive Control | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.9.3 | Hovering and Depth Control | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.9.4 | Ballast and Trim | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.9.5 | Maneuvering System | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.9.6 | Ship Control Systems Software Release 1...n (Specify) | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.9.7 | Other Ship Control Systems 1...n (Specify) | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.10 | Auxiliary Systems | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.10.1 | Auxiliary Equipment Integration, Assembly, Test, and Checkout | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.10.2 | Emergency Systems | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.10.3 | Launch and Recovery System | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.10.4 | Environmental Control System | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.10.5 | Anchoring, Mooring and Towing | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.10.6 | Miscellaneous Fluid Systems | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.10.7 | Auxiliary Systems Software Release 1...n (Specify) | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.10.8 | Other Auxiliary Systems 1...n (Specify) | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.2.11 | Vehicle Software Release 1...n (Specify) | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.3 | Payload 1...n (Specify) | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.3.1 | Payload Integration, Assembly, Test, and Checkout | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.3.2 | Survivability Payload 1...n (Specify) | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.3.3 | Intelligence, Surveillance, and Reconnaissance (ISR) Payload 1...n (Specify) | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.3.4 | Armament/Weapons Delivery Payload 1...n (Specify) | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.3.5 | Mission Payload 1...n (Specify) | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.3.6 | Payload Software Release 1...n (Specify) | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.3.7 | Other Payload 1...n (Specify) | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.4 | Shipboard Segment | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.4.1 | Shipboard Segment Integration, Assembly, Test, and Checkout | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.4.2 | Unmanned Maritime System Command and Control Subsystem | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.4.2.1 | Unmanned Maritime System Control Console(s) | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.4.2.2 | Payload Control Console(s) | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.4.3 | Communication Subsystem | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.4.4 | Power Subsystem | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.4.5 | Launch and Recovery Equipment | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.4.6 | Storage Subsystems | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.4.7 | Vehicle Handling Equipment | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.4.8 | Auxiliary Equipment | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.4.9 | Shipboard Software Release 1...n (Specify) | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.4.10 | Other Shipboard Subsystems 1...n (Specify) | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.5 | Shore Segment | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.6 | Transportation Segment/Vehicles | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.7 | UM System Software Release 1...n (Specify) | APPENDIX H: UNMANNED MARITIME SYSTEMS
1.8 | Systems Engineering | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.2 Systems Engineering. The technical and management efforts of directing and controlling a totally integrated engineering effort of a system or program. The following represent many, but not all, of the systems engineering efforts needed for a system or program. If required, one or more areas of effort (e.g., software systems engineering, cybersecurity, etc., may be identified at the next level below systems engineering. In those cases, the remaining totality of systems engineering efforts will be defined as “core systems engineering” at the level equal to the segregated items.
1.8.1 | Software Systems Engineering | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.2.1 Software Systems Engineering. The efforts which encompass software systems technologies, software engineering methods, and management techniques that improve the quality and delivery of software intensive systems and applications. Includes, for example: a. The application of a systematic, disciplined, quantifiable approach to the development and operations and support (O&S) of software b. The determination of software development or software test facility/environment requirements c. Application of systems engineering to software, that is, the systematic application of scientific and technical knowledge, methods, and experience to the design, implementation, testing, and documentation of software d. Analyzing the system requirements allocated to the software, developing the software requirements, developing the software architecture, designing the software, implementing the software in the code, integrating the software components, and testing the software to verify that the software satisfies the specified requirements allocated to the software component of a system or subsystem.
1.8.2 | Integrated Logistics Support (ILS) Systems Engineering | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.2.2 Integrated Logistics Support (ILS) Systems Engineering. The efforts to ensure the integrated planning and action of a number of disciplines in concert with one another to assure system availability. The planning of each element of ILS (e.g., integrated product support (IPS) elements) is developed in coordination with systems engineering and other efforts. Includes, for example: a. Product support management b. Design interface c. Sustaining engineering d. Supply support e. Maintenance planning and management f. Packaging, handling, storage, and transportation g. Technical data h. Support equipment i. Training and training support j. Manpower and personnel k. Facilities and infrastructure l. Computer resources
1.8.3 | Cybersecurity Systems Engineering | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.2.3 Cybersecurity Systems Engineering. The efforts to apply scientific and engineering principles to identify security vulnerabilities and minimize or contain risks associated with these vulnerabilities. Includes, for example: a. Cybersecurity requirements evaluation b. Cyberattack surface characterization c. Cooperative vulnerability identification d. Vulnerability analysis e. System cross-functional cyber analysis f. Advise on RMF compliance tasks/documents (security assessment plan, etc.) g. Security configuration management (assess planned services for risk and impact) h. Develop system-level security architecture i. Design, develop, and implement system security measures that meets technical requirements j. Develop and implement specific security countermeasures for the system k. Develop approaches to mitigate system vulnerabilities l. Ensure the design of hardware, operating systems, and software applications adequately address cybersecurity requirements for the system
1.8.4 | Core Systems Engineering | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.2.4 Core Systems Engineering. The technical and management efforts that establish the technical framework for delivering materiel capabilities and ensure the effective development and delivery of capability through the implementation of a balanced approach with respect to cost, schedule, performance, and risk. This effort uses integrated, disciplined and consistent systems engineering activities and processes for development of resilient systems that are trusted, assured and easily modified. Systems engineering is composed of 16 processes: eight technical processes and eight technical management processes. These processes provide a structured approach to increasing the technical maturity of a system and increasing the likelihood that the capability being developed balances mission performance with cost, schedule, risk, and design constraints. To fulfill that purpose, a program implements the systems engineering technical processes to support the iterative maturation of the system solution or operational need. The technical processes enable the systems engineering team to ensure that the delivered capability accurately reflects the operational needs of the stakeholders. The technical processes include top down design processes such as stakeholder requirements definition, requirements analysis, and architecture design, as well as bottom-up realization processes such as transition, validation, verification, integration, and implementation. The eight technical management processes are implemented across the acquisition life cycle and provide insight and control to assist the program manager and systems engineer to meet performance, schedule, and cost goals. The eight technical processes closely align with the acquisition life cycle phases and include the top-down design processes and bottom-up realization processes that support transformation of operational needs into operational capabilities. The eight technical management processes are: decision analysis, technical planning, technical assessment, requirements management, risk management, configuration management, technical data management, and interface management. Also included are specialty engineering disciplines which bring together the hardware, software, and human elements of the systems. Includes, for example: a. System safety which is applicable to most DoD systems; this reflects the ubiquitous nature of software-driven functions, network connectivity, and systems of systems; specific certifications include safety, security, cybersecurity and airworthiness b. Reliability and maintainability – ensure that design interface and integration of the quantitative systems engineering design characteristics (i.e., reliability, maintainability, etc.) with the functional integrated product support elements c. Quality – ensures configuration item level requirements for the systems and subsystems meet critical functions and key quality attributes. d. Manufacturing and producibility – ensure manufacturing and producibility readiness, processes assessed and demonstrated, and risks identified, managed and reduced throughout the program’s life cycle e. Human systems integration – optimize total system performance and total ownership costs, while ensuring that the system is designed, operated, and maintained to effectively provide the user with the ability to complete their mission; ensure ergonomics, human factors engineering, and cognitive engineering is employed to provide for effective human-machine interfaces; define the human performance characteristics of the user based on the system description, projected characteristics of target occupational specialties, and recruitment and retention trends; establish requirements for the physical environment; determine the most efficient and cost-effective mix of DoD manpower and contract support; develop training options for operators, maintenance and support personnel; ensure that appropriate environmental safety and occupational health; assess risks to personnel and address, in terms of system design, protection from direct threat events and accidents (such as chemical, biological, and nuclear threats). f. System of systems (SoS) and system level architecting, modeling and simulation, verification and validation and external interface definition and management g. For sea systems; the Expanded Ship Work Breakdown Structure (ESWBS), configuration management (811), human factors (892), standardization (893), value engineering (894), and reliability and maintainability (895) elements Excludes, for example: a. Actual design engineering and the production engineering directly related to the WBS element with which it is associated b. Any systems engineering efforts that are called out in software systems engineering, ILS systems engineering, cybersecurity systems engineering, or “other” systems engineering effort separately identified in the WBS.
1.8.5 | Other Systems Engineering 1...n (Specify) | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.2.5 Other Systems Engineering 1...n (Specify). This element should be replaced with other systems engineering elements that cannot be categorized into one of the above elements or need to be separately identified due to high cost, high risk concerns within systems engineering. Each additional element is to be clearly identified and defined.
1.9 | Program Management | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.3 Program Management. The business and administrative planning, organizing, directing, coordinating, controlling, and approval actions designated to accomplish overall program objectives, which are not associated with specific hardware elements and are not included in systems engineering. If required, one or more areas of effort (e.g., software program management, cybersecurity program management, etc.,) may be identified at the next level below program management. In those cases, the remaining totality of program management efforts will be defined as “core program management” at the level equal to the segregated items.
1.9.1 | Software Program Management | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.3.1 Software Program Management. The software program management encompasses the management of the full software life cycle, from conception to deployment. The function focuses at the system level of applying business and project management skills needed to produce high-quality software products. Includes, for example: a. Overseeing requirements analysis and design, and effective implementation and delivery of all fully-tested software b. Ensure sufficient end-user involvement c. Maintain communication among customers, developers, users, and project managers d. Establish realistic or articulated project goals e. Develop accurate estimates of needed resources f. Define system requirements and specifications g. Assure reporting of the project’s status h. Proper management of risks i. Ensure the use of mature technology and handle the project’s complexity
1.9.2 | Integrated Logistics Support (ILS) Program Management | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.3.2 Integrated Logistics Support Program Management. The efforts to manage the planning and execution of the ILS disciplines to assure system acquisition logistics availability. Includes, for example: a. Support element management, defined as the logistics tasks management effort and technical control, and the business management of the support elements. The logistics management function encompasses the support evaluation and supportability assurance required to produce an affordable and supportable defense materiel system. b. Planning and management of all the functions of logistics. Examples are: maintenance support planning and support facilities planning; other support requirements determination; support equipment requirements determination; supply support; packaging, handling, storage, and transportation; provisioning requirements determination and planning; training system requirements determination; computer resource determination; organizational, intermediate, and depot maintenance determination management; and data management
1.9.3 | Cybersecurity Management | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.3.3 Cybersecurity Program Management. The management and understanding of cybersecurity program and its ramifications across the organization (only if costs are collected in this manner). Includes, for example: a. Overseeing cybersecurity risk assessment, management, and mediation b. Cybersecurity threat vectors and mitigation processes c. Ensuring design and management of secure information systems d. Emerging tools and resources for organizational and platform security
1.9.4 | Core Program Management | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.3.4 Core Program Management. The efforts to understand and manage multiple discipline areas in order the successfully accomplish program objectives for development, production, and sustainment of systems to meet the user’s operational needs Includes, for example: a. Cost, schedule, performance measurement management, warranty administration, contract management, vendor liaison, subcontract management, etc. b. For sea systems; the Expanded Ship Work Breakdown Structure (ESWBS), project management (897); data management (896); and supply support (853) elements Excludes, for example: a. Actual program management directly related to another WBS element b. Any program management efforts that are called out in software program management, cybersecurity program management, or “other” program management effort separately identified in the WBS.
1.9.5 | Other Program Management 1...n (Specify) | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.3.5 Other Program Management 1...n (Specify). This element should be replaced with other program management elements that cannot be categorized into one of the above elements or need to be separately identified due to high cost or high risk concerns within program management. Each additional element is to be clearly identified and defined.
1.1 | System Test and Evaluation | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.4 System Test and Evaluation. The use of pilot, prototype, production, or specifically fabricated hardware/software to obtain or validate engineering data on the performance of the system during the developmental phase of the program. It also includes all effort associated with the development of any specialized tools or data in support of the system level test program. Includes, for example: a. Detailed planning, conduct, support, data reduction and reports (excluding the contract data requirements list data) from such testing, and test articles that are functionally configured to represent and test subsystems/components of the defense materiel end item being developed or produced b. Design and production of models, specimens, fixtures and instrumentation c. System level labs that integrate both hardware and software NOTE: Test articles that are functionally configured to represent and test the complete defense materiel end item being developed or produced, are excluded from this WBS element. Excludes, for example: a. All formal and informal testing up through the subsystem level, which can be associated with the hardware/software element acceptance testing NOTE: These excluded efforts are to be included with the appropriate hardware or software elements.
1.10.1 | Development Test and Evaluation | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.4.1 Development Test and Evaluation. The test and evaluation conducted by the developing agency of the DoD component. It includes test and evaluation conducted to: a. Demonstrate that the engineering design and development process is complete b. Demonstrate that the design risks have been minimized c. Demonstrate that the system will meet specifications d. Assess the system’s military utility when introduced e. Determine whether the engineering design is supportable (practical, maintainable, safe, etc.) for operational use f. Provide test data with which to examine and evaluate trade-offs against specification requirements, life cycle cost, and schedule g. Perform the logistics testing efforts to evaluate the achievement of supportability goals, the adequacy of the support package for the system, (e.g., deliverable maintenance tools, test equipment, technical publications, maintenance instructions, and personnel skills and training requirements, etc.) Includes, for example: a. All contractor/system developer in-house effort b. Where applicable, models, tests and associated simulations (e.g., such as wind tunnel, static, drop, and fatigue); integration ground tests; test bed aircraft and associated support; qualification test and evaluation, development flight test, test instrumentation, environmental tests, ballistics, radiological, range and accuracy demonstrations, test facility operations, test equipment (including its support equipment), chase and calibrated pacer aircraft and support thereto, and logistics testing c. For aircraft; avionics integration test composed of the following: i. Test bench/laboratory, including design, acquisition, and installation of basic computers and test equipment that will provide an ability to simulate in the laboratory the operational environment of the avionics system/subsystem ii. Air vehicle equipment, consisting of the avionics and/or other air vehicle subsystem modules that are required by the bench/lab or flying test bed in order to provide a compatible airframe avionics system/subsystem for evaluation purposes iii. Flying test bed, including requirements analysis, design of modifications, lease or purchase of test bed aircraft, modification of aircraft, installation of avionics equipment and instrumentation, and checkout of an existing aircraft used essentially as a flying avionics laboratory iv. Avionics test program, consisting of the effort required to develop test plans/procedures, conduct tests, and analyze hardware and software test results to verify the avionics equipment’s operational capability and compatibility as an integrated air vehicle subsystem v. Software, referring to the effort required to design, code, de-bug, and document software programs necessary to direct the avionics integration test d. For engines: engine military qualification tests and engine preliminary flight rating tests e. For sea systems: model basin, hydrostatic, fatigue, shock, special sea tests and trials, etc., including the Expanded Ship Work Breakdown Structure (ESWBS), trials agenda preparation, data collection and analysis (842); dock and sea trials (9823); and hull vibration survey (9825) elements f. For missiles: test articles such as inert measurement vehicles, launch separation vehicles, separation and control test vehicles, boost test vehicles g. For ordnance: test articles such as ballistic test rounds, inert measurement rounds, dummy rounds, launch separation rounds, etc.
1.10.2 | Operational Test and Evaluation | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.4.2 Operational Test and Evaluation. The test and evaluation conducted by agencies other than the developing command to assess the prospective system’s military utility, operational effectiveness, operational suitability, logistics supportability (including compatibility, inter-operability, reliability, maintainability, logistic requirements, etc.), cost of ownership, and need for any modifications. Includes, for example: a. Initial operational test and evaluation conducted during the development of a system b. Such tests as system demonstration, flight tests, sea trials, mobility demonstrations, on-orbit tests, spin demonstration, stability tests, qualification operational test and evaluation, etc., and support thereto, required to prove the operational capability of the deliverable system. c. Contractor support (e.g., technical assistance, maintenance, labor, material, etc.) consumed during this phase of testing d. Logistics testing efforts to evaluate the achievement of supportability goals and the adequacy of the support for the system (e.g., deliverable maintenance tools, test equipment, technical publications, maintenance instructions, personnel skills and training requirements, and software support facility/environment elements)
1.10.3 | Cybersecurity Test and Evaluation | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.4.3 Cybersecurity System Test and Evaluation. The developmental test and evaluation and operational test and evaluation conducted and monitored by the developing agency of the DoD. The technical efforts of ensuring the confidentiality, integrity, and availability of information and technology by monitoring and defending against cyber (network) attacks. Includes, for example: a. Vulnerability scanning and interpretation b. Vulnerability testing and penetration testing (usually linked to patch management) c. Security information and event management d. Destructive and non-destructive exploitation e. Test conducted in an operational environment with certified red teams f. Cybersecurity compliance tracking and reporting g. Malware scanning, detection, and prevention services h. Security, IT certification, and accreditation compliance services
1.10.4 | Mock-ups/System Integration Labs (SILs) | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.4.4 Mock-ups/System Integration Labs (SILs). The design engineering and production of system or subsystem mock-ups that have special contractual or engineering significance or that are not required solely for the conduct of one of the above elements of testing. SILs are often used in lieu of (or in addition to) mock-ups. SILs are risk reduction facilities where software and hardware can be developed, integrated, tested, and evaluated for both standalone functionality and/or interoperability prior to being fielded. Includes, for example: a. Hardware/lab equipment b. SIL Software (written to simulate the operating environment or written to operate the SIL)
1.10.5 | Test and Evaluation Support | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.4.5 Test and Evaluation Support. The support elements necessary to operate and maintain, during test and evaluation, systems and subsystems, which are not consumed during the testing phase and are not allocated to a specific phase of testing. Includes, for example: a. Repairable spares, repair of reparables, repair parts, consumables, warehousing and distribution of spares and repair parts, test and support equipment, test bed vehicles, drones, surveillance aircraft/chase aircraft, tracking vessels, contractor technical support Excludes, for example: a. Operational and maintenance personnel, special fixtures, special instrumentation, etc., that are utilized and/or consumed in a single element of testing and that should be included under that element of testing
1.10.6 | Test Facilities | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.4.6 Test Facilities. The special test facilities required for performance of the various developmental tests necessary to prove the design and reliability of the system or subsystem. Includes, for example: a. Test tank test fixtures, propulsion test fixtures, white rooms, test chambers, range/targeting facilities Excludes, for example: a. Brick and mortar-type facilities identified as industrial facilities
1.11 | Training | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.5 Training. Deliverable training services, devices, accessories, aids, equipment, and parts used to facilitate instruction through which personnel will learn to operate and maintain the system with maximum efficiency. Includes, for example: a. All effort associated with the design, development, and production of deliverable training equipment and its associated software as well as the execution of training services Excludes, for example: a. Overall planning, management, and task analysis functions inherent in the WBS element systems engineering/program management
1.11.1 | Equipment | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.5.1 Equipment. Distinctive deliverable end items of training equipment, assigned by either a contractor or military service, required to meet specific training objectives. Includes, for example: a. Operational and Maintenance Trainers and training equipment including items such as cutaways, mock-ups, and models (e.g. Operator Instructional Equipment, Maintainer Instructional Equipment)
1.11.1.1 | Operator Instructional Equipment | APPENDIX H: UNMANNED MARITIME SYSTEMS | [Blank]
1.11.1.2 | Maintainer Instructional Equipment | APPENDIX H: UNMANNED MARITIME SYSTEMS | [Blank]
1.11.2 | Services | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.5.2 Services. Deliverable training services, accessories, and courseware aids necessary to accomplish the objectives of training. Includes, for example: a. Operational and Maintenance Training Services including courses, course materials; and curriculum required to design, execute, and produce a contractor developed training program and related software programs (e.g. operator instructional services, maintainer instructional services) Excludes, for example: a. Deliverable training data associated with support data (see Data Deliverables 1...n (Specify), Support Data)
1.11.2.1 | Operator Instructional Services | APPENDIX H: UNMANNED MARITIME SYSTEMS | [Blank]
1.11.2.2 | Maintainer Instructional Services | APPENDIX H: UNMANNED MARITIME SYSTEMS | [Blank]
1.11.3 | Facilities | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.5.3 Facilities. The special construction necessary to accomplish training objectives. Includes, for example: a. Modification or rehabilitation of existing training facilities and infrastructure used to accomplish training objectives Excludes, for example: a. Installed equipment used to acquaint the trainee with the system or establish trainee proficiency b. The brick and mortar-type facilities identified as industrial facilities
1.11.4 | Training Software 1...n (Specify) | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.5.4 Training Software Release 1...n (Specify). Updated/upgraded software for training purposes delivered to the field during the acquisition phase.
1.12 | Data | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.6 Data. The deliverable data required to be listed on a contract data requirements list. Includes, for example: a. Only such effort that can be reduced or avoided if the data item is eliminated b. Government-peculiar data; acquiring, assembling, reproducing, packaging and shipping the data c. Transforming data into Government
1.12.1 | Data Deliverables 1...n (Specify) | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.6.1 Data Deliverables 1...n (Specify). Deliverable data which provides technical, engineering, management, support, or other data required for contract delivery. Includes, for example: a. Technical Publications. Technical data, providing instructions for installation, operation, maintenance, training, and support, formatted into a technical manual. Data may be presented in any form regardless of the form or method of recording. Technical orders that meet the criteria of this definition may also be classified as technical manuals. For sea systems: Expanded Ship Work Breakdown Structure (ESWBS), technical manuals and other data (856) element. b. Engineering Data. Recorded scientific or technical information (regardless of the form or method of recording) including computer software documentation. Engineering data defines and documents an engineering design or product configuration (sufficient to allow duplication of the original items) and is used to support production, engineering, and logistics activities. For sea systems; Expanded Ship Work Breakdown Structure (ESWBS), design support, ship’s selected records (8302); design support, services, reproduction (8303); and engineering drawings and specifications (855) elements. c. Management Data. The data items necessary for configuration management, cost, schedule, contractual data management, program management, etc., required by the Government. For sea systems; Expanded Ship Work Breakdown Structure (ESWBS), contract data requirements (988) element. d. Support Data. The data items designed to document support planning in accordance with functional categories
1.12.2 | Data Depository | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.6.2 Data Repository. The activity and enterprise data storage entity (or sometimes entities) for Government approved documents that are the property of the Government into which data has been specifically partitioned for analytical or reporting purposes. As custodian for the Government, the repository, authorized by approved change orders, maintains master documents at the latest approved revision level. Includes, for example: a. All effort necessary to maintain documents
1.12.3 | Data Rights 1...n (Specify) | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.6.3 Data Rights 1...n (Specify). Government’s license rights of valuable intellectual property including technical data of any recorded information of a scientific or technical nature (e.g., product design or maintenance data, computer databases, and computer software documentation); and computer software including executable code, source code, code listings, design details, processes, flow charts, and related material. Includes, for example: a. Unlimited Rights. Developed exclusively at Government expense, and certain types of data (e.g., Form, Fit, and Function data (FFF); Operation, Maintenance, Installation, and Training (OMIT)). These rights involve the right to use, modify, reproduce, display, release, or disclose technical data in whole or in part, in any manner, and for any purpose whatsoever, and to have or authorize others to do so. b. Government Purpose Rights. This right involves the right to use, duplicate, or disclose technical data for Government purposes only, and to have or permit others to do so for Government purposes only. Government purposes include competitive procurement, but do not include the right to permit others to use the data for commercial purposes. c. Limited Rights. A limited rights agreement permits the Government to use proprietary technical data in whole or in part. It also means that the Government has to obtain the expressed permission of the party providing the technical data to release it, or disclose it, outside the Government.
1.13 | Peculiar Support Equipment | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.7 Peculiar Support Equipment. The design, development, and production of those deliverable items and associated software required to support and maintain the system or portions of the system while the system is not directly engaged in the performance of its mission, and which are not common support equipment. Items should be designated by commodity subassembly (airframe, engine, avionics, etc.). Includes, for example: a. Vehicles, equipment, tools, etc., used to fuel, service, transport, hoist, repair, overhaul, assemble, disassemble, test, inspect, or otherwise maintain mission equipment b. Any production of duplicate or modified factory test or tooling equipment delivered to the Government for use in maintaining the system. (Factory test and tooling equipment initially used by the contractor in the production process but subsequently delivered to the Government will be included as cost of the item produced.) c. Any additional equipment or software required to maintain or modify the software portions of the system Excludes, for example: a. Overall planning, management, and task analysis functions inherent in the work breakdown structure elements Systems Engineering and Program Management b. Common support equipment, presently in the DoD inventory or commercially available, bought by the using command, not by the acquiring command
1.13.1 | Test and Measurement Equipment | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.7.1 Test and Measurement Equipment. The peculiar or unique testing and measurement equipment that allows an operator or maintenance function to evaluate operational conditions of a system or equipment by performing specific diagnostics, screening, or quality assurance effort at an organizational, intermediate, or depot level of equipment support. Includes, for example: a. Test measurement and diagnostic equipment, precision measuring equipment, automatic test equipment, manual test equipment, automatic test systems, test program sets, appropriate interconnect devices, automated load modules, tapes, and related software, firmware and support hardware (power supply equipment, etc.) used at all levels of maintenance b. Packages that enable line or shop replaceable units, printed circuit boards, or similar items to be diagnosed using automatic test equipment
1.13.1.1 | Test and Measurement Equipment (Airframe/Hull/Vehicle) | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.7.1.1 Test and Measurement Equipment (Airframe/Hull/Vehicle). This element captures the cost of the airframe, ship hull, or ground vehicle hull/frame related test and measurement equipment. Identify the related WBS subassemblies associated with the airframe/hull/vehicle. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested
1.13.1.2 | Test and Measurement Equipment (Propulsion) | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.7.1.2 Test and Measurement Equipment (Propulsion). This element captures the cost of the propulsion system, engines, prime movers, turbines, etc. related test and measurement equipment. Identify the related WBS subassemblies associated with propulsion. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.13.1.3 | Test and Measurement Equipment (Electronics/Avionics) | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.7.1.3 Test and Measurement Equipment (Electronics/Avionics). This element captures the cost of the electronics/avionics related test and measurement equipment. Identify the related WBS subassemblies associated with electronics/avionics. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.13.1.4 | Test and Measurement Equipment (Other Major Subsystems 1...n (Specify)) | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.7.1.4 Test and Measurement Equipment (Other Major Subsystem 1...n (Specify)). This element captures the cost of other major subsystems (e.g., armament, weapons, vehicle subsystems, etc.) not captured above related test and measurement equipment. Identify the related WBS subassemblies associated with the other major subsystems. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.13.2 | Support and Handling Equipment | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.7.2 Support and Handling Equipment. The peculiar or unique tools and handling equipment used for support of the mission system at an organizational, intermediate, or depot level Includes, for example: a. Ground support equipment, vehicular support equipment, powered support equipment, non-powered support equipment, munitions material handling equipment, materiel handling equipment, and software support equipment (hardware and software)
1.13.2.1 | Support and Handling Equipment (Airframe/Hull/Vehicle) | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.7.2.1 Support and Handling Equipment (Airframe/Hull/Vehicle). This element captures the cost of the airframe, ship hull, or ground vehicle hull/frame related support and handling equipment. Identify the related WBS subassemblies associated with airframe/hull/vehicle. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.13.2.2 | Support and Handling Equipment (Propulsion) | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.7.2.2 Support and Handling Equipment (Propulsion). This element captures the cost of propulsion related support and handling equipment. Identify the related WBS subassemblies associated with propulsion. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.13.2.3 | Support and Handling Equipment (Electronics/Avionics) | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.7.2.3 Support and Handling Equipment (Electronics/Avionics). This element captures the cost of the electronics/avionics related support and handling equipment. Identify the related WBS subassemblies associated with electronics/avionics. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.13.2.4 | Support and Handling Equipment (Other Major Subsystems 1...n (Specify)) | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.7.2.4 Support and Handling Equipment (Other Major Subsystem 1...n (Specify)). This element captures the cost of other major subsystems (e.g., armament, weapons, vehicle subsystems, etc.) not captured above related support and handling equipment. Identify the related WBS subassemblies associated with the other major subsystems. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.14 | Common Support Equipment | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.8 Common Support Equipment. The items required to support and maintain the system or portions of the system while not directly engaged in the performance of its mission, and which are presently in the DoD inventory for support of other systems. Includes, for example: a. Acquisition of additional quantities of this equipment needed to support the item b. All efforts required to assure the availability of this equipment to support the item
1.14.1 | Test and Measurement Equipment | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.8.1 Test and Measurement Equipment. The common testing and measurement equipment that allows an operator or maintenance function to evaluate operational conditions of a system or equipment by performing specific diagnostics, screening, or quality assurance effort at an organizational, intermediate, or depot level of equipment support. Includes, for example: a. Test measurement and diagnostic equipment, precision measuring equipment, automatic test equipment, manual test equipment, automatic test systems, test program sets, appropriate interconnect devices, automated load modules, tapes, and related software, firmware, and support hardware (power supply equipment, etc.) Used at all levels of maintenance b. Packages that enable line or shop replaceable units, printed circuit boards, or similar items to be diagnosed using automatic test equipment
1.14.1.1 | Test and Measurement Equipment (Airframe/Hull/Vehicle) | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.8.1.1 Test and Measurement Equipment (Airframe/Hull/Vehicle). This element captures the cost of the airframe, ship hull, or ground vehicle hull/frame related test and measurement equipment. Identify the related WBS subassemblies associated with the airframe/hull/vehicle. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.14.1.2 | Test and Measurement Equipment (Propulsion) | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.8.1.2 Test and Measurement Equipment (Propulsion). This element captures the cost of the propulsion system, engines, prime movers, turbines, etc. related test and measurement equipment. Identify the related WBS subassemblies associated with propulsion. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.14.1.3 | Test and Measurement Equipment (Electronics/Avionics) | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.8.1.3 Test and Measurement Equipment (Electronics/Avionics). This element captures the cost of the electronics/avionics related test and measurement equipment. Identify the related WBS subassemblies associated with electronics/avionics. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.14.1.4 | Test and Measurement Equipment (Other Major Subsystems 1...n (Specify)) | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.8.1.4 Test and Measurement Equipment (Other Major Subsystem 1...n (Specify)). This element captures the cost of other major subsystems (e.g., armament, weapons, vehicle subsystems, etc.) not captured above related test and measurement equipment. Identify the related WBS subassemblies associated with the other major subsystems. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.14.2 | Support and Handling Equipment | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.8.2 Support and Handling Equipment. The common tools and handling equipment used for support of the mission system at an organizational, intermediate, or depot level Includes, for example: a. Ground support equipment, vehicular support equipment, powered support equipment, non-powered support equipment, munitions material handling equipment, materiel handling equipment, and software support equipment (hardware/software)
1.14.2.1 | Support and Handling Equipment (Airframe/Hull/Vehicle) | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.8.2.1 Support and Handling Equipment (Airframe/Hull/Vehicle). This element captures the cost of the airframe, ship hull, or ground vehicle hull/frame related support and handling equipment. Identify the related WBS subassemblies associated with airframe/hull/vehicle. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.14.2.2 | Support and Handling Equipment (Propulsion) | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.8.2.2 Support and Handling Equipment (Propulsion). This element captures the cost of propulsion related support and handling equipment. Identify the related WBS subassemblies associated with propulsion. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.14.2.3 | Support and Handling Equipment (Electronics/Avionics) | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.8.2.3 Support and Handling Equipment (Electronics/Avionics). This element captures the cost of the electronics/avionics related support and handling equipment. Identify the related WBS subassemblies associated with electronics/avionics. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.14.2.4 | Support and Handling Equipment (Other Major Subsystems 1...n (Specify)) | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.8.2.4 Support and Handling Equipment (Other Major Subsystem 1...n (Specify)). This element captures the cost of other major subsystems (e.g., armament, weapons, vehicle subsystems, etc.) not captured above related support and handling equipment. Identify the related WBS subassemblies associated with the other major subsystems. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested.
1.15 | Operational/Site Activation by Site 1...n (Specify) | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.9 Operational/Site Activation by Site 1...n (Specify). The real estate, construction, conversion, utilities, and equipment to provide all facilities required to house, service, and launch prime mission equipment at the organizational and intermediate level. Includes, for example: a. Conversion of site, ship, or vehicle b. System assembly, checkout, and installation (of mission and support equipment) into site facility or ship to achieve operational status c. Contractor support in relation to operational/site activation
1.15.1 | System Assembly, Installation, and Checkout | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.9.1 System Assembly, Installation, and Checkout. The materials and services involved in the assembly of mission equipment at the site. Includes, for example: a. Installation of mission and support equipment in the operations or support facilities and complete system checkout or shakedown to ensure operational status. Where appropriate, specify by site, ship, or vehicle. b. The efforts and activities associated with shipping the system from contractor facility to customer site. That site could be a DT&E site, an installation and checkout site, or any similar site that is outside the direct control of the contractor. Excludes, for example: a. Field team installation
1.15.2 | Contractor Technical Support | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.9.2 Contractor Technical Support. The materials and services provided by the contractor related to activation. Includes, for example: a. Repair of reparables, standby services, and final turnover
1.15.3 | Site Construction | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.9.3 Site Construction. Real estate, site planning and preparation, construction, and other special-purpose facilities necessary to achieve system operational status. Includes, for example: a. Construction of utilities, roads, and interconnecting cabling
1.15.4 | Site/Ship/Vehicle Conversion | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.9.4 Site/Ship/Vehicle Conversion. The materials and services required to convert existing sites, ships, or vehicles to accommodate the mission equipment and selected support equipment directly related to the specific system. Includes, for example: a. Operations, support, and other special purpose facilities conversion necessary to achieve system operational status, e.g., launch. Where appropriate, specify by site, ship, or vehicle
1.15.5 | Interim Contractor Support (ICS) | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.9.5 Interim Contractor Support (ICS). The effort required to provide temporary contractor support in lieu of a permanent support solution (organic or commercial) for a predetermined time, while a permanent support capability is put in place. Interim support is usually required for support of prototypes and early test and production assets during development and initial fielding (i.e., Initial Operating Capability (IOC)). Includes, for example: a. Providing life cycle logistics in accordance with the integrated product support (IPS) elements in support of the prime mission product. Excludes, for example: a. The development and production of the original prime mission product.
1.16 | Contractor Logistics Support (CLS) | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.10 Contractor Logistics Support (CLS). Contracted weapon system sustainment including performance of maintenance and/or materiel management functions for a DoD weapon system by a commercial activity or contractor sustainment of a weapon system that is intended to start after a permanent decision is made to cover the operations and support efforts of the weapon system. CLS generally starts before FOC (final operating capability) or when performance based logistics (PBL) is implemented in the operating and support (O&S) phase. Includes, for example: a. Prime Mission Product (PMP) maintenance and refurbishment. The cost for this element includes maintenance and refurbishment (including the development and production) of existing operational systems. b. Support functions required to maintain the system, such as sustaining engineering, program management, logistics support, and supply chain management c. Test and evaluation for system and subsystem modifications d. Repair of reparable items; replacement of condemned items (including all PMP, support equipment, and training equipment) e. Operational, maintenance and other personnel required at the operational unit level f. Unit operations costs, including operating material and support services at the operating unit g. Installation and personnel support functions in support of the unit level manpower Excludes, for example: a. Does not include interim contractor support (ICS), a temporary measure for a system’s initial period of operation before a permanent form of support is in place. b. Contractor sustainment support for a specific sustainment task that a service would otherwise conduct itself.
1.17 | Industrial Facilities | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.11 Industrial Facilities. The construction, conversion, or expansion of industrial facilities for production, inventory, and contractor depot maintenance required when that service is for the specific system. Includes, for example: a. Equipment acquisition or modernization, where applicable b. Maintenance of these facilities or equipment c. Industrial facilities for hazardous waste management to satisfy environmental standards Excludes, for example: a. Capital equipment
1.17.1 | Construction/Conversion/Expansion | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.11.1 Construction/Conversion/Expansion. The real estate and preparation of system peculiar industrial facilities for production, inventory, depot maintenance, and other related activities.
1.17.2 | Equipment Acquisition or Modernization | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.11.2 Equipment Acquisition or Modernization. The production equipment acquisition, modernization, or transfer of equipment for the particular system. This pertains to Government owned and leased equipment under facilities contract.
1.17.3 | Maintenance (Industrial Facilities) | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.11.3 Maintenance (Industrial Facilities). The maintenance, preservation, and repair of industrial facilities and equipment.
1.18 | Initial Spares and Repair Parts | APPENDIX H: UNMANNED MARITIME SYSTEMS | K.3.12 Initial Spares and Repair Parts. The deliverable spare components, assemblies, and subassemblies used for initial replacement purposes in the materiel system equipment end item. Includes, for example: a. Repairable spares (reparables) and repair parts required as initial stockage to support and maintain newly fielded systems or subsystems during the initial phase of service, including pipeline and war reserve quantities, at all levels of maintenance and support. Lower level WBS breakouts should be by subsystem. b. Spare training and support equipment items c. The combination of resources, processes, planning, procedures, design, considerations, methods, and all hardware to ensure that all system, equipment, and support items are preserved, packaged, handled, and transported properly, including environmental considerations, equipment preservation for short and long term storage, and transportability. This includes requirements such as special environmentally controlled, shock isolated containers for transport to and from repair facilities and ensuring proper Care of Supplies in Storage (COSIS) program requirements are followed. Excludes, for example: a. Development test spares and spares provided specifically for use during installation, assembly, and checkout on site

## I
WBS # | WBS Nomenclature | Appendix | WBS Definition
1 | Launch Vehicle System | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.1 | Systems Engineering, Integration, Test, Program Management (SEIT/PM) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.1.1 | Systems Engineering (SE) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.1.2 | Assembly, Integration and Test | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.1.3 | Program Management (PM) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.2 | Launch Vehicle | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.2.1 | SEIT/PM | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.2.2 | Stages 1...n (Specify) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.2.2.1 | SEIT/PM | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.2.2.2 | Structures and Mechanisms | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.2.2.3 | Propulsions System | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.2.2.4 | Reaction Control System | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.2.2.5 | Recovery System | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.2.2.6 | Environmental Control System | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.2.2.7 | Stage Peculiar Avionics | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.2.2.8 | Other Systems 1...n (Specify) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.2.3 | Payload Accommodations 1...n (Specify) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.2.3.1 | SEIT/PM | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.2.3.2 | Payload Fairings | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.2.3.3 | Payload Adapter (Pedestals) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.2.3.4 | Mission Unique Hardware (Launch Vehicle) 1...n (Specify) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.2.4 | Avionics | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.2.4.1 | SEIT/PM | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.2.4.2 | Guidance, Navigation, and Control | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.2.4.3 | Power | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.2.4.4 | Data Acquisition and Telemetry | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.2.4.5 | Range Tracking and Safety (Airborne) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.2.4.6 | Flight Software Release 1...n (Specify) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.2.4.7 | Other Avionics 1...n (Specify) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.3 | Mission Integration and Analysis 1...f (Specify) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.3.1 | Mission Standard Integration and Analysis | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.3.2 | Mission Unique Integration and Analysis 1...n (Specify) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.4 | Launch Operations Site 1...n (Specify) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.4.1 | SEIT/PM | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.4.2 | Vehicle Processing and Checkout | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.4.3 | Mission Services | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.4.3.1 | Mission Unique Hardware (Launch Operations) 1...n (Specify) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.4.3.2 | Space Vehicle Processing | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.4.4 | Launch | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.4.5 | Flight Operations | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.4.6 | Post Launch | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.4.6.1 | Recovery Operations and Services | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.4.6.2 | Post Launch Refurbishment | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.4.7 | Site Maintenance | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.4.8 | Base Support | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.4.9 | Range Tracking and Safety (Ground) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.4.9.1 | Range Ground System | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.4.9.2 | Range Operations | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.5 | Launch Site 1...n (Specify) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.5.1 | SEIT/PM | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.5.2 | Operational/Site Activation | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.5.3 | Peculiar Support Equipment | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.5.4 | Ground Command, Control, and Communications (GC3) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.5.4.1 | SEIT/PM | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.5.4.2 | Command, Control, and Communications | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.5.4.3 | Other Ground Command, Control, and Communications 1...n (Specify) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.6 | System Test and Evaluation | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.6.1 | Development Test and Evaluation | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.6.2 | Operational Test and Evaluation | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.6.3 | Cybersecurity Test and Evaluation | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.6.4 | Mock-ups/System Integration labs (SILs) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.6.5 | Test and Evaluation Support | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.6.6 | Test Facilities | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.7 | Training | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.7.1 | Equipment | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.7.1.1 | Operator Instructional Equipment | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.7.1.2 | Maintainer Instructional Equipment | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.7.2 | Services | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.7.2.1 | Operator Instructional Services | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.7.2.2 | Maintainer Instructional Services | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.7.3 | Facilities | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.7.4 | Training Software 1...n (Specify) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.8 | Data | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.8.1 | Data Deliverables 1...n (Specify) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.8.2 | Data Repository | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.8.3 | Data Rights 1...n (Specify) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.9 | Peculiar Support Equipment | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.9.1 | Test and Measurement Equipment | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.9.1.1 | Test and Measurement Equipment (Airframe/Hull/Vehicle) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.9.1.2 | Test and Measurement Equipment (Propulsion) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.9.1.3 | Test and Measurement Equipment (Electronics/Avionics) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.9.1.4 | Test and Measurement Equipment (Other Major Subsystems 1...n (Specify)) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.9.2 | Support and Handling Equipment | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.9.2.1 | Support and Handling Equipment (Airframe/Hull/Vehicle) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.9.2.2 | Support and Handling Equipment (Propulsion) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.9.2.3 | Support and Handling Equipment (Electronics/Avionics) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.9.2.4 | Support and Handling Equipment (Other Major Subsystems 1...n (Specify)) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.1 | Common Support Equipment | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.10.1 | Test and Measurement Equipment | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.10.1.1 | Test and Measurement Equipment (Airframe/Hull/Vehicle) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.10.1.2 | Test and Measurement Equipment (Propulsion) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.10.1.3 | Test and Measurement Equipment (Electronics/Avionics) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.10.1.4 | Test and Measurement Equipment (Other Major Subsystems 1...n (Specify)) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.10.2 | Support and Handling Equipment | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.10.2.1 | Support and Handling Equipment (Airframe/Hull/Vehicle) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.10.2.2 | Support and Handling Equipment (Propulsion) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.10.2.3 | Support and Handling Equipment (Electronics/Avionics) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.10.2.4 | Support and Handling Equipment (Other Major Subsystems 1...n (Specify)) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.11 | Industrial Facilities | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.11.1 | Construction/Conversion/Expansion | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.11.2 | Equipment Acquisition or Modernization | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.11.3 | Maintenance (Industrial Facilities) | APPENDIX I: LAUNCH VEHICLE SYSTEMS
1.12 | Initial Spares and Repair Parts | APPENDIX I: LAUNCH VEHICLE SYSTEMS

## J1
WBS # | WBS Nomenclature | Appendix | WBS Definition
1 | Information Systems (IS)/Defense Business Systems (DBS) (Investment) | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.1 | IS/DBS Development/Customization/Configuration | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.1.1 | Custom Application 1...n (Specify) | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.1.1.1 | Subsystem Hardware (Specify) | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.1.1.2 | Subsystem Software CSCI 1...n (Specify) | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.1.1.3 | Subsystem Software Level Integration, Assembly, Test, and Checkout | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.1.2 | Enterprise Service Element 1...n (Specify) | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.1.2.1 | Enterprise Service Element Hardware (Specify) | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.1.2.2 | Enterprise Service Element Software CSCI 1...n (Specify) | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.1.2.3 | Enterprise Service Element Integration, Assembly, Test, and Checkout | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.1.3 | Enterprise/Management Information System 1...n (Specify) | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.1.3.1 | Business Area Hardware (Specify) | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.1.3.2 | Business Area Software CSCI 1...n (Specify) | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.1.3.3 | Business Area Integration, Assembly, Test, and Checkout | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.1.4 | External System Interface Development 1...n (Specify) | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.1.4.1 | External System Interface Hardware (Specify) | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.1.4.2 | External System Interface Software CSCI 1...n (Specify) | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.1.4.3 | External System Interface Integration, Assembly, Test, and Checkout | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.1.5 | System Level Hardware (Specify) | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.2 | System Level Integration | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.3 | Systems Engineering | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.3.1 | Software Systems Engineering | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.3.2 | Integrated Logistics Support (ILS) Systems Engineering | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.3.3 | Cybersecurity Systems Engineering | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.3.4 | Core Systems Engineering | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.3.5 | Other Systems Engineering 1...n (Specify) | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.4 | Program Management | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.4.1 | Software Program Management | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.4.2 | Integrated Logistics Support (ILS) Program Management | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.4.3 | Cybersecurity Program Management | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.4.4 | Core Program Management | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.4.5 | Other Program Management 1...n (Specify) | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.5 | Change Management | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.6 | Data Management | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.7 | System Test and Evaluation | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.7.1 | Development Test and Evaluation | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.7.2 | Operational Test and Evaluation | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.7.3 | Cybersecurity Test and Evaluation | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.7.4 | Mock-ups/System Integration Labs (SILs) | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.7.5 | Test Facilities | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.8 | Training | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.8.1 | Equipment | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.8.2 | Services | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.8.3 | Facilities | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.8.4 | Training Software 1...n (Specify) | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.9 | Data | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.9.1 | Data Deliverables 1...n (Specify) | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.9.2 | Data Repository | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.9.3 | Data Rights 1...n (Specify) | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.1 | Peculiar Support Equipment | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.10.1 | Test and Measurement Equipment | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.10.2 | Support and Handling Equipment | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.11 | Common Support Equipment | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.11.1 | Test and Measurement Equipment | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.11.2 | Support and Handling Equipment | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.12 | Operational Infrastructure/Site Activation By Site 1...n (Specify) | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.12.1 | Initial Hardware Procurement | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.12.1.1 | End User Equipment | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.12.1.2 | Cybersecurity Equipment | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.12.1.3 | IT Infrastructure and Enterprise Software Equipment | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.12.1.4 | Other 1...n (Specify) | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.12.2 | Initial Software License Procurement | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.12.2.1 | End User Software License | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.12.2.2 | Cybersecurity Software Licenses/Services | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.12.2.3 | IT Infrastructure and Equipment | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.12.2.4 | Other 1...n (Specify) | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.12.3 | Initial Software Release (Pre-IOC) Modification/Enhancement | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.12.3.1 | Routine Fixes/Deficiency Correction | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.12.3.2 | Deployment Independent Verification and Validation | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.12.3.3 | Installation/Test | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.12.4 | Site Activation | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.12.4.1 | Data Migration | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.12.4.2 | User Training | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.12.4.3 | User Documentation | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.12.4.4 | Management/Engineering Support | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.12.4.5 | Site Installation, Test, and Checkout | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.12.5 | Interim Operations and Support (Pre-IOC) | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.12.5.1 | Help Desk | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.12.5.2 | System Database Administrator | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.12.5.3 | Installation, Test, and Checkout | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.12.5.4 | IT Equipment Maintenance | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.13 | Industrial Facilities | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.13.1 | Construction/Conversion/Expansion | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.13.2 | Equipment Acquisition or Modernization | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.13.3 | Maintenance (Industrial Facilities) | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)
1.14 | Initial Spares and Repair Parts | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (INVESTMENT)

## J2
WBS # | WBS Nomenclature | Appendix | WBS Definition
2 | Information Systems/Defense Business Systems (IS/DBS) (Sustainment) | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.1 | Program Management | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.2 | Systems/Sustainment Engineering | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.3 | Change Management | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.4 | Help Desk | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.5 | Data Cleansing/Data Maintenance | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.6 | System/Database Administration | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.7 | IT Infrastructure/Network Maintenance Support | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.7.1 | IT Infrastructure Hardware/Equipment Maintenance | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.7.2 | IT Infrastructure Software License Support Services | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.7.3 | IT Infrastructure Management | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.7.4 | Other IT Infrastructure Support 1...n (Specify) | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.8 | Operational Hardware Refresh/Upgrade | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.8.1 | End-User Equipment | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.8.2 | Cybersecurity Equipment | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.8.3 | IT Infrastructure and Enterprise Services Equipment | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.8.4 | Other (Specify) | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.9 | Operational Software License Refresh/Update | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.9.1 | End-User Software License | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.9.2 | Cybersecurity Software Licenses/Services | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.9.3 | IT Infrastructure and Enterprise Software Licenses/Services | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.9.4 | Other (Specify) | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.1 | Cybersecurity Maintenance Management | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.10.1 | Cybersecurity Compliance Operations and Tracking | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.10.2 | Follow-on Cybersecurity Test and Evaluation | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.10.3 | Cybersecurity and IT Certification and Accreditation | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.11 | Follow-on User Training | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.12 | System Independent Verification and Validation | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.13 | Continuing System Improvements | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.13.1 | Operational Hardware Modification | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.13.1.1 | Mod Kit Hardware Development | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.13.1.2 | Mod Kit Hardware Procurement | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.13.1.3 | Mod Kit Hardware Installation | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.13.2 | Software Release Modification/Enhancement 1...n (Specify) | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.13.2.1 | Modifications/Enhancements | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.13.2.2 | Routine Fixes and Deficiency Correction | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.13.2.3 | Installation/Test | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.13.2.4 | IAVAs | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.14 | AW/Safety/Networthiness Certification | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)
2.15 | Facilities | APPENDIX J: INFORMATION SYSTEMS/DEFENSE BUSINESS SYSTEMS (SUSTAINMENT)

## K
WBS # | WBS Nomenclature | Appendix | WBS Definition | APPENDIX A: AIRCRAFT SYSTEMS | APPENDIX C: MISSILE/ORDNANCE SYSTEMS | APPENDIX D: STRATEGIC MISSILE SYSTEMS | APPENDIX E: SEA SYSTEMS | APPENDIX G: GROUND VEHICLE SYSTEMS | APPENDIX H: UNMANNED MARITIME SYSTEMS
various | Integration, Assembly, Test, and Checkout | APPENDIX K: COMMON ELEMENTS | K.3.1 Integration, Assembly, Test, and Checkout. In those instances in which an integration, assembly, test, and checkout element is used (Appendices A-D, G, H, and J), this element includes all effort of technical and functional activities associated with the design, development, and production of mating surfaces, structures, equipment, parts, materials, and software required to assemble the subsystem equipment (hardware/software) elements into a mission system (including modification installation) as a whole and not directly part of any other individual subsystem element. When applicable, rate tooling may be shown at the next lower level breakout of integration, assembly, test, and checkout. Includes, for example: a. The development of engineering layouts, determination of overall design characteristics, and determination of requirements of design review b. The set-up, conduct, and review of testing assembled components or subsystems prior to installation c. The detailed production design, producibility engineering planning (PEP), and manufacturing process capability, including the process design development and demonstration effort to achieve compatibility with engineering requirements and the ability to produce economically and consistent quality d. Inspection activities related to receiving, factory and vendor liaison e. Overall design and producibility engineering f. Design maintenance effort and development of functional test procedures g. Detailed production design h. Quality planning and control i. Tooling (initial production facilities, factory support equipment) including planning, design, and fabrication of basic and rate tools and functional test equipment, as well as the maintenance of such equipment j. Production scheduling and expediting k. Administrative engineering l. The joining or mating and final assembly of hardware and software items to form a complete system or subsystem when the effort is performed at the manufacturing facility m. Integration of software (including loading and verification of firmware) n. Conduct of production acceptance testing Excludes, for example: a. All systems engineering, program management, and system test and evaluation that are associated with the overall system NOTE: When an integration, assembly, test, and checkout element is utilized at lower levels of the contract work breakdown structure, it will be summarized into the next higher-level equipment (hardware/software) WBS element and should never be summarized directly into a higher-level integration, assembly, test, and checkout element.
various | Systems Engineering | APPENDIX K: COMMON ELEMENTS | K.3.2 Systems Engineering. The technical and management efforts of directing and controlling a totally integrated engineering effort of a system or program. The following represent many, but not all, of the systems engineering efforts needed for a system or program. If required, one or more areas of effort (e.g., software systems engineering, cybersecurity, etc., may be identified at the next level below systems engineering. In those cases, the remaining totality of systems engineering efforts will be defined as “core systems engineering” at the level equal to the segregated items. | 1.6 | 1.7 | 1.5 | 1.2 | 1.3
various | Software Systems Engineering | APPENDIX K: COMMON ELEMENTS | K.3.2.1 Software Systems Engineering. The efforts which encompass software systems technologies, software engineering methods, and management techniques that improve the quality and delivery of software intensive systems and applications. Includes, for example: a. The application of a systematic, disciplined, quantifiable approach to the development and operations and support (O&S) of software b. The determination of software development or software test facility/environment requirements c. Application of systems engineering to software, that is, the systematic application of scientific and technical knowledge, methods, and experience to the design, implementation, testing, and documentation of software d. Analyzing the system requirements allocated to the software, developing the software requirements, developing the software architecture, designing the software, implementing the software in the code, integrating the software components, and testing the software to verify that the software satisfies the specified requirements allocated to the software component of a system or subsystem. | 1.6.1 | 1.7.1 | 1.5.1 | 1.2.1 | 1.3.1
various | Integrated Logistics Support (ILS) Systems Engineering | APPENDIX K: COMMON ELEMENTS | K.3.2.2 Integrated Logistics Support (ILS) Systems Engineering. The efforts to ensure the integrated planning and action of a number of disciplines in concert with one another to assure system availability. The planning of each element of ILS (e.g., integrated product support (IPS) elements) is developed in coordination with systems engineering and other efforts. Includes, for example: a. Product support management b. Design interface c. Sustaining engineering d. Supply support e. Maintenance planning and management f. Packaging, handling, storage, and transportation g. Technical data h. Support equipment i. Training and training support j. Manpower and personnel k. Facilities and infrastructure l. Computer resources | 1.6.2 | 1.7.2 | 1.5.2 | 1.2.2 | 1.3.2
various | Cybersecurity Systems Engineering | APPENDIX K: COMMON ELEMENTS | K.3.2.3 Cybersecurity Systems Engineering. The efforts to apply scientific and engineering principles to identify security vulnerabilities and minimize or contain risks associated with these vulnerabilities. Includes, for example: a. Cybersecurity requirements evaluation b. Cyberattack surface characterization c. Cooperative vulnerability identification d. Vulnerability analysis e. System cross-functional cyber analysis f. Advise on RMF compliance tasks/documents (security assessment plan, etc.) g. Security configuration management (assess planned services for risk and impact) h. Develop system-level security architecture i. Design, develop, and implement system security measures that meets technical requirements j. Develop and implement specific security countermeasures for the system k. Develop approaches to mitigate system vulnerabilities l. Ensure the design of hardware, operating systems, and software applications adequately address cybersecurity requirements for the system | 1.6.3 | 1.7.3 | 1.5.3 | 1.2.3 | 1.3.3
various | Core Systems Engineering | APPENDIX K: COMMON ELEMENTS | K.3.2.4 Core Systems Engineering. The technical and management efforts that establish the technical framework for delivering materiel capabilities and ensure the effective development and delivery of capability through the implementation of a balanced approach with respect to cost, schedule, performance, and risk. This effort uses integrated, disciplined and consistent systems engineering activities and processes for development of resilient systems that are trusted, assured and easily modified. Systems engineering is composed of 16 processes: eight technical processes and eight technical management processes. These processes provide a structured approach to increasing the technical maturity of a system and increasing the likelihood that the capability being developed balances mission performance with cost, schedule, risk, and design constraints. To fulfill that purpose, a program implements the systems engineering technical processes to support the iterative maturation of the system solution or operational need. The technical processes enable the systems engineering team to ensure that the delivered capability accurately reflects the operational needs of the stakeholders. The technical processes include top down design processes such as stakeholder requirements definition, requirements analysis, and architecture design, as well as bottom-up realization processes such as transition, validation, verification, integration, and implementation. The eight technical management processes are implemented across the acquisition life cycle and provide insight and control to assist the program manager and systems engineer to meet performance, schedule, and cost goals. The eight technical processes closely align with the acquisition life cycle phases and include the top-down design processes and bottom-up realization processes that support transformation of operational needs into operational capabilities. The eight technical management processes are: decision analysis, technical planning, technical assessment, requirements management, risk management, configuration management, technical data management, and interface management. Also included are specialty engineering disciplines which bring together the hardware, software, and human elements of the systems. Includes, for example: a. System safety which is applicable to most DoD systems; this reflects the ubiquitous nature of software-driven functions, network connectivity, and systems of systems; specific certifications include safety, security, cybersecurity and airworthiness b. Reliability and maintainability – ensure that design interface and integration of the quantitative systems engineering design characteristics (i.e., reliability, maintainability, etc.) with the functional integrated product support elements c. Quality – ensures configuration item level requirements for the systems and subsystems meet critical functions and key quality attributes. d. Manufacturing and producibility – ensure manufacturing and producibility readiness, processes assessed and demonstrated, and risks identified, managed and reduced throughout the program’s life cycle e. Human systems integration – optimize total system performance and total ownership costs, while ensuring that the system is designed, operated, and maintained to effectively provide the user with the ability to complete their mission; ensure ergonomics, human factors engineering, and cognitive engineering is employed to provide for effective human-machine interfaces; define the human performance characteristics of the user based on the system description, projected characteristics of target occupational specialties, and recruitment and retention trends; establish requirements for the physical environment; determine the most efficient and cost-effective mix of DoD manpower and contract support; develop training options for operators, maintenance and support personnel; ensure that appropriate environmental safety and occupational health; assess risks to personnel and address, in terms of system design, protection from direct threat events and accidents (such as chemical, biological, and nuclear threats). f. System of systems (SoS) and system level architecting, modeling and simulation, verification and validation and external interface definition and management g. For sea systems; the Expanded Ship Work Breakdown Structure (ESWBS), configuration management (811), human factors (892), standardization (893), value engineering (894), and reliability and maintainability (895) elements Excludes, for example: a. Actual design engineering and the production engineering directly related to the WBS element with which it is associated b. Any systems engineering efforts that are called out in software systems engineering, ILS systems engineering, cybersecurity systems engineering, or “other” systems engineering effort separately identified in the WBS. | 1.6.4 | 1.7.4 | 1.5.7 | 1.2.4 | 1.3.4
various | Other Systems Engineering 1...n (Specify) | APPENDIX K: COMMON ELEMENTS | K.3.2.5 Other Systems Engineering 1...n (Specify). This element should be replaced with other systems engineering elements that cannot be categorized into one of the above elements or need to be separately identified due to high cost, high risk concerns within systems engineering. Each additional element is to be clearly identified and defined. | 1.6.5 | 1.7.5 | 1.5.8 | 1.2.5 | 1.3.5
various | Program Management | APPENDIX K: COMMON ELEMENTS | K.3.3 Program Management. The business and administrative planning, organizing, directing, coordinating, controlling, and approval actions designated to accomplish overall program objectives, which are not associated with specific hardware elements and are not included in systems engineering. If required, one or more areas of effort (e.g., software program management, cybersecurity program management, etc.,) may be identified at the next level below program management. In those cases, the remaining totality of program management efforts will be defined as “core program management” at the level equal to the segregated items. | 1.7 | 1.8 | 1.6 | 1.3 | 1.4
various | Software Program Management | APPENDIX K: COMMON ELEMENTS | K.3.3.1 Software Program Management. The software program management encompasses the management of the full software life cycle, from conception to deployment. The function focuses at the system level of applying business and project management skills needed to produce high-quality software products. Includes, for example: a. Overseeing requirements analysis and design, and effective implementation and delivery of all fully-tested software b. Ensure sufficient end-user involvement c. Maintain communication among customers, developers, users, and project managers d. Establish realistic or articulated project goals e. Develop accurate estimates of needed resources f. Define system requirements and specifications g. Assure reporting of the project’s status h. Proper management of risks i. Ensure the use of mature technology and handle the project’s complexity | 1.7.1 | 1.8.1 | 1.6.1 | 1.3.1 | 1.4.1
various | Integrated Logistics Support (ILS) Program Management | APPENDIX K: COMMON ELEMENTS | K.3.3.2 Integrated Logistics Support Program Management. The efforts to manage the planning and execution of the ILS disciplines to assure system acquisition logistics availability. Includes, for example: a. Support element management, defined as the logistics tasks management effort and technical control, and the business management of the support elements. The logistics management function encompasses the support evaluation and supportability assurance required to produce an affordable and supportable defense materiel system. b. Planning and management of all the functions of logistics. Examples are: maintenance support planning and support facilities planning; other support requirements determination; support equipment requirements determination; supply support; packaging, handling, storage, and transportation; provisioning requirements determination and planning; training system requirements determination; computer resource determination; organizational, intermediate, and depot maintenance determination management; and data management | 1.7.2 | 1.8.2 | 1.6.2 | 1.3.2 | 1.4.2
various | Cybersecurity Management | APPENDIX K: COMMON ELEMENTS | K.3.3.3 Cybersecurity Program Management. The management and understanding of cybersecurity program and its ramifications across the organization (only if costs are collected in this manner). Includes, for example: a. Overseeing cybersecurity risk assessment, management, and mediation b. Cybersecurity threat vectors and mitigation processes c. Ensuring design and management of secure information systems d. Emerging tools and resources for organizational and platform security | 1.7.3 | 1.8.3 | 1.6.3 | 1.3.3 | 1.4.3
various | Core Program Management | APPENDIX K: COMMON ELEMENTS | K.3.3.4 Core Program Management. The efforts to understand and manage multiple discipline areas in order the successfully accomplish program objectives for development, production, and sustainment of systems to meet the user’s operational needs Includes, for example: a. Cost, schedule, performance measurement management, warranty administration, contract management, vendor liaison, subcontract management, etc. b. For sea systems; the Expanded Ship Work Breakdown Structure (ESWBS), project management (897); data management (896); and supply support (853) elements Excludes, for example: a. Actual program management directly related to another WBS element b. Any program management efforts that are called out in software program management, cybersecurity program management, or “other” program management effort separately identified in the WBS. | 1.7.4 | 1.8.4 | 1.6.4 | 1.3.4 | 1.4.4
various | Other Program Management 1...n (Specify) | APPENDIX K: COMMON ELEMENTS | K.3.3.5 Other Program Management 1...n (Specify). This element should be replaced with other program management elements that cannot be categorized into one of the above elements or need to be separately identified due to high cost or high risk concerns within program management. Each additional element is to be clearly identified and defined. | 1.7.5 | 1.8.5 | 1.6.5 | 1.3.5 | 1.4.5
various | System Test and Evaluation | APPENDIX K: COMMON ELEMENTS | K.3.4 System Test and Evaluation. The use of pilot, prototype, production, or specifically fabricated hardware/software to obtain or validate engineering data on the performance of the system during the developmental phase of the program. It also includes all effort associated with the development of any specialized tools or data in support of the system level test program. Includes, for example: a. Detailed planning, conduct, support, data reduction and reports (excluding the contract data requirements list data) from such testing, and test articles that are functionally configured to represent and test subsystems/components of the defense materiel end item being developed or produced b. Design and production of models, specimens, fixtures and instrumentation c. System level labs that integrate both hardware and software NOTE: Test articles that are functionally configured to represent and test the complete defense materiel end item being developed or produced, are excluded from this WBS element. Excludes, for example: a. All formal and informal testing up through the subsystem level, which can be associated with the hardware/software element acceptance testing NOTE: These excluded efforts are to be included with the appropriate hardware or software elements. | 1.8 | 1.8 | 1.6.6 | 1.4 | 1.5
various | Development Test and Evaluation | APPENDIX K: COMMON ELEMENTS | K.3.4.1 Development Test and Evaluation. The test and evaluation conducted by the developing agency of the DoD component. It includes test and evaluation conducted to: a. Demonstrate that the engineering design and development process is complete b. Demonstrate that the design risks have been minimized c. Demonstrate that the system will meet specifications d. Assess the system’s military utility when introduced e. Determine whether the engineering design is supportable (practical, maintainable, safe, etc.) for operational use f. Provide test data with which to examine and evaluate trade-offs against specification requirements, life cycle cost, and schedule g. Perform the logistics testing efforts to evaluate the achievement of supportability goals, the adequacy of the support package for the system, (e.g., deliverable maintenance tools, test equipment, technical publications, maintenance instructions, and personnel skills and training requirements, etc.) Includes, for example: a. All contractor/system developer in-house effort b. Where applicable, models, tests and associated simulations (e.g., such as wind tunnel, static, drop, and fatigue); integration ground tests; test bed aircraft and associated support; qualification test and evaluation, development flight test, test instrumentation, environmental tests, ballistics, radiological, range and accuracy demonstrations, test facility operations, test equipment (including its support equipment), chase and calibrated pacer aircraft and support thereto, and logistics testing c. For aircraft; avionics integration test composed of the following: i. Test bench/laboratory, including design, acquisition, and installation of basic computers and test equipment that will provide an ability to simulate in the laboratory the operational environment of the avionics system/subsystem ii. Air vehicle equipment, consisting of the avionics and/or other air vehicle subsystem modules that are required by the bench/lab or flying test bed in order to provide a compatible airframe avionics system/subsystem for evaluation purposes iii. Flying test bed, including requirements analysis, design of modifications, lease or purchase of test bed aircraft, modification of aircraft, installation of avionics equipment and instrumentation, and checkout of an existing aircraft used essentially as a flying avionics laboratory iv. Avionics test program, consisting of the effort required to develop test plans/procedures, conduct tests, and analyze hardware and software test results to verify the avionics equipment’s operational capability and compatibility as an integrated air vehicle subsystem v. Software, referring to the effort required to design, code, de-bug, and document software programs necessary to direct the avionics integration test d. For engines: engine military qualification tests and engine preliminary flight rating tests e. For sea systems: model basin, hydrostatic, fatigue, shock, special sea tests and trials, etc., including the Expanded Ship Work Breakdown Structure (ESWBS), trials agenda preparation, data collection and analysis (842); dock and sea trials (9823); and hull vibration survey (9825) elements f. For missiles: test articles such as inert measurement vehicles, launch separation vehicles, separation and control test vehicles, boost test vehicles g. For ordnance: test articles such as ballistic test rounds, inert measurement rounds, dummy rounds, launch separation rounds, etc. | 1.8.1 | 1.9.1 | 1.7 | 1.4.1 | 1.5.1
various | Operational Test and Evaluation | APPENDIX K: COMMON ELEMENTS | K.3.4.2 Operational Test and Evaluation. The test and evaluation conducted by agencies other than the developing command to assess the prospective system’s military utility, operational effectiveness, operational suitability, logistics supportability (including compatibility, inter-operability, reliability, maintainability, logistic requirements, etc.), cost of ownership, and need for any modifications. Includes, for example: a. Initial operational test and evaluation conducted during the development of a system b. Such tests as system demonstration, flight tests, sea trials, mobility demonstrations, on-orbit tests, spin demonstration, stability tests, qualification operational test and evaluation, etc., and support thereto, required to prove the operational capability of the deliverable system. c. Contractor support (e.g., technical assistance, maintenance, labor, material, etc.) consumed during this phase of testing d. Logistics testing efforts to evaluate the achievement of supportability goals and the adequacy of the support for the system (e.g., deliverable maintenance tools, test equipment, technical publications, maintenance instructions, personnel skills and training requirements, and software support facility/environment elements) | 1.8.2 | 1.9.2 | 1.7.1 | 1.4.2 | 1.5.2
various | Cybersecurity Test and Evaluation | APPENDIX K: COMMON ELEMENTS | K.3.4.3 Cybersecurity System Test and Evaluation. The developmental test and evaluation and operational test and evaluation conducted and monitored by the developing agency of the DoD. The technical efforts of ensuring the confidentiality, integrity, and availability of information and technology by monitoring and defending against cyber (network) attacks. Includes, for example: a. Vulnerability scanning and interpretation b. Vulnerability testing and penetration testing (usually linked to patch management) c. Security information and event management d. Destructive and non-destructive exploitation e. Test conducted in an operational environment with certified red teams f. Cybersecurity compliance tracking and reporting g. Malware scanning, detection, and prevention services h. Security, IT certification, and accreditation compliance services | 1.8.3 | 1.9.3 | 1.7.2 | 1.4.3 | 1.5.3
various | Mock-ups/System Integration Labs (SILs) | APPENDIX K: COMMON ELEMENTS | K.3.4.4 Mock-ups/System Integration Labs (SILs). The design engineering and production of system or subsystem mock-ups that have special contractual or engineering significance or that are not required solely for the conduct of one of the above elements of testing. SILs are often used in lieu of (or in addition to) mock-ups. SILs are risk reduction facilities where software and hardware can be developed, integrated, tested, and evaluated for both standalone functionality and/or interoperability prior to being fielded. Includes, for example: a. Hardware/lab equipment b. SIL Software (written to simulate the operating environment or written to operate the SIL) | 1.8.4 | 1.9.4 | 1.7.3 | 1.4.4 | 1.5.4
various | Test and Evaluation Support | APPENDIX K: COMMON ELEMENTS | K.3.4.5 Test and Evaluation Support. The support elements necessary to operate and maintain, during test and evaluation, systems and subsystems, which are not consumed during the testing phase and are not allocated to a specific phase of testing. Includes, for example: a. Repairable spares, repair of reparables, repair parts, consumables, warehousing and distribution of spares and repair parts, test and support equipment, test bed vehicles, drones, surveillance aircraft/chase aircraft, tracking vessels, contractor technical support Excludes, for example: a. Operational and maintenance personnel, special fixtures, special instrumentation, etc., that are utilized and/or consumed in a single element of testing and that should be included under that element of testing | 1.8.5 | 1.9.5 | 1.7.4 | 1.4.5 | 1.5.5
various | Test Facilities | APPENDIX K: COMMON ELEMENTS | K.3.4.6 Test Facilities. The special test facilities required for performance of the various developmental tests necessary to prove the design and reliability of the system or subsystem. Includes, for example: a. Test tank test fixtures, propulsion test fixtures, white rooms, test chambers, range/targeting facilities Excludes, for example: a. Brick and mortar-type facilities identified as industrial facilities | 1.8.6 | 1.9.6 | 1.7.5 | 1.4.6 | 1.5.6
various | Training | APPENDIX K: COMMON ELEMENTS | K.3.5 Training. Deliverable training services, devices, accessories, aids, equipment, and parts used to facilitate instruction through which personnel will learn to operate and maintain the system with maximum efficiency. Includes, for example: a. All effort associated with the design, development, and production of deliverable training equipment and its associated software as well as the execution of training services Excludes, for example: a. Overall planning, management, and task analysis functions inherent in the WBS element systems engineering/program management | 1.9 | 1.1 | 1.7.6 | 1.5 | 1.6
various | Equipment | APPENDIX K: COMMON ELEMENTS | K.3.5.1 Equipment. Distinctive deliverable end items of training equipment, assigned by either a contractor or military service, required to meet specific training objectives. Includes, for example: a. Operational and Maintenance Trainers and training equipment including items such as cutaways, mock-ups, and models (e.g. Operator Instructional Equipment, Maintainer Instructional Equipment) | 1.9.1 | 1.10.1 | 1.8 | 1.5.1 | 1.6.1
various | Operator Instructional Equipment | APPENDIX K: COMMON ELEMENTS | [Blank] | 1.9.1.1 | 1.10.1.1 | 1.8.1 | 1.5.1.1 | 1.6.1.1
various | Maintainer Instructional Equipment | APPENDIX K: COMMON ELEMENTS | [Blank] | 1.9.1.2 | 1.10.1.2 | 1.8.1.1 | 1.5.1.2 | 1.6.1.2
various | Services | APPENDIX K: COMMON ELEMENTS | K.3.5.2 Services. Deliverable training services, accessories, and courseware aids necessary to accomplish the objectives of training. Includes, for example: a. Operational and Maintenance Training Services including courses, course materials; and curriculum required to design, execute, and produce a contractor developed training program and related software programs (e.g. operator instructional services, maintainer instructional services) Excludes, for example: a. Deliverable training data associated with support data (see Data Deliverables 1...n (Specify), Support Data) | 1.9.2. | 1.10.2 | 1.8.1.2 | 1.5.2 | 1.6.2
various | Operator Instructional Services | APPENDIX K: COMMON ELEMENTS | [Blank] | 1.9.2.1 | 1.10.2.1 | 1.8.2 | 1.5.2.1 | 1.6.2.1
various | Maintainer Instructional Services | APPENDIX K: COMMON ELEMENTS | [Blank] | 1.9.2.2 | 1.10.2.2 | 1.8.2.1 | 1.5.2.2 | 1.6.2.2
various | Facilities | APPENDIX K: COMMON ELEMENTS | K.3.5.3 Facilities. The special construction necessary to accomplish training objectives. Includes, for example: a. Modification or rehabilitation of existing training facilities and infrastructure used to accomplish training objectives Excludes, for example: a. Installed equipment used to acquaint the trainee with the system or establish trainee proficiency b. The brick and mortar-type facilities identified as industrial facilities | 1.9.3 | 1.10.3 | 1.8.2.2 | 1.5.3 | 1.6.3
various | Training Software 1...n (Specify) | APPENDIX K: COMMON ELEMENTS | K.3.5.4 Training Software Release 1...n (Specify). Updated/upgraded software for training purposes delivered to the field during the acquisition phase. | 1.9.4 | 1.10.4 | 1.8.3 | 1.5.4 | 1.6.4
various | Data | APPENDIX K: COMMON ELEMENTS | K.3.6 Data. The deliverable data required to be listed on a contract data requirements list. Includes, for example: a. Only such effort that can be reduced or avoided if the data item is eliminated b. Government-peculiar data; acquiring, assembling, reproducing, packaging and shipping the data c. Transforming data into Government | 1.1 | 1.11 | 1.8.4 | 1.6 | 1.7
various | Data Deliverables 1...n (Specify) | APPENDIX K: COMMON ELEMENTS | K.3.6.1 Data Deliverables 1...n (Specify). Deliverable data which provides technical, engineering, management, support, or other data required for contract delivery. Includes, for example: a. Technical Publications. Technical data, providing instructions for installation, operation, maintenance, training, and support, formatted into a technical manual. Data may be presented in any form regardless of the form or method of recording. Technical orders that meet the criteria of this definition may also be classified as technical manuals. For sea systems: Expanded Ship Work Breakdown Structure (ESWBS), technical manuals and other data (856) element. b. Engineering Data. Recorded scientific or technical information (regardless of the form or method of recording) including computer software documentation. Engineering data defines and documents an engineering design or product configuration (sufficient to allow duplication of the original items) and is used to support production, engineering, and logistics activities. For sea systems; Expanded Ship Work Breakdown Structure (ESWBS), design support, ship’s selected records (8302); design support, services, reproduction (8303); and engineering drawings and specifications (855) elements. c. Management Data. The data items necessary for configuration management, cost, schedule, contractual data management, program management, etc., required by the Government. For sea systems; Expanded Ship Work Breakdown Structure (ESWBS), contract data requirements (988) element. d. Support Data. The data items designed to document support planning in accordance with functional categories | 1.10.1 | 1.11.1 | 1.9 | 1.6.1 | 1.7.1
various | Data Repository | APPENDIX K: COMMON ELEMENTS | K.3.6.2 Data Repository. The activity and enterprise data storage entity (or sometimes entities) for Government approved documents that are the property of the Government into which data has been specifically partitioned for analytical or reporting purposes. As custodian for the Government, the repository, authorized by approved change orders, maintains master documents at the latest approved revision level. Includes, for example: a. All effort necessary to maintain documents | 1.10.2 | 1.11.2 | 1.9.1 | 1.6.2 | 1.7.2
various | Data Rights 1...n (Specify) | APPENDIX K: COMMON ELEMENTS | K.3.6.3 Data Rights 1...n (Specify). Government’s license rights of valuable intellectual property including technical data of any recorded information of a scientific or technical nature (e.g., product design or maintenance data, computer databases, and computer software documentation); and computer software including executable code, source code, code listings, design details, processes, flow charts, and related material. Includes, for example: a. Unlimited Rights. Developed exclusively at Government expense, and certain types of data (e.g., Form, Fit, and Function data (FFF); Operation, Maintenance, Installation, and Training (OMIT)). These rights involve the right to use, modify, reproduce, display, release, or disclose technical data in whole or in part, in any manner, and for any purpose whatsoever, and to have or authorize others to do so. b. Government Purpose Rights. This right involves the right to use, duplicate, or disclose technical data for Government purposes only, and to have or permit others to do so for Government purposes only. Government purposes include competitive procurement, but do not include the right to permit others to use the data for commercial purposes. c. Limited Rights. A limited rights agreement permits the Government to use proprietary technical data in whole or in part. It also means that the Government has to obtain the expressed permission of the party providing the technical data to release it, or disclose it, outside the Government. | 1.10.3 | 1.11.3 | 1.9.2 | 1.6.3 | 1.7.3
various | Peculiar Support Equipment | APPENDIX K: COMMON ELEMENTS | K.3.7 Peculiar Support Equipment. The design, development, and production of those deliverable items and associated software required to support and maintain the system or portions of the system while the system is not directly engaged in the performance of its mission, and which are not common support equipment. Items should be designated by commodity subassembly (airframe, engine, avionics, etc.). Includes, for example: a. Vehicles, equipment, tools, etc., used to fuel, service, transport, hoist, repair, overhaul, assemble, disassemble, test, inspect, or otherwise maintain mission equipment b. Any production of duplicate or modified factory test or tooling equipment delivered to the Government for use in maintaining the system. (Factory test and tooling equipment initially used by the contractor in the production process but subsequently delivered to the Government will be included as cost of the item produced.) c. Any additional equipment or software required to maintain or modify the software portions of the system Excludes, for example: a. Overall planning, management, and task analysis functions inherent in the work breakdown structure elements Systems Engineering and Program Management b. Common support equipment, presently in the DoD inventory or commercially available, bought by the using command, not by the acquiring command | 1.11 | 1.12 | 1.9.3 | 1.7 | 1.8
various | Test and Measurement Equipment | APPENDIX K: COMMON ELEMENTS | K.3.7.1 Test and Measurement Equipment. The peculiar or unique testing and measurement equipment that allows an operator or maintenance function to evaluate operational conditions of a system or equipment by performing specific diagnostics, screening, or quality assurance effort at an organizational, intermediate, or depot level of equipment support. Includes, for example: a. Test measurement and diagnostic equipment, precision measuring equipment, automatic test equipment, manual test equipment, automatic test systems, test program sets, appropriate interconnect devices, automated load modules, tapes, and related software, firmware and support hardware (power supply equipment, etc.) used at all levels of maintenance b. Packages that enable line or shop replaceable units, printed circuit boards, or similar items to be diagnosed using automatic test equipment | 1.11.1 | 1.12.1 | 1.1 | 1.7.1 | 1.8.1
various | Test and Measurement Equipment (Airframe/Hull/Vehicle) | APPENDIX K: COMMON ELEMENTS | K.3.7.1.1 Test and Measurement Equipment (Airframe/Hull/Vehicle). This element captures the cost of the airframe, ship hull, or ground vehicle hull/frame related test and measurement equipment. Identify the related WBS subassemblies associated with the airframe/hull/vehicle. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested | 1.11.1.1 | 1.12.1.1 | 1.10.1 | 1.7.1.1 | 1.8.1.1
various | Test and Measurement Equipment (Propulsion) | APPENDIX K: COMMON ELEMENTS | K.3.7.1.2 Test and Measurement Equipment (Propulsion). This element captures the cost of the propulsion system, engines, prime movers, turbines, etc. related test and measurement equipment. Identify the related WBS subassemblies associated with propulsion. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested. | 1.11.1.2 | 1.12.1.2 | 1.10.1.1 | 1.7.1.2 | 1.8.1.2
various | Test and Measurement Equipment (Electronics/Avionics) | APPENDIX K: COMMON ELEMENTS | K.3.7.1.3 Test and Measurement Equipment (Electronics/Avionics). This element captures the cost of the electronics/avionics related test and measurement equipment. Identify the related WBS subassemblies associated with electronics/avionics. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested. | 1.11.1.3 | 1.12.1.3 | 1.10.1.2 | 1.7.1.3 | 1.8.1.3
various | Test and Measurement Equipment (Other Major Subsystems 1...n (Specify)) | APPENDIX K: COMMON ELEMENTS | K.3.7.1.4 Test and Measurement Equipment (Other Major Subsystem 1...n (Specify)). This element captures the cost of other major subsystems (e.g., armament, weapons, vehicle subsystems, etc.) not captured above related test and measurement equipment. Identify the related WBS subassemblies associated with the other major subsystems. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested. | 1.11.1.4 | 1.12.1.4 | 1.10.1.3 | 1.7.1.4 | 1.8.1.4
various | Support and Handling Equipment | APPENDIX K: COMMON ELEMENTS | K.3.7.2 Support and Handling Equipment. The peculiar or unique tools and handling equipment used for support of the mission system at an organizational, intermediate, or depot level Includes, for example: a. Ground support equipment, vehicular support equipment, powered support equipment, non-powered support equipment, munitions material handling equipment, materiel handling equipment, and software support equipment (hardware and software) | 1.11.2 | 1.12.2 | 1.10.1.4 | 1.7.2 | 1.8.2
various | Support and Handling Equipment (Airframe/Hull/Vehicle) | APPENDIX K: COMMON ELEMENTS | K.3.7.2.1 Support and Handling Equipment (Airframe/Hull/Vehicle). This element captures the cost of the airframe, ship hull, or ground vehicle hull/frame related support and handling equipment. Identify the related WBS subassemblies associated with airframe/hull/vehicle. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested. | 1.11.2.1 | 1.12.2.1 | 1.10.2 | 1.7.2.1 | 1.8.2.1
various | Support and Handling Equipment (Propulsion) | APPENDIX K: COMMON ELEMENTS | K.3.7.2.2 Support and Handling Equipment (Propulsion). This element captures the cost of propulsion related support and handling equipment. Identify the related WBS subassemblies associated with propulsion. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested. | 1.11.2.2 | 1.12.2.2 | 1.10.2.1 | 1.7.2.2 | 1.8.2.2
various | Support and Handling Equipment (Electronics/Avionics) | APPENDIX K: COMMON ELEMENTS | K.3.7.2.3 Support and Handling Equipment (Electronics/Avionics). This element captures the cost of the electronics/avionics related support and handling equipment. Identify the related WBS subassemblies associated with electronics/avionics. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested. | 1.11.2.3 | 1.12.2.3 | 1.10.2.2 | 1.7.2.3 | 1.8.2.3
various | Support and Handling Equipment (Other Major Subsystems 1...n (Specify)) | APPENDIX K: COMMON ELEMENTS | K.3.7.2.4 Support and Handling Equipment (Other Major Subsystem 1...n (Specify)). This element captures the cost of other major subsystems (e.g., armament, weapons, vehicle subsystems, etc.) not captured above related support and handling equipment. Identify the related WBS subassemblies associated with the other major subsystems. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested. | 1.11.2.4 | 1.12.2.4 | 1.10.2.3 | 1.7.2.4 | 1.8.2.4
various | Common Support Equipment | APPENDIX K: COMMON ELEMENTS | K.3.8 Common Support Equipment. The items required to support and maintain the system or portions of the system while not directly engaged in the performance of its mission, and which are presently in the DoD inventory for support of other systems. Includes, for example: a. Acquisition of additional quantities of this equipment needed to support the item b. All efforts required to assure the availability of this equipment to support the item | 1.12 | 1.13 | 1.10.2.4 | 1.8 | 1.9
various | Test and Measurement Equipment | APPENDIX K: COMMON ELEMENTS | K.3.8.1 Test and Measurement Equipment. The common testing and measurement equipment that allows an operator or maintenance function to evaluate operational conditions of a system or equipment by performing specific diagnostics, screening, or quality assurance effort at an organizational, intermediate, or depot level of equipment support. Includes, for example: a. Test measurement and diagnostic equipment, precision measuring equipment, automatic test equipment, manual test equipment, automatic test systems, test program sets, appropriate interconnect devices, automated load modules, tapes, and related software, firmware, and support hardware (power supply equipment, etc.) Used at all levels of maintenance b. Packages that enable line or shop replaceable units, printed circuit boards, or similar items to be diagnosed using automatic test equipment | 1.12.1 | 1.13.1 | 1.11 | 1.8.1 | 1.9.1
various | Test and Measurement Equipment (Airframe/Hull/Vehicle) | APPENDIX K: COMMON ELEMENTS | K.3.8.1.1 Test and Measurement Equipment (Airframe/Hull/Vehicle). This element captures the cost of the airframe, ship hull, or ground vehicle hull/frame related test and measurement equipment. Identify the related WBS subassemblies associated with the airframe/hull/vehicle. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested. | 1.12.1.1 | 1.13.1.1 | 1.11.1 | 1.8.1.1 | 1.9.1.1
various | Test and Measurement Equipment (Propulsion) | APPENDIX K: COMMON ELEMENTS | K.3.8.1.2 Test and Measurement Equipment (Propulsion). This element captures the cost of the propulsion system, engines, prime movers, turbines, etc. related test and measurement equipment. Identify the related WBS subassemblies associated with propulsion. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested. | 1.12.1.2 | 1.13.1.2 | 1.11.1.1 | 1.8.1.2 | 1.9.1.2
various | Test and Measurement Equipment (Electronics/Avionics) | APPENDIX K: COMMON ELEMENTS | K.3.8.1.3 Test and Measurement Equipment (Electronics/Avionics). This element captures the cost of the electronics/avionics related test and measurement equipment. Identify the related WBS subassemblies associated with electronics/avionics. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested. | 1.12.1.3 | 1.13.1.3 | 1.11.1.2 | 1.8.1.3 | 1.9.1.3
various | Test and Measurement Equipment (Other Major Subsystems 1...n (Specify)) | APPENDIX K: COMMON ELEMENTS | K.3.8.1.4 Test and Measurement Equipment (Other Major Subsystem 1...n (Specify)). This element captures the cost of other major subsystems (e.g., armament, weapons, vehicle subsystems, etc.) not captured above related test and measurement equipment. Identify the related WBS subassemblies associated with the other major subsystems. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested. | 1.12.1.4 | 1.13.1.4 | 1.11.1.3 | 1.8.1.4 | 1.9.1.4
various | Support and Handling Equipment | APPENDIX K: COMMON ELEMENTS | K.3.8.2 Support and Handling Equipment. The common tools and handling equipment used for support of the mission system at an organizational, intermediate, or depot level Includes, for example: a. Ground support equipment, vehicular support equipment, powered support equipment, non-powered support equipment, munitions material handling equipment, materiel handling equipment, and software support equipment (hardware/software) | 1.12.2 | 1.13.2 | 1.11.1.4 | 1.8.2 | 1.9.2
various | Support and Handling Equipment (Airframe/Hull/Vehicle) | APPENDIX K: COMMON ELEMENTS | K.3.8.2.1 Support and Handling Equipment (Airframe/Hull/Vehicle). This element captures the cost of the airframe, ship hull, or ground vehicle hull/frame related support and handling equipment. Identify the related WBS subassemblies associated with airframe/hull/vehicle. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested. | 1.12.2.1 | 1.13.2.1 | 1.11.2 | 1.8.2.1 | 1.9.2.1
various | Support and Handling Equipment (Propulsion) | APPENDIX K: COMMON ELEMENTS | K.3.8.2.2 Support and Handling Equipment (Propulsion). This element captures the cost of propulsion related support and handling equipment. Identify the related WBS subassemblies associated with propulsion. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested. | 1.12.2.2 | 1.13.2.2 | 1.11.2.1 | 1.8.2.2 | 1.9.2.2
various | Support and Handling Equipment (Electronics/Avionics) | APPENDIX K: COMMON ELEMENTS | K.3.8.2.3 Support and Handling Equipment (Electronics/Avionics). This element captures the cost of the electronics/avionics related support and handling equipment. Identify the related WBS subassemblies associated with electronics/avionics. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested. | 1.12.2.3 | 1.13.2.3 | 1.11.2.2 | 1.8.2.3 | 1.9.2.3
various | Support and Handling Equipment (Other Major Subsystems 1...n (Specify)) | APPENDIX K: COMMON ELEMENTS | K.3.8.2.4 Support and Handling Equipment (Other Major Subsystem 1...n (Specify)). This element captures the cost of other major subsystems (e.g., armament, weapons, vehicle subsystems, etc.) not captured above related support and handling equipment. Identify the related WBS subassemblies associated with the other major subsystems. If necessary, further breakdown by maintenance level (operational/intermediate/depot), may be requested. | 1.12.2.4 | 1.13.2.4 | 1.11.2.3 | 1.8.2.4 | 1.9.2.4
various | Operational/Site Activation by Site 1...n (Specify) | APPENDIX K: COMMON ELEMENTS | K.3.9 Operational/Site Activation by Site 1...n (Specify). The real estate, construction, conversion, utilities, and equipment to provide all facilities required to house, service, and launch prime mission equipment at the organizational and intermediate level. Includes, for example: a. Conversion of site, ship, or vehicle b. System assembly, checkout, and installation (of mission and support equipment) into site facility or ship to achieve operational status c. Contractor support in relation to operational/site activation | 1.13 | 1.14 | 1.11.2.4 | 1.9 | 1.1
various | System Assembly, Installation, and Checkout | APPENDIX K: COMMON ELEMENTS | K.3.9.1 System Assembly, Installation, and Checkout. The materials and services involved in the assembly of mission equipment at the site. Includes, for example: a. Installation of mission and support equipment in the operations or support facilities and complete system checkout or shakedown to ensure operational status. Where appropriate, specify by site, ship, or vehicle. b. The efforts and activities associated with shipping the system from contractor facility to customer site. That site could be a DT&E site, an installation and checkout site, or any similar site that is outside the direct control of the contractor. Excludes, for example: a. Field team installation | 1.13.1 | 1.14.1 | 1.12 | 1.9.1 | 1.10.1
various | Contractor Technical Support | APPENDIX K: COMMON ELEMENTS | K.3.9.2 Contractor Technical Support. The materials and services provided by the contractor related to activation. Includes, for example: a. Repair of reparables, standby services, and final turnover | 1.13.2 | 1.14.2 | 1.12.1 | 1.9.2 | 1.10.2
various | Site Construction | APPENDIX K: COMMON ELEMENTS | K.3.9.3 Site Construction. Real estate, site planning and preparation, construction, and other special-purpose facilities necessary to achieve system operational status. Includes, for example: a. Construction of utilities, roads, and interconnecting cabling | 1.13.3 | 1.14.3 | 1.12.2 | 1.9.3 | 1.10.3
various | Site/Ship/Vehicle Conversion | APPENDIX K: COMMON ELEMENTS | K.3.9.4 Site/Ship/Vehicle Conversion. The materials and services required to convert existing sites, ships, or vehicles to accommodate the mission equipment and selected support equipment directly related to the specific system. Includes, for example: a. Operations, support, and other special purpose facilities conversion necessary to achieve system operational status, e.g., launch. Where appropriate, specify by site, ship, or vehicle | 1.13.4 | 1.14.4 | 1.12.3 | 1.9.4 | 1.10.4
various | Interim Contractor Support | APPENDIX K: COMMON ELEMENTS | K.3.9.5 Interim Contractor Support (ICS). The effort required to provide temporary contractor support in lieu of a permanent support solution (organic or commercial) for a predetermined time, while a permanent support capability is put in place. Interim support is usually required for support of prototypes and early test and production assets during development and initial fielding (i.e., Initial Operating Capability (IOC)). Includes, for example: a. Providing life cycle logistics in accordance with the integrated product support (IPS) elements in support of the prime mission product. Excludes, for example: a. The development and production of the original prime mission product. | 1.13.5 | 1.14.5 | 1.12.4 | 1.9.5 | 1.10.5
various | Contractor Logistics Support (CLS) | APPENDIX K: COMMON ELEMENTS | K.3.10 Contractor Logistics Support (CLS). Contracted weapon system sustainment including performance of maintenance and/or materiel management functions for a DoD weapon system by a commercial activity or contractor sustainment of a weapon system that is intended to start after a permanent decision is made to cover the operations and support efforts of the weapon system. CLS generally starts before FOC (final operating capability) or when performance based logistics (PBL) is implemented in the operating and support (O&S) phase. Includes, for example: a. Prime Mission Product (PMP) maintenance and refurbishment. The cost for this element includes maintenance and refurbishment (including the development and production) of existing operational systems. b. Support functions required to maintain the system, such as sustaining engineering, program management, logistics support, and supply chain management c. Test and evaluation for system and subsystem modifications d. Repair of reparable items; replacement of condemned items (including all PMP, support equipment, and training equipment) e. Operational, maintenance and other personnel required at the operational unit level f. Unit operations costs, including operating material and support services at the operating unit g. Installation and personnel support functions in support of the unit level manpower Excludes, for example: a. Does not include interim contractor support (ICS), a temporary measure for a system’s initial period of operation before a permanent form of support is in place. b. Contractor sustainment support for a specific sustainment task that a service would otherwise conduct itself. | 1.14 | 1.15 | 1.12.5 | 1.1 | 1.11
various | Industrial Facilities | APPENDIX K: COMMON ELEMENTS | K.3.11 Industrial Facilities. The construction, conversion, or expansion of industrial facilities for production, inventory, and contractor depot maintenance required when that service is for the specific system. Includes, for example: a. Equipment acquisition or modernization, where applicable b. Maintenance of these facilities or equipment c. Industrial facilities for hazardous waste management to satisfy environmental standards Excludes, for example: a. Capital equipment | 1.15 | 1.16 | 1.12.6 | 1.11 | 1.12
various | Construction/Conversion/Expansion | APPENDIX K: COMMON ELEMENTS | K.3.11.1 Construction/Conversion/Expansion. The real estate and preparation of system peculiar industrial facilities for production, inventory, depot maintenance, and other related activities. | 1.15.1 | 1.16.1 | 1.12.7 | 1.11.1 | 1.12.1
various | Equipment Acquisition or Modernization | APPENDIX K: COMMON ELEMENTS | K.3.11.2 Equipment Acquisition or Modernization. The production equipment acquisition, modernization, or transfer of equipment for the particular system. This pertains to Government owned and leased equipment under facilities contract. | 1.15.2 | 1.16.2 | 1.12.8 | 1.11.2 | 1.12.2
various | Maintenance (Industrial Facilities) | APPENDIX K: COMMON ELEMENTS | K.3.11.3 Maintenance (Industrial Facilities). The maintenance, preservation, and repair of industrial facilities and equipment. | 1.15.3 | 1.16.3 | 1.13 | 1.11.3 | 1.12.3
various | Initial Spares and Repair Parts | APPENDIX K: COMMON ELEMENTS | K.3.12 Initial Spares and Repair Parts. The deliverable spare components, assemblies, and subassemblies used for initial replacement purposes in the materiel system equipment end item. Includes, for example: a. Repairable spares (reparables) and repair parts required as initial stockage to support and maintain newly fielded systems or subsystems during the initial phase of service, including pipeline and war reserve quantities, at all levels of maintenance and support. Lower level WBS breakouts should be by subsystem. b. Spare training and support equipment items c. The combination of resources, processes, planning, procedures, design, considerations, methods, and all hardware to ensure that all system, equipment, and support items are preserved, packaged, handled, and transported properly, including environmental considerations, equipment preservation for short and long term storage, and transportability. This includes requirements such as special environmentally controlled, shock isolated containers for transport to and from repair facilities and ensuring proper Care of Supplies in Storage (COSIS) program requirements are followed. Excludes, for example: a. Development test spares and spares provided specifically for use during installation, assembly, and checkout on site | 1.16 | 1.17 | 1.14 | 1.12 | 1.13